## WorkCrew
ID | Name | Subcontractor | CrewSize | Productivity | Prod_Unit | Cost | Cost_Unit
1 | Slab Crew - 1 | CONTRACTOR1 | 6
2 | Slab Crew - 1 | CONTRACTOR1 | 6
3 | Wall Crew - 1 | CONTRACTOR2 | 2
4 | Wall Crew - 2 | CONTRACTOR2 | 2
5 | Column Crew - 1 | CONTRACTOR3 | 4
6 | Column Crew - 1 | CONTRACTOR3 | 4

## Plan_S_0
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-08 | 2022-03-13 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-14 | 2022-03-19 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-20 | 2022-03-25 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-03-25 | 2022-03-26 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-19 | 2022-03-20 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-11 | 2022-03-12 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-15 | 2022-03-16 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-21 | 2022-03-22 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-03-27 | 2022-03-28 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-19 | 2022-03-21 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-22 | 2022-03-24 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-13 | 2022-03-15 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-16 | 2022-03-18 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-10 | 2022-03-12 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-25 | 2022-03-27 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-03-28 | 2022-03-30 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-26 | 2022-03-31 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-04-01 | 2022-04-06 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-07 | 2022-04-12 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-13 | 2022-04-18 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-18 | 2022-04-19 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-31 | 2022-04-01 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-04-06 | 2022-04-07 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-12 | 2022-04-13 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-04-02 | 2022-04-03 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-04-04 | 2022-04-05 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-04-08 | 2022-04-09 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-14 | 2022-04-15 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-20 | 2022-04-21 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-12 | 2022-04-14 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-15 | 2022-04-17 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-06 | 2022-04-08 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-04-09 | 2022-04-11 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-31 | 2022-04-02 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-04-03 | 2022-04-05 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-18 | 2022-04-20 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-04-21 | 2022-04-23 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-04-19 | 2022-04-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-25 | 2022-04-30 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-05-01 | 2022-05-06 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-07 | 2022-05-12 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-12 | 2022-05-13 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-04-24 | 2022-04-25 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-30 | 2022-05-01 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-06 | 2022-05-07 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-04-26 | 2022-04-27 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-04-28 | 2022-04-29 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-05-02 | 2022-05-03 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-08 | 2022-05-09 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-14 | 2022-05-15 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-06 | 2022-05-08 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-09 | 2022-05-11 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-30 | 2022-05-02 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-05-03 | 2022-05-05 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-24 | 2022-04-26 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-27 | 2022-04-29 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-12 | 2022-05-14 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-15 | 2022-05-17 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-05-13 | 2022-05-18 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-05-19 | 2022-05-24 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-25 | 2022-05-30 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-31 | 2022-06-05 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-05 | 2022-06-06 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-05-18 | 2022-05-19 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-24 | 2022-05-25 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-30 | 2022-05-31 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-05-20 | 2022-05-21 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-05-22 | 2022-05-23 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-05-26 | 2022-05-27 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-06-01 | 2022-06-02 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-07 | 2022-06-08 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-30 | 2022-06-01 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-02 | 2022-06-04 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-24 | 2022-05-26 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-05-27 | 2022-05-29 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-05-18 | 2022-05-20 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-05-21 | 2022-05-23 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-05 | 2022-06-07 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-08 | 2022-06-10 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-06-06 | 2022-06-11 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-06-12 | 2022-06-17 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-18 | 2022-06-23 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-24 | 2022-06-29 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-29 | 2022-06-30 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-06-11 | 2022-06-12 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-06-17 | 2022-06-18 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-23 | 2022-06-24 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-06-13 | 2022-06-14 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-06-15 | 2022-06-16 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-06-19 | 2022-06-20 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-25 | 2022-06-26 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-01 | 2022-07-02 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-23 | 2022-06-25 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-26 | 2022-06-28 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-06-17 | 2022-06-19 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-06-20 | 2022-06-22 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-06-11 | 2022-06-13 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-06-14 | 2022-06-16 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-29 | 2022-07-01 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-02 | 2022-07-04 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-06-30 | 2022-07-05 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-07-06 | 2022-07-11 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-07-12 | 2022-07-17 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-18 | 2022-07-23 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-23 | 2022-07-24 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-07-05 | 2022-07-06 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-07-11 | 2022-07-12 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-17 | 2022-07-18 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-07-07 | 2022-07-08 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-07-09 | 2022-07-10 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-07-13 | 2022-07-14 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-19 | 2022-07-20 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-25 | 2022-07-26 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-07-17 | 2022-07-19 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-20 | 2022-07-22 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-07-11 | 2022-07-13 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-07-14 | 2022-07-16 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-07-05 | 2022-07-07 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-07-08 | 2022-07-10 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-23 | 2022-07-25 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-26 | 2022-07-28 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-07-24 | 2022-07-29 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-07-30 | 2022-08-04 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-08-05 | 2022-08-10 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-08-11 | 2022-08-16 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-08-16 | 2022-08-17 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-07-29 | 2022-07-30 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-08-04 | 2022-08-05 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-08-10 | 2022-08-11 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-07-31 | 2022-08-01 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-08-02 | 2022-08-03 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-08-06 | 2022-08-07 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-08-12 | 2022-08-13 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-08-18 | 2022-08-19 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-08-10 | 2022-08-12 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-08-13 | 2022-08-15 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-08-04 | 2022-08-06 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-08-07 | 2022-08-09 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-07-29 | 2022-07-31 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-08-01 | 2022-08-03 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-08-16 | 2022-08-18 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-08-19 | 2022-08-21 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-08-17 | 2022-08-22 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-08-23 | 2022-08-28 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-08-29 | 2022-09-03 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-09-04 | 2022-09-09 | 1

## Plan_S_1
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-08 | 2022-03-13 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-06-07 | 2022-06-12 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-06-22 | 2022-06-27 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-07-04 | 2022-07-05 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-08 | 2022-03-09 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-14 | 2022-03-15 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-06-29 | 2022-06-30 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-10 | 2022-03-11 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-12 | 2022-03-13 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-18 | 2022-03-19 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-06-26 | 2022-06-27 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-07-02 | 2022-07-03 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-06-25 | 2022-06-27 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-06-22 | 2022-06-24 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-13 | 2022-03-15 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-04-07 | 2022-04-09 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-10 | 2022-03-12 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-07-01 | 2022-07-03 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-28 | 2022-06-30 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-14 | 2022-03-19 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-20 | 2022-03-25 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-06-30 | 2022-07-05 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-07-06 | 2022-07-11 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-07-16 | 2022-07-17 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-25 | 2022-03-26 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-29 | 2022-03-30 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-07-10 | 2022-07-11 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-23 | 2022-03-24 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-20 | 2022-03-21 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-27 | 2022-03-28 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-07-07 | 2022-07-08 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-07-13 | 2022-07-14 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-07-06 | 2022-07-08 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-07-09 | 2022-07-11 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-29 | 2022-03-31 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-26 | 2022-03-28 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-19 | 2022-03-21 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-23 | 2022-03-25 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-07-12 | 2022-07-14 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-07-15 | 2022-07-17 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-26 | 2022-03-31 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-01 | 2022-04-06 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-07-12 | 2022-07-17 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-07-18 | 2022-07-23 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-07-28 | 2022-07-29 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-31 | 2022-04-01 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-10 | 2022-04-11 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-07-19 | 2022-07-20 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-04-02 | 2022-04-03 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-04-06 | 2022-04-07 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-08 | 2022-04-09 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-07-22 | 2022-07-23 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-07-25 | 2022-07-26 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-07-21 | 2022-07-23 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-07-18 | 2022-07-20 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-05-10 | 2022-05-12 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-10 | 2022-04-12 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-01 | 2022-04-03 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-04 | 2022-04-06 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-07-24 | 2022-07-26 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-07-27 | 2022-07-29 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-07 | 2022-04-12 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-13 | 2022-04-18 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-07-24 | 2022-07-29 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-07-30 | 2022-08-04 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-08-09 | 2022-08-10 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-14 | 2022-04-15 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-20 | 2022-04-21 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-07-31 | 2022-08-01 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-12 | 2022-04-13 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-16 | 2022-04-17 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-18 | 2022-04-19 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-08-03 | 2022-08-04 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-08-06 | 2022-08-07 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-07-30 | 2022-08-01 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-08-02 | 2022-08-04 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-19 | 2022-04-21 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-22 | 2022-04-24 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-13 | 2022-04-15 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-16 | 2022-04-18 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-08-05 | 2022-08-07 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-08-08 | 2022-08-10 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-19 | 2022-04-24 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-07 | 2022-05-12 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-08-05 | 2022-08-10 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-08-11 | 2022-08-16 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-08-18 | 2022-08-19 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-28 | 2022-04-29 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-16 | 2022-05-17 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-08-12 | 2022-08-13 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-24 | 2022-04-25 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-26 | 2022-04-27 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-14 | 2022-05-15 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-08-15 | 2022-08-16 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-08-21 | 2022-08-22 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-08-11 | 2022-08-13 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-08-14 | 2022-08-16 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-06-04 | 2022-06-06 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-27 | 2022-05-29 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-05-02 | 2022-05-04 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-25 | 2022-04-27 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-08-17 | 2022-08-19 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-08-20 | 2022-08-22 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-29 | 2022-05-04 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-19 | 2022-05-24 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-08-17 | 2022-08-22 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-08-23 | 2022-08-28 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-09-02 | 2022-09-03 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-11 | 2022-05-12 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-31 | 2022-06-01 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-08-24 | 2022-08-25 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-04 | 2022-05-05 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-07 | 2022-05-08 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-28 | 2022-05-29 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-08-26 | 2022-08-27 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-08-30 | 2022-08-31 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-08-26 | 2022-08-28 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-08-23 | 2022-08-25 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-30 | 2022-06-01 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-07 | 2022-06-09 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-13 | 2022-05-15 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-06 | 2022-05-08 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-08-29 | 2022-08-31 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-09-01 | 2022-09-03 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-13 | 2022-05-18 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-01 | 2022-06-06 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-08-29 | 2022-09-03 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-09-04 | 2022-09-09 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-09-12 | 2022-09-13 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-23 | 2022-05-24 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-09 | 2022-06-10 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-09-08 | 2022-09-09 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-19 | 2022-05-20 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-21 | 2022-05-22 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-07 | 2022-06-08 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-09-05 | 2022-09-06 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-09-14 | 2022-09-15 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-09-07 | 2022-09-09 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-09-04 | 2022-09-06 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-10 | 2022-06-12 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-17 | 2022-06-19 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-18 | 2022-05-20 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-22 | 2022-05-24 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-09-15 | 2022-09-17 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-09-11 | 2022-09-13 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-25 | 2022-05-30 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-14 | 2022-06-19 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-09-10 | 2022-09-15 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-09-16 | 2022-09-21 | 1

## Plan_S_2
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-08 | 2022-03-13 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-06-07 | 2022-06-12 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-06-22 | 2022-06-27 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-07-04 | 2022-07-05 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-08 | 2022-03-09 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-14 | 2022-03-15 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-06-29 | 2022-06-30 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-10 | 2022-03-11 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-12 | 2022-03-13 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-18 | 2022-03-19 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-06-26 | 2022-06-27 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-07-02 | 2022-07-03 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-06-25 | 2022-06-27 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-06-22 | 2022-06-24 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-13 | 2022-03-15 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-04-07 | 2022-04-09 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-10 | 2022-03-12 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-07-01 | 2022-07-03 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-28 | 2022-06-30 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-14 | 2022-03-19 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-20 | 2022-03-25 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-06-30 | 2022-07-05 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-07-06 | 2022-07-11 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-07-16 | 2022-07-17 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-25 | 2022-03-26 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-29 | 2022-03-30 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-07-10 | 2022-07-11 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-23 | 2022-03-24 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-20 | 2022-03-21 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-27 | 2022-03-28 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-07-07 | 2022-07-08 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-07-13 | 2022-07-14 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-07-06 | 2022-07-08 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-07-09 | 2022-07-11 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-29 | 2022-03-31 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-26 | 2022-03-28 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-19 | 2022-03-21 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-23 | 2022-03-25 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-07-12 | 2022-07-14 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-07-15 | 2022-07-17 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-26 | 2022-03-31 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-01 | 2022-04-06 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-07-12 | 2022-07-17 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-07-18 | 2022-07-23 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-07-28 | 2022-07-29 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-31 | 2022-04-01 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-10 | 2022-04-11 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-07-19 | 2022-07-20 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-04-02 | 2022-04-03 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-04-06 | 2022-04-07 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-08 | 2022-04-09 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-07-22 | 2022-07-23 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-07-25 | 2022-07-26 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-07-21 | 2022-07-23 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-07-18 | 2022-07-20 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-05-10 | 2022-05-12 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-10 | 2022-04-12 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-01 | 2022-04-03 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-04 | 2022-04-06 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-07-24 | 2022-07-26 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-07-27 | 2022-07-29 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-07 | 2022-04-12 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-13 | 2022-04-18 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-07-24 | 2022-07-29 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-07-30 | 2022-08-04 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-08-09 | 2022-08-10 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-14 | 2022-04-15 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-20 | 2022-04-21 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-07-31 | 2022-08-01 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-12 | 2022-04-13 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-16 | 2022-04-17 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-18 | 2022-04-19 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-08-03 | 2022-08-04 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-08-06 | 2022-08-07 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-07-30 | 2022-08-01 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-08-02 | 2022-08-04 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-19 | 2022-04-21 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-22 | 2022-04-24 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-13 | 2022-04-15 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-16 | 2022-04-18 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-08-05 | 2022-08-07 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-08-08 | 2022-08-10 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-19 | 2022-04-24 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-07 | 2022-05-12 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-08-05 | 2022-08-10 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-08-11 | 2022-08-16 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-08-18 | 2022-08-19 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-28 | 2022-04-29 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-16 | 2022-05-17 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-08-12 | 2022-08-13 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-24 | 2022-04-25 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-26 | 2022-04-27 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-14 | 2022-05-15 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-08-15 | 2022-08-16 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-08-21 | 2022-08-22 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-08-11 | 2022-08-13 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-08-14 | 2022-08-16 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-06-04 | 2022-06-06 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-27 | 2022-05-29 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-05-02 | 2022-05-04 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-25 | 2022-04-27 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-08-17 | 2022-08-19 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-08-20 | 2022-08-22 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-29 | 2022-05-04 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-19 | 2022-05-24 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-08-17 | 2022-08-22 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-08-23 | 2022-08-28 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-09-02 | 2022-09-03 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-11 | 2022-05-12 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-31 | 2022-06-01 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-08-24 | 2022-08-25 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-04 | 2022-05-05 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-07 | 2022-05-08 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-28 | 2022-05-29 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-08-26 | 2022-08-27 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-08-30 | 2022-08-31 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-08-26 | 2022-08-28 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-08-23 | 2022-08-25 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-30 | 2022-06-01 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-07 | 2022-06-09 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-13 | 2022-05-15 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-06 | 2022-05-08 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-08-29 | 2022-08-31 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-09-01 | 2022-09-03 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-13 | 2022-05-18 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-01 | 2022-06-06 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-08-29 | 2022-09-03 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-09-04 | 2022-09-09 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-09-12 | 2022-09-13 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-23 | 2022-05-24 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-09 | 2022-06-10 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-09-08 | 2022-09-09 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-19 | 2022-05-20 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-21 | 2022-05-22 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-07 | 2022-06-08 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-09-05 | 2022-09-06 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-09-14 | 2022-09-15 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-09-07 | 2022-09-09 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-09-04 | 2022-09-06 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-10 | 2022-06-12 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-17 | 2022-06-19 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-18 | 2022-05-20 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-22 | 2022-05-24 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-09-15 | 2022-09-17 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-09-11 | 2022-09-13 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-25 | 2022-05-30 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-14 | 2022-06-19 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-09-10 | 2022-09-15 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-09-16 | 2022-09-21 | 1

## Plan_S_3
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-08 | 2022-03-13 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-14 | 2022-03-19 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-20 | 2022-03-25 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-03-25 | 2022-03-26 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-19 | 2022-03-20 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-11 | 2022-03-12 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-15 | 2022-03-16 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-21 | 2022-03-22 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-03-27 | 2022-03-28 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-19 | 2022-03-21 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-22 | 2022-03-24 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-13 | 2022-03-15 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-16 | 2022-03-18 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-10 | 2022-03-12 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-25 | 2022-03-27 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-03-28 | 2022-03-30 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-26 | 2022-03-31 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-04-01 | 2022-04-06 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-07 | 2022-04-12 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-13 | 2022-04-18 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-18 | 2022-04-19 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-31 | 2022-04-01 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-04-06 | 2022-04-07 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-12 | 2022-04-13 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-04-02 | 2022-04-03 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-04-04 | 2022-04-05 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-04-08 | 2022-04-09 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-14 | 2022-04-15 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-20 | 2022-04-21 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-12 | 2022-04-14 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-15 | 2022-04-17 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-06 | 2022-04-08 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-04-09 | 2022-04-11 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-31 | 2022-04-02 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-04-03 | 2022-04-05 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-18 | 2022-04-20 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-04-21 | 2022-04-23 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-04-19 | 2022-04-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-25 | 2022-04-30 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-05-01 | 2022-05-06 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-07 | 2022-05-12 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-12 | 2022-05-13 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-04-24 | 2022-04-25 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-30 | 2022-05-01 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-06 | 2022-05-07 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-04-26 | 2022-04-27 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-04-28 | 2022-04-29 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-05-02 | 2022-05-03 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-08 | 2022-05-09 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-14 | 2022-05-15 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-06 | 2022-05-08 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-09 | 2022-05-11 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-30 | 2022-05-02 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-05-03 | 2022-05-05 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-24 | 2022-04-26 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-27 | 2022-04-29 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-12 | 2022-05-14 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-15 | 2022-05-17 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-05-13 | 2022-05-18 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-05-19 | 2022-05-24 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-25 | 2022-05-30 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-31 | 2022-06-05 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-05 | 2022-06-06 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-05-18 | 2022-05-19 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-24 | 2022-05-25 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-30 | 2022-05-31 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-05-20 | 2022-05-21 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-05-22 | 2022-05-23 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-05-26 | 2022-05-27 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-06-01 | 2022-06-02 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-07 | 2022-06-08 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-30 | 2022-06-01 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-02 | 2022-06-04 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-24 | 2022-05-26 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-05-27 | 2022-05-29 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-05-18 | 2022-05-20 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-05-21 | 2022-05-23 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-05 | 2022-06-07 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-08 | 2022-06-10 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-06-06 | 2022-06-11 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-06-12 | 2022-06-17 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-18 | 2022-06-23 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-24 | 2022-06-29 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-29 | 2022-06-30 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-06-11 | 2022-06-12 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-06-17 | 2022-06-18 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-23 | 2022-06-24 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-06-13 | 2022-06-14 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-06-15 | 2022-06-16 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-06-19 | 2022-06-20 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-25 | 2022-06-26 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-01 | 2022-07-02 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-23 | 2022-06-25 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-26 | 2022-06-28 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-06-17 | 2022-06-19 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-06-20 | 2022-06-22 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-06-11 | 2022-06-13 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-06-14 | 2022-06-16 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-29 | 2022-07-01 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-02 | 2022-07-04 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-06-30 | 2022-07-05 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-07-06 | 2022-07-11 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-07-12 | 2022-07-17 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-18 | 2022-07-23 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-23 | 2022-07-24 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-07-05 | 2022-07-06 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-07-11 | 2022-07-12 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-17 | 2022-07-18 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-07-07 | 2022-07-08 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-07-09 | 2022-07-10 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-07-13 | 2022-07-14 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-19 | 2022-07-20 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-25 | 2022-07-26 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-07-17 | 2022-07-19 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-20 | 2022-07-22 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-07-11 | 2022-07-13 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-07-14 | 2022-07-16 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-07-05 | 2022-07-07 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-07-08 | 2022-07-10 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-23 | 2022-07-25 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-26 | 2022-07-28 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-07-24 | 2022-07-29 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-07-30 | 2022-08-04 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-08-05 | 2022-08-10 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-08-11 | 2022-08-16 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-08-16 | 2022-08-17 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-07-29 | 2022-07-30 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-08-04 | 2022-08-05 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-08-10 | 2022-08-11 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-07-31 | 2022-08-01 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-08-02 | 2022-08-03 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-08-06 | 2022-08-07 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-08-12 | 2022-08-13 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-08-18 | 2022-08-19 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-08-10 | 2022-08-12 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-08-13 | 2022-08-15 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-08-04 | 2022-08-06 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-08-07 | 2022-08-09 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-07-29 | 2022-07-31 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-08-01 | 2022-08-03 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-08-16 | 2022-08-18 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-08-19 | 2022-08-21 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-08-17 | 2022-08-22 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-08-23 | 2022-08-28 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-08-29 | 2022-09-03 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-09-04 | 2022-09-09 | 1

## Plan_S_4
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-10 | 2022-03-15 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-04-03 | 2022-04-08 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-05-03 | 2022-05-08 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-05-10 | 2022-05-11 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-14 | 2022-03-15 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-20 | 2022-03-21 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-04-10 | 2022-04-11 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-18 | 2022-03-19 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-04-14 | 2022-04-15 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-05-13 | 2022-05-14 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-07-20 | 2022-07-22 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-07-23 | 2022-07-25 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-22 | 2022-03-24 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-07-09 | 2022-07-11 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-13 | 2022-03-15 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-17 | 2022-03-19 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-08-05 | 2022-08-07 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-07-26 | 2022-07-28 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-16 | 2022-03-21 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-22 | 2022-03-27 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-15 | 2022-04-20 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-27 | 2022-06-01 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-06-03 | 2022-06-04 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-26 | 2022-03-27 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-04-12 | 2022-04-13 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-30 | 2022-05-01 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-24 | 2022-03-25 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-22 | 2022-03-23 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-04-01 | 2022-04-02 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-05-16 | 2022-05-17 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-06-05 | 2022-06-06 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-27 | 2022-04-29 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-24 | 2022-04-26 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-18 | 2022-04-20 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-04-12 | 2022-04-14 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-31 | 2022-04-02 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-25 | 2022-03-27 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-02 | 2022-06-04 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-06 | 2022-06-08 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-28 | 2022-04-02 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-21 | 2022-04-26 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-05-21 | 2022-05-26 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-06-09 | 2022-06-14 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-16 | 2022-06-17 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-04-03 | 2022-04-04 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-05-02 | 2022-05-03 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-28 | 2022-05-29 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-04-07 | 2022-04-08 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-04-05 | 2022-04-06 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-28 | 2022-04-29 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-26 | 2022-05-27 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-29 | 2022-06-30 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-27 | 2022-05-29 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-30 | 2022-06-01 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-05-03 | 2022-05-05 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-05-09 | 2022-05-11 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-06 | 2022-04-08 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-09 | 2022-04-11 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-14 | 2022-06-16 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-17 | 2022-06-19 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-09 | 2022-04-14 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-05-15 | 2022-05-20 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-06-15 | 2022-06-20 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-07-07 | 2022-07-12 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-08-10 | 2022-08-11 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-19 | 2022-04-20 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-31 | 2022-06-01 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-07-04 | 2022-07-05 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-22 | 2022-04-23 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-25 | 2022-04-26 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-05-20 | 2022-05-21 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-07-02 | 2022-07-03 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-07-18 | 2022-07-19 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-21 | 2022-06-23 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-24 | 2022-06-26 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-21 | 2022-05-23 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-05-24 | 2022-05-26 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-21 | 2022-04-23 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-30 | 2022-05-02 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-07-13 | 2022-07-15 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-08-08 | 2022-08-10 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-27 | 2022-05-02 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-06-03 | 2022-06-08 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-07-24 | 2022-07-29 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-08-12 | 2022-08-17 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-08-22 | 2022-08-23 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-05-06 | 2022-05-07 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-06-20 | 2022-06-21 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-07-30 | 2022-07-31 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-05-04 | 2022-05-05 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-05-08 | 2022-05-09 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-06-22 | 2022-06-23 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-08-03 | 2022-08-04 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-08-19 | 2022-08-20 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-08-01 | 2022-08-03 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-07-29 | 2022-07-31 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-06-10 | 2022-06-12 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-06-27 | 2022-06-29 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-05-06 | 2022-05-08 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-05-12 | 2022-05-14 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-08-18 | 2022-08-20 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-08-21 | 2022-08-23 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-05-09 | 2022-05-14 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-06-28 | 2022-07-03 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-08-06 | 2022-08-11 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-08-24 | 2022-08-29 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-08-30 | 2022-08-31 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-06-09 | 2022-06-10 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-07-27 | 2022-07-28 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-08-28 | 2022-08-29 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-22 | 2022-05-23 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-06-14 | 2022-06-15 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-07-23 | 2022-07-24 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-08-26 | 2022-08-27 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-09-02 | 2022-09-03 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-08-25 | 2022-08-27 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-08-15 | 2022-08-17 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-07-03 | 2022-07-05 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-07-06 | 2022-07-08 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-15 | 2022-05-17 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-18 | 2022-05-20 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-09-02 | 2022-09-04 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-09-14 | 2022-09-16 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-06-21 | 2022-06-26 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-07-30 | 2022-08-04 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-08-30 | 2022-09-04 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-09-05 | 2022-09-10 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-09-15 | 2022-09-16 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-07-13 | 2022-07-14 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-08-12 | 2022-08-13 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-09-06 | 2022-09-07 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-07-16 | 2022-07-17 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-07-10 | 2022-07-11 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-08-16 | 2022-08-17 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-09-09 | 2022-09-10 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-09-12 | 2022-09-13 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-09-05 | 2022-09-07 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-09-08 | 2022-09-10 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-08-29 | 2022-08-31 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-08-11 | 2022-08-13 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-07-16 | 2022-07-18 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-30 | 2022-07-02 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-09-11 | 2022-09-13 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-09-17 | 2022-09-19 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-07-18 | 2022-07-23 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-08-18 | 2022-08-23 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-09-11 | 2022-09-16 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-09-17 | 2022-09-22 | 1

## Plan_S_5
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-08 | 2022-03-13 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-26 | 2022-03-31 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-07 | 2022-04-12 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-05-21 | 2022-05-22 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-12 | 2022-03-13 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-18 | 2022-03-19 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-04-21 | 2022-04-22 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-08 | 2022-03-09 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-10 | 2022-03-11 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-04-03 | 2022-04-04 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-05-14 | 2022-05-15 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-02 | 2022-04-04 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-05 | 2022-04-07 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-16 | 2022-03-18 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-13 | 2022-03-15 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-10 | 2022-03-12 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-04-15 | 2022-04-17 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-04 | 2022-05-06 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-14 | 2022-03-19 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-20 | 2022-03-25 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-05-19 | 2022-05-24 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-25 | 2022-05-30 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-06-05 | 2022-06-06 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-27 | 2022-03-28 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-04-05 | 2022-04-06 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-05-30 | 2022-05-31 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-24 | 2022-03-25 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-20 | 2022-03-21 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-04-11 | 2022-04-12 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-05-25 | 2022-05-26 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-06-01 | 2022-06-02 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-28 | 2022-05-30 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-24 | 2022-05-26 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-29 | 2022-03-31 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-26 | 2022-03-28 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-19 | 2022-03-21 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-23 | 2022-03-25 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-31 | 2022-06-02 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-04 | 2022-06-06 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-04-01 | 2022-04-06 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-13 | 2022-04-18 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-05-31 | 2022-06-05 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-06-06 | 2022-06-11 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-15 | 2022-06-16 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-04-14 | 2022-04-15 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-23 | 2022-04-24 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-06-08 | 2022-06-09 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-04-16 | 2022-04-17 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-04-09 | 2022-04-10 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-19 | 2022-04-20 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-06-10 | 2022-06-11 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-13 | 2022-06-14 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-06-07 | 2022-06-09 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-06-12 | 2022-06-14 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-21 | 2022-04-23 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-18 | 2022-04-20 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-11 | 2022-04-13 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-08 | 2022-04-10 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-16 | 2022-06-18 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-08-08 | 2022-08-10 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-19 | 2022-04-24 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-25 | 2022-04-30 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-06-12 | 2022-06-17 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-18 | 2022-06-23 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-29 | 2022-06-30 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-25 | 2022-04-26 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-03 | 2022-05-04 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-06-17 | 2022-06-18 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-28 | 2022-04-29 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-30 | 2022-05-01 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-05-06 | 2022-05-07 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-06-22 | 2022-06-23 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-27 | 2022-06-28 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-07-15 | 2022-07-17 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-28 | 2022-06-30 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-30 | 2022-05-02 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-05-16 | 2022-05-18 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-27 | 2022-04-29 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-24 | 2022-04-26 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-07-21 | 2022-07-23 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-08-12 | 2022-08-14 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-05-01 | 2022-05-06 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-07 | 2022-05-12 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-24 | 2022-06-29 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-30 | 2022-07-05 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-08-09 | 2022-08-10 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-05-12 | 2022-05-13 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-17 | 2022-05-18 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-07-03 | 2022-07-04 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-05-08 | 2022-05-09 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-05-10 | 2022-05-11 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-06-03 | 2022-06-04 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-07-07 | 2022-07-08 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-08-13 | 2022-08-14 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-07-06 | 2022-07-08 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-07-02 | 2022-07-04 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-13 | 2022-05-15 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-20 | 2022-05-22 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-05-10 | 2022-05-12 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-05-07 | 2022-05-09 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-18 | 2022-07-20 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-10 | 2022-07-12 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-05-13 | 2022-05-18 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-07-06 | 2022-07-11 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-07-24 | 2022-07-29 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-08-18 | 2022-08-23 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-08-26 | 2022-08-27 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-28 | 2022-05-29 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-07-13 | 2022-07-14 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-08-03 | 2022-08-04 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-23 | 2022-05-24 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-19 | 2022-05-20 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-07-11 | 2022-07-12 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-31 | 2022-08-01 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-08-23 | 2022-08-24 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-08-31 | 2022-09-02 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-08-28 | 2022-08-30 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-08-22 | 2022-08-24 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-08-25 | 2022-08-27 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-08-19 | 2022-08-21 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-06-21 | 2022-06-23 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-09-06 | 2022-09-08 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-09-03 | 2022-09-05 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-07-12 | 2022-07-17 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-07-18 | 2022-07-23 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-08-09 | 2022-08-14 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-08-30 | 2022-09-04 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-09-04 | 2022-09-05 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-07-28 | 2022-07-29 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-08-06 | 2022-08-07 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-08-20 | 2022-08-21 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-07-22 | 2022-07-23 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-07-19 | 2022-07-20 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-08-16 | 2022-08-17 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-09-01 | 2022-09-02 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-09-07 | 2022-09-08 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-09-09 | 2022-09-11 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-08-15 | 2022-08-17 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-08-02 | 2022-08-04 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-08-05 | 2022-08-07 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-07-30 | 2022-08-01 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-07-27 | 2022-07-29 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-09-17 | 2022-09-19 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-09-14 | 2022-09-16 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-07-30 | 2022-08-04 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-08-24 | 2022-08-29 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-09-06 | 2022-09-11 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-09-14 | 2022-09-19 | 1

## Plan_D_0
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-12 | 2022-04-17 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-17 | 2022-04-18 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-14 | 2022-03-15 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-17 | 2022-04-18 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-18 | 2022-03-20 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-29 | 2022-03-31 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-14 | 2022-05-16 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-17 | 2022-04-19 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-21 | 2022-04-26 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-28 | 2022-04-29 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-23 | 2022-03-24 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-27 | 2022-03-28 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-28 | 2022-03-29 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-28 | 2022-04-29 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-27 | 2022-03-29 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-03-31 | 2022-04-02 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-21 | 2022-03-23 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-17 | 2022-03-19 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-26 | 2022-04-28 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-04-27 | 2022-04-29 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-10 | 2022-05-15 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-15 | 2022-05-16 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-31 | 2022-04-01 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-06 | 2022-04-07 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-26 | 2022-03-27 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-06 | 2022-04-07 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-15 | 2022-05-16 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-23 | 2022-04-25 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-10 | 2022-05-12 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-19 | 2022-04-21 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-03 | 2022-04-05 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-24 | 2022-03-26 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-24 | 2022-03-26 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-16 | 2022-05-18 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-17 | 2022-05-19 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-03 | 2022-04-08 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-09 | 2022-04-14 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-16 | 2022-05-21 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-21 | 2022-05-22 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-02 | 2022-04-03 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-08 | 2022-04-09 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-14 | 2022-04-15 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-04 | 2022-04-05 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-08 | 2022-04-09 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-15 | 2022-04-16 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-21 | 2022-05-22 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-14 | 2022-04-16 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-15 | 2022-04-17 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-08 | 2022-04-10 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-09 | 2022-04-11 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-05 | 2022-04-07 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-02 | 2022-04-04 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-27 | 2022-05-29 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-27 | 2022-05-29 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-06 | 2022-04-11 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-15 | 2022-04-20 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-03 | 2022-05-08 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-22 | 2022-05-27 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-27 | 2022-05-28 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-11 | 2022-04-12 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-22 | 2022-04-23 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-08 | 2022-05-09 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-13 | 2022-04-14 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-11 | 2022-04-12 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-20 | 2022-04-21 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-08 | 2022-05-09 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-27 | 2022-05-28 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-21 | 2022-05-23 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-13 | 2022-05-15 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-20 | 2022-04-22 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-01 | 2022-05-03 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-11 | 2022-04-13 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-12 | 2022-04-14 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-30 | 2022-06-01 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-06 | 2022-06-08 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-19 | 2022-04-24 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-25 | 2022-04-30 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-10 | 2022-05-15 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-28 | 2022-06-02 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-02 | 2022-06-03 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-26 | 2022-04-27 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-01 | 2022-05-02 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-19 | 2022-05-20 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-24 | 2022-04-25 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-24 | 2022-04-25 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-04-30 | 2022-05-01 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-19 | 2022-05-20 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-02 | 2022-06-03 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-24 | 2022-05-26 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-24 | 2022-05-26 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-02 | 2022-05-04 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-04 | 2022-05-06 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-24 | 2022-04-26 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-29 | 2022-05-01 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-02 | 2022-06-04 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-06 | 2022-06-08 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-27 | 2022-05-02 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-04 | 2022-05-09 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-23 | 2022-05-28 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-03 | 2022-06-08 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-08 | 2022-06-09 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-03 | 2022-05-04 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-24 | 2022-05-25 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-05-30 | 2022-05-31 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-03 | 2022-05-04 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-13 | 2022-05-14 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-24 | 2022-05-25 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-05-31 | 2022-06-01 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-08 | 2022-06-09 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-05-30 | 2022-06-01 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-03 | 2022-06-05 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-21 | 2022-05-23 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-10 | 2022-05-12 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-07 | 2022-05-09 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-05 | 2022-05-07 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-09 | 2022-06-11 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-09 | 2022-06-11 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-16 | 2022-05-21 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-29 | 2022-06-03 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-04 | 2022-06-09 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-09 | 2022-06-14 | 1

## Plan_D_1
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-08 | 2022-03-13 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-16 | 2022-03-21 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-22 | 2022-03-27 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-03-31 | 2022-04-01 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-25 | 2022-03-26 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-15 | 2022-03-16 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-25 | 2022-03-26 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-03-30 | 2022-03-31 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-21 | 2022-03-23 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-24 | 2022-03-26 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-13 | 2022-03-15 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-16 | 2022-03-18 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-10 | 2022-03-12 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-27 | 2022-03-29 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-03-30 | 2022-04-01 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-28 | 2022-04-02 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-03 | 2022-04-08 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-28 | 2022-04-29 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-27 | 2022-03-28 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-08 | 2022-04-09 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-19 | 2022-03-20 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-21 | 2022-03-22 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-27 | 2022-03-28 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-03 | 2022-04-04 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-11 | 2022-04-12 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-02 | 2022-04-04 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-05 | 2022-04-07 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-21 | 2022-03-23 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-24 | 2022-03-26 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-08 | 2022-04-10 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-04-11 | 2022-04-13 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-22 | 2022-03-27 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-28 | 2022-04-02 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-09 | 2022-04-14 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-05 | 2022-05-10 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-10 | 2022-05-11 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-29 | 2022-03-30 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-05 | 2022-04-06 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-14 | 2022-04-15 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-04-01 | 2022-04-02 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-04-02 | 2022-04-03 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-07 | 2022-04-08 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-14 | 2022-04-15 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-10 | 2022-05-11 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-14 | 2022-04-16 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-17 | 2022-04-19 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-02 | 2022-04-04 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-05 | 2022-04-07 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-27 | 2022-03-29 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-30 | 2022-04-01 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-10 | 2022-05-12 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-13 | 2022-05-15 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-03 | 2022-04-08 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-09 | 2022-04-14 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-15 | 2022-04-20 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-11 | 2022-05-16 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-16 | 2022-05-17 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-10 | 2022-04-11 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-18 | 2022-04-19 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-24 | 2022-04-25 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-09 | 2022-04-10 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-12 | 2022-04-13 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-16 | 2022-04-17 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-24 | 2022-04-25 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-17 | 2022-05-18 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-20 | 2022-04-22 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-23 | 2022-04-25 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-14 | 2022-04-16 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-17 | 2022-04-19 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-08 | 2022-04-10 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-11 | 2022-04-13 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-16 | 2022-05-18 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-19 | 2022-05-21 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-15 | 2022-04-20 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-21 | 2022-04-26 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-27 | 2022-05-02 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-18 | 2022-05-23 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-23 | 2022-05-24 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-20 | 2022-04-21 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-27 | 2022-04-28 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-02 | 2022-05-03 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-21 | 2022-04-22 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-22 | 2022-04-23 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-26 | 2022-04-27 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-02 | 2022-05-03 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-23 | 2022-05-24 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-02 | 2022-05-04 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-05 | 2022-05-07 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-26 | 2022-04-28 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-29 | 2022-05-01 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-20 | 2022-04-22 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-23 | 2022-04-25 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-23 | 2022-05-25 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-05-26 | 2022-05-28 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-23 | 2022-04-28 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-29 | 2022-05-04 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-04 | 2022-05-09 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-24 | 2022-05-29 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-05-29 | 2022-05-30 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-06 | 2022-05-07 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-07 | 2022-05-08 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-12 | 2022-05-13 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-04 | 2022-05-05 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-04 | 2022-05-05 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-08 | 2022-05-09 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-14 | 2022-05-15 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-05-29 | 2022-05-30 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-29 | 2022-05-31 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-01 | 2022-06-03 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-04 | 2022-05-06 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-07 | 2022-05-09 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-28 | 2022-04-30 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-01 | 2022-05-03 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-04 | 2022-06-06 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-07 | 2022-06-09 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-10 | 2022-05-15 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-16 | 2022-05-21 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-30 | 2022-06-04 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-04 | 2022-06-09 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-09 | 2022-06-10 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-21 | 2022-05-22 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-25 | 2022-05-26 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-04 | 2022-06-05 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-18 | 2022-05-19 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-20 | 2022-05-21 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-27 | 2022-05-28 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-04 | 2022-06-05 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-09 | 2022-06-10 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-04 | 2022-06-06 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-07 | 2022-06-09 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-21 | 2022-05-23 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-24 | 2022-05-26 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-15 | 2022-05-17 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-18 | 2022-05-20 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-10 | 2022-06-12 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-10 | 2022-06-12 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-23 | 2022-05-28 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-29 | 2022-06-03 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-05 | 2022-06-10 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-10 | 2022-06-15 | 1

## Plan_D_10
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-22 | 2022-03-27 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-03-29 | 2022-03-30 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-01 | 2022-04-02 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-19 | 2022-03-21 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-19 | 2022-03-21 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-13 | 2022-03-15 | 4
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-10 | 2022-03-12 | 4
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-08 | 2022-03-10 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-28 | 2022-03-30 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-03-28 | 2022-03-30 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-25 | 2022-03-30 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-03 | 2022-04-08 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-11 | 2022-04-12 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-26 | 2022-03-27 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-04 | 2022-04-05 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-29 | 2022-03-30 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-01 | 2022-04-02 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-11 | 2022-04-12 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-31 | 2022-04-02 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-03-31 | 2022-04-02 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-22 | 2022-03-24 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-22 | 2022-03-24 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-16 | 2022-03-18 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-16 | 2022-03-18 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-12 | 2022-04-14 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-17 | 2022-05-19 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-31 | 2022-04-05 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-07 | 2022-04-12 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-13 | 2022-04-18 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-04-19 | 2022-04-20 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-24 | 2022-03-25 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-07 | 2022-04-08 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-13 | 2022-04-14 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-07 | 2022-04-08 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-13 | 2022-04-14 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-04-19 | 2022-04-20 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-26 | 2022-04-28 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-12 | 2022-04-14 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-06 | 2022-04-08 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-06 | 2022-04-08 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-25 | 2022-03-27 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-25 | 2022-03-27 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-14 | 2022-05-16 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-04-29 | 2022-05-01 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-09 | 2022-04-14 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-15 | 2022-04-20 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-04-20 | 2022-04-25 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-15 | 2022-05-16 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-04 | 2022-04-05 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-24 | 2022-04-25 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-30 | 2022-05-01 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-17 | 2022-04-18 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-17 | 2022-04-18 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-24 | 2022-04-25 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-26 | 2022-04-27 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-09 | 2022-05-10 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-23 | 2022-04-25 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-23 | 2022-04-25 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-16 | 2022-04-18 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-16 | 2022-04-18 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-03 | 2022-04-05 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-03 | 2022-04-05 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-08 | 2022-05-10 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-02 | 2022-05-04 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-21 | 2022-04-26 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-26 | 2022-05-01 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-02 | 2022-05-07 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-17 | 2022-05-22 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-24 | 2022-05-25 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-26 | 2022-04-27 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-03 | 2022-05-04 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-09 | 2022-05-10 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-28 | 2022-04-29 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-28 | 2022-04-29 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-03 | 2022-05-04 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-07 | 2022-05-08 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-24 | 2022-05-25 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-11 | 2022-05-13 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-23 | 2022-05-25 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-02 | 2022-05-04 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-05 | 2022-05-07 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-26 | 2022-04-28 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-29 | 2022-05-01 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-01 | 2022-06-03 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-01 | 2022-06-03 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-29 | 2022-05-04 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-05 | 2022-05-10 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-11 | 2022-05-16 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-26 | 2022-05-31 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-05-31 | 2022-06-01 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-07 | 2022-05-08 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-12 | 2022-05-13 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-18 | 2022-05-19 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-05 | 2022-05-06 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-05 | 2022-05-06 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-12 | 2022-05-13 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-18 | 2022-05-19 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-05-31 | 2022-06-01 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-20 | 2022-05-22 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-17 | 2022-05-19 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-11 | 2022-05-13 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-14 | 2022-05-16 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-05 | 2022-05-07 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-08 | 2022-05-10 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-04 | 2022-06-06 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-04 | 2022-06-06 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-08 | 2022-05-13 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-14 | 2022-05-19 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-20 | 2022-05-25 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-01 | 2022-06-06 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-08 | 2022-06-09 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-15 | 2022-05-16 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-27 | 2022-05-28 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-02 | 2022-06-03 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-21 | 2022-05-22 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-21 | 2022-05-22 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-27 | 2022-05-28 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-02 | 2022-06-03 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-08 | 2022-06-09 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-05-29 | 2022-05-31 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-05-29 | 2022-05-31 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-26 | 2022-05-28 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-26 | 2022-05-28 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-23 | 2022-05-25 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-20 | 2022-05-22 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-07 | 2022-06-09 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-07 | 2022-06-09 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-23 | 2022-05-28 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-29 | 2022-06-03 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-04 | 2022-06-09 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-09 | 2022-06-14 | 1

## Plan_D_11
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-22 | 2022-03-27 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-03-29 | 2022-03-30 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-24 | 2022-03-25 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-18 | 2022-03-19 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-03-29 | 2022-03-30 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-18 | 2022-03-20 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-21 | 2022-03-23 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-15 | 2022-03-17 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-27 | 2022-03-29 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-03-30 | 2022-04-01 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-28 | 2022-04-02 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-03 | 2022-04-08 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-16 | 2022-04-17 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-16 | 2022-03-17 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-08 | 2022-04-09 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-03 | 2022-04-04 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-30 | 2022-05-01 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-02 | 2022-04-04 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-05 | 2022-04-07 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-08 | 2022-04-10 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-04-11 | 2022-04-13 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-09 | 2022-04-14 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-01 | 2022-05-06 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-06 | 2022-05-07 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-26 | 2022-03-27 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-05 | 2022-04-06 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-14 | 2022-04-15 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-05 | 2022-04-06 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-14 | 2022-04-15 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-06 | 2022-05-07 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-14 | 2022-04-16 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-17 | 2022-04-19 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-03-30 | 2022-04-01 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-02 | 2022-04-04 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-24 | 2022-03-26 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-27 | 2022-03-29 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-06 | 2022-05-08 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-09 | 2022-05-11 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-31 | 2022-04-05 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-06 | 2022-04-11 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-15 | 2022-04-20 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-07 | 2022-05-12 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-12 | 2022-05-13 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-09 | 2022-04-10 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-12 | 2022-04-13 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-22 | 2022-04-23 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-07 | 2022-04-08 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-10 | 2022-04-11 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-12 | 2022-04-13 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-22 | 2022-04-23 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-12 | 2022-05-13 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-20 | 2022-04-22 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-23 | 2022-04-25 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-11 | 2022-04-13 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-14 | 2022-04-16 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-05 | 2022-04-07 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-08 | 2022-04-10 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-12 | 2022-05-14 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-15 | 2022-05-17 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-12 | 2022-04-17 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-19 | 2022-04-24 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-25 | 2022-04-30 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-13 | 2022-05-18 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-18 | 2022-05-19 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-18 | 2022-04-19 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-24 | 2022-04-25 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-04-30 | 2022-05-01 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-19 | 2022-04-20 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-20 | 2022-04-21 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-24 | 2022-04-25 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-02 | 2022-05-03 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-18 | 2022-05-19 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-04-30 | 2022-05-02 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-03 | 2022-05-05 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-26 | 2022-04-28 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-24 | 2022-04-26 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-17 | 2022-04-19 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-20 | 2022-04-22 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-18 | 2022-05-20 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-05-21 | 2022-05-23 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-21 | 2022-04-26 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-27 | 2022-05-02 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-03 | 2022-05-08 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-19 | 2022-05-24 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-05-24 | 2022-05-25 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-26 | 2022-04-27 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-04 | 2022-05-05 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-09 | 2022-05-10 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-28 | 2022-04-29 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-26 | 2022-04-27 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-03 | 2022-05-04 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-20 | 2022-05-21 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-05-24 | 2022-05-25 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-24 | 2022-05-26 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-27 | 2022-05-29 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-06 | 2022-05-08 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-09 | 2022-05-11 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-03 | 2022-05-05 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-30 | 2022-05-02 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-05-30 | 2022-06-01 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-02 | 2022-06-04 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-09 | 2022-05-14 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-15 | 2022-05-20 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-27 | 2022-06-01 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-01 | 2022-06-06 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-06 | 2022-06-07 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-16 | 2022-05-17 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-22 | 2022-05-23 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-01 | 2022-06-02 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-14 | 2022-05-15 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-14 | 2022-05-15 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-20 | 2022-05-21 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-01 | 2022-06-02 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-06 | 2022-06-07 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-01 | 2022-06-03 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-04 | 2022-06-06 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-20 | 2022-05-22 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-23 | 2022-05-25 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-14 | 2022-05-16 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-17 | 2022-05-19 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-06 | 2022-06-08 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-07 | 2022-06-09 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-21 | 2022-05-26 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-26 | 2022-05-31 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-02 | 2022-06-07 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-07 | 2022-06-12 | 1

## Plan_D_12
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-19 | 2022-03-24 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-03-27 | 2022-03-28 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-18 | 2022-03-19 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-03-25 | 2022-03-26 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-18 | 2022-03-20 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-21 | 2022-03-23 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-15 | 2022-03-17 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-24 | 2022-03-26 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-03-27 | 2022-03-29 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-03-28 | 2022-04-02 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-04 | 2022-04-05 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-16 | 2022-03-17 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-22 | 2022-03-23 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-30 | 2022-03-31 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-03 | 2022-04-04 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-21 | 2022-04-22 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-30 | 2022-04-01 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-02 | 2022-04-04 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-21 | 2022-03-23 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-24 | 2022-03-26 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-05 | 2022-04-07 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-04-12 | 2022-04-14 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-25 | 2022-03-30 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-31 | 2022-04-05 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-06 | 2022-04-11 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-09 | 2022-05-14 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-14 | 2022-05-15 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-04-01 | 2022-04-02 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-07 | 2022-04-08 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-12 | 2022-04-13 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-30 | 2022-03-31 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-04-01 | 2022-04-02 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-06 | 2022-04-07 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-14 | 2022-04-15 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-14 | 2022-05-15 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-15 | 2022-04-17 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-15 | 2022-04-17 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-06 | 2022-04-08 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-09 | 2022-04-11 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-30 | 2022-04-01 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-02 | 2022-04-04 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-02 | 2022-06-04 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-15 | 2022-05-17 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-04 | 2022-04-09 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-10 | 2022-04-15 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-16 | 2022-04-21 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-15 | 2022-05-20 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-20 | 2022-05-21 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-09 | 2022-04-10 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-15 | 2022-04-16 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-21 | 2022-04-22 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-11 | 2022-04-12 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-09 | 2022-04-10 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-19 | 2022-04-20 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-23 | 2022-04-24 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-20 | 2022-05-21 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-22 | 2022-04-24 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-05 | 2022-05-07 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-18 | 2022-04-20 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-18 | 2022-04-20 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-09 | 2022-04-11 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-12 | 2022-04-14 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-30 | 2022-06-01 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-28 | 2022-05-30 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-12 | 2022-04-17 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-22 | 2022-04-27 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-27 | 2022-05-02 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-21 | 2022-05-26 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-26 | 2022-05-27 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-17 | 2022-04-18 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-27 | 2022-04-28 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-02 | 2022-05-03 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-17 | 2022-04-18 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-19 | 2022-04-20 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-27 | 2022-04-28 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-02 | 2022-05-03 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-26 | 2022-05-27 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-16 | 2022-05-18 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-02 | 2022-05-04 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-28 | 2022-04-30 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-28 | 2022-04-30 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-24 | 2022-04-26 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-21 | 2022-04-23 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-26 | 2022-05-28 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-05 | 2022-06-07 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-20 | 2022-04-25 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-28 | 2022-05-03 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-03 | 2022-05-08 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-27 | 2022-06-01 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-01 | 2022-06-02 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-25 | 2022-04-26 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-04 | 2022-05-05 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-08 | 2022-05-09 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-29 | 2022-04-30 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-30 | 2022-05-01 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-05 | 2022-05-06 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-08 | 2022-05-09 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-01 | 2022-06-02 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-11 | 2022-05-13 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-23 | 2022-05-25 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-08 | 2022-05-10 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-05 | 2022-05-07 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-25 | 2022-04-27 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-02 | 2022-05-04 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-01 | 2022-06-03 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-05 | 2022-06-07 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-04 | 2022-05-09 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-10 | 2022-05-15 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-16 | 2022-05-21 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-02 | 2022-06-07 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-07 | 2022-06-08 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-16 | 2022-05-17 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-22 | 2022-05-23 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-05-24 | 2022-05-25 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-17 | 2022-05-18 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-10 | 2022-05-11 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-18 | 2022-05-19 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-05-28 | 2022-05-29 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-07 | 2022-06-08 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-05-22 | 2022-05-24 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-05-25 | 2022-05-27 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-19 | 2022-05-21 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-20 | 2022-05-22 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-13 | 2022-05-15 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-10 | 2022-05-12 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-08 | 2022-06-10 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-08 | 2022-06-10 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-22 | 2022-05-27 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-28 | 2022-06-02 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-03 | 2022-06-08 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-08 | 2022-06-13 | 1

## Plan_D_13
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-27 | 2022-05-02 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-05-02 | 2022-05-03 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-18 | 2022-03-19 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-05-02 | 2022-05-03 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-26 | 2022-03-28 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-21 | 2022-03-23 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-17 | 2022-03-19 | 4
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-18 | 2022-03-20 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-14 | 2022-03-16 | 4
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-11 | 2022-03-13 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-07 | 2022-05-09 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-03 | 2022-05-05 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-03 | 2022-05-08 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-08 | 2022-05-09 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-30 | 2022-03-31 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-29 | 2022-03-30 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-09 | 2022-05-10 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-27 | 2022-03-29 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-06 | 2022-04-08 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-23 | 2022-03-25 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-20 | 2022-03-22 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-09 | 2022-05-11 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-12 | 2022-05-14 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-10 | 2022-05-15 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-15 | 2022-05-16 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-26 | 2022-03-27 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-02 | 2022-04-03 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-08 | 2022-04-09 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-08 | 2022-04-09 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-15 | 2022-05-16 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-15 | 2022-04-17 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-05 | 2022-04-07 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-02 | 2022-04-04 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-02 | 2022-04-04 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-30 | 2022-04-01 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-30 | 2022-04-01 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-21 | 2022-05-23 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-15 | 2022-05-17 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-03 | 2022-04-08 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-09 | 2022-04-14 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-16 | 2022-05-21 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-21 | 2022-05-22 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-04 | 2022-04-05 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-10 | 2022-04-11 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-14 | 2022-04-15 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-05 | 2022-04-06 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-10 | 2022-04-11 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-16 | 2022-04-17 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-21 | 2022-05-22 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-27 | 2022-04-29 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-06 | 2022-05-08 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-16 | 2022-04-18 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-24 | 2022-04-26 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-09 | 2022-04-11 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-09 | 2022-04-11 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-24 | 2022-05-26 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-25 | 2022-05-27 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-06 | 2022-04-11 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-12 | 2022-04-17 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-18 | 2022-04-23 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-22 | 2022-05-27 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-27 | 2022-05-28 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-12 | 2022-04-13 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-18 | 2022-04-19 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-04-24 | 2022-04-25 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-14 | 2022-04-15 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-12 | 2022-04-13 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-18 | 2022-04-19 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-04-23 | 2022-04-24 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-27 | 2022-05-28 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-04-30 | 2022-05-02 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-04-30 | 2022-05-02 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-19 | 2022-04-21 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-18 | 2022-04-20 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-12 | 2022-04-14 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-12 | 2022-04-14 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-27 | 2022-05-29 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-05 | 2022-06-07 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-15 | 2022-04-20 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-21 | 2022-04-26 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-04-26 | 2022-05-01 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-28 | 2022-06-02 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-02 | 2022-06-03 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-22 | 2022-04-23 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-04-26 | 2022-04-27 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-07 | 2022-05-08 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-20 | 2022-04-21 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-20 | 2022-04-21 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-04-26 | 2022-04-27 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-04 | 2022-05-05 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-02 | 2022-06-03 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-28 | 2022-05-30 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-18 | 2022-05-20 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-04 | 2022-05-06 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-04-27 | 2022-04-29 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-21 | 2022-04-23 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-22 | 2022-04-24 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-02 | 2022-06-04 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-06 | 2022-06-08 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-03 | 2022-05-08 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-11 | 2022-05-16 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-17 | 2022-05-22 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-03 | 2022-06-08 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-08 | 2022-06-09 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-12 | 2022-05-13 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-23 | 2022-05-24 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-05-25 | 2022-05-26 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-19 | 2022-05-20 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-19 | 2022-05-20 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-23 | 2022-05-24 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-05-30 | 2022-05-31 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-08 | 2022-06-09 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-05-30 | 2022-06-01 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-03 | 2022-06-05 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-21 | 2022-05-23 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-18 | 2022-05-20 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-13 | 2022-05-15 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-10 | 2022-05-12 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-09 | 2022-06-11 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-08 | 2022-06-10 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-23 | 2022-05-28 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-29 | 2022-06-03 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-04 | 2022-06-09 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-09 | 2022-06-14 | 1

## Plan_D_14
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-24 | 2022-04-29 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-29 | 2022-04-30 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-18 | 2022-03-19 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-29 | 2022-04-30 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-18 | 2022-03-20 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-21 | 2022-03-23 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-15 | 2022-03-17 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-04-29 | 2022-05-01 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-02 | 2022-05-04 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-30 | 2022-05-05 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-05 | 2022-05-06 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-16 | 2022-03-17 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-22 | 2022-03-23 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-29 | 2022-03-30 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-16 | 2022-03-17 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-18 | 2022-03-19 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-24 | 2022-03-25 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-29 | 2022-03-30 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-05 | 2022-05-06 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-27 | 2022-03-29 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-03-30 | 2022-04-01 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-05 | 2022-05-07 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-08 | 2022-05-10 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-06 | 2022-05-11 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-11 | 2022-05-12 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-27 | 2022-03-28 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-01 | 2022-04-02 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-07 | 2022-04-08 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-27 | 2022-03-28 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-01 | 2022-04-02 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-07 | 2022-04-08 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-11 | 2022-05-12 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-05 | 2022-04-07 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-08 | 2022-04-10 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-02 | 2022-04-04 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-30 | 2022-04-01 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-24 | 2022-03-26 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-27 | 2022-03-29 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-11 | 2022-05-13 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-14 | 2022-05-16 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-03 | 2022-04-08 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-09 | 2022-04-14 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-12 | 2022-05-17 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-21 | 2022-05-22 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-05 | 2022-04-06 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-09 | 2022-04-10 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-16 | 2022-04-17 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-03 | 2022-04-04 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-05 | 2022-04-06 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-09 | 2022-04-10 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-16 | 2022-04-17 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-21 | 2022-05-22 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-14 | 2022-04-16 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-17 | 2022-04-19 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-11 | 2022-04-13 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-08 | 2022-04-10 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-02 | 2022-04-04 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-05 | 2022-04-07 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-17 | 2022-05-19 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-20 | 2022-05-22 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-06 | 2022-04-11 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-12 | 2022-04-17 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-18 | 2022-04-23 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-23 | 2022-05-28 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-28 | 2022-05-29 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-12 | 2022-04-13 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-26 | 2022-04-27 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-07 | 2022-05-08 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-11 | 2022-04-12 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-13 | 2022-04-14 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-01 | 2022-05-02 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-09 | 2022-05-10 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-28 | 2022-05-29 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-04-23 | 2022-04-25 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-04-26 | 2022-04-28 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-20 | 2022-04-22 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-17 | 2022-04-19 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-11 | 2022-04-13 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-14 | 2022-04-16 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-28 | 2022-05-30 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-05-31 | 2022-06-02 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-18 | 2022-04-23 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-04 | 2022-05-09 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-10 | 2022-05-15 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-29 | 2022-06-03 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-03 | 2022-06-04 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-23 | 2022-04-24 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-14 | 2022-05-15 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-18 | 2022-05-19 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-24 | 2022-04-25 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-26 | 2022-04-27 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-14 | 2022-05-15 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-18 | 2022-05-19 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-03 | 2022-06-04 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-23 | 2022-05-25 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-03 | 2022-06-05 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-09 | 2022-05-11 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-12 | 2022-05-14 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-23 | 2022-04-25 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-26 | 2022-04-28 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-05 | 2022-06-07 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-07 | 2022-06-09 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-28 | 2022-05-03 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-16 | 2022-05-21 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-24 | 2022-05-29 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-04 | 2022-06-09 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-09 | 2022-06-10 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-03 | 2022-05-04 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-23 | 2022-05-24 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-05-30 | 2022-05-31 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-07 | 2022-05-08 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-03 | 2022-05-04 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-23 | 2022-05-24 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-01 | 2022-06-02 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-09 | 2022-06-10 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-05-29 | 2022-05-31 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-01 | 2022-06-03 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-21 | 2022-05-23 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-24 | 2022-05-26 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-03 | 2022-05-05 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-06 | 2022-05-08 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-10 | 2022-06-12 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-09 | 2022-06-11 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-18 | 2022-05-23 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-30 | 2022-06-04 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-05 | 2022-06-10 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-10 | 2022-06-15 | 2

## Plan_D_15
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-25 | 2022-03-30 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-03-30 | 2022-03-31 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-18 | 2022-03-19 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-01 | 2022-04-02 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-18 | 2022-03-20 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-21 | 2022-03-23 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-15 | 2022-03-17 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-30 | 2022-04-01 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-02 | 2022-04-04 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-03 | 2022-04-08 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-22 | 2022-04-23 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-11 | 2022-04-12 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-18 | 2022-03-19 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-23 | 2022-03-24 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-10 | 2022-04-11 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-13 | 2022-04-14 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-27 | 2022-03-29 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-05 | 2022-04-07 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-08 | 2022-04-10 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-04-11 | 2022-04-13 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-28 | 2022-04-02 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-14 | 2022-04-19 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-25 | 2022-04-30 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-04 | 2022-05-05 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-07 | 2022-04-08 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-23 | 2022-04-24 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-27 | 2022-03-28 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-03 | 2022-04-04 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-20 | 2022-04-21 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-01 | 2022-05-02 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-19 | 2022-04-21 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-22 | 2022-04-24 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-14 | 2022-04-16 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-02 | 2022-04-04 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-24 | 2022-03-26 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-27 | 2022-03-29 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-04-30 | 2022-05-02 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-03 | 2022-05-05 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-31 | 2022-04-05 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-12 | 2022-04-17 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-29 | 2022-05-04 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-05 | 2022-05-10 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-18 | 2022-05-19 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-05 | 2022-04-06 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-18 | 2022-04-19 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-04 | 2022-05-05 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-05 | 2022-04-06 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-07 | 2022-04-08 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-17 | 2022-04-18 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-07 | 2022-05-08 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-14 | 2022-05-15 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-06 | 2022-05-08 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-09 | 2022-05-11 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-25 | 2022-04-27 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-17 | 2022-04-19 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-05 | 2022-04-07 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-08 | 2022-04-10 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-12 | 2022-05-14 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-15 | 2022-05-17 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-08 | 2022-04-13 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-19 | 2022-04-24 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-11 | 2022-05-16 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-24 | 2022-05-29 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-29 | 2022-05-30 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-15 | 2022-04-16 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-29 | 2022-04-30 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-16 | 2022-05-17 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-16 | 2022-04-17 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-13 | 2022-04-14 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-01 | 2022-05-02 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-18 | 2022-05-19 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-29 | 2022-05-30 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-18 | 2022-05-20 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-21 | 2022-05-23 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-24 | 2022-04-26 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-27 | 2022-04-29 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-13 | 2022-04-15 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-20 | 2022-04-22 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-29 | 2022-05-31 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-01 | 2022-06-03 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-20 | 2022-04-25 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-07 | 2022-05-12 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-19 | 2022-05-24 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-30 | 2022-06-04 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-04 | 2022-06-05 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-25 | 2022-04-26 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-16 | 2022-05-17 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-24 | 2022-05-25 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-26 | 2022-04-27 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-28 | 2022-04-29 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-12 | 2022-05-13 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-24 | 2022-05-25 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-04 | 2022-06-05 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-24 | 2022-05-26 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-04 | 2022-06-06 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-12 | 2022-05-14 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-15 | 2022-05-17 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-30 | 2022-05-02 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-03 | 2022-05-05 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-07 | 2022-06-09 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-06 | 2022-06-08 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-01 | 2022-05-06 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-18 | 2022-05-23 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-25 | 2022-05-30 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-05 | 2022-06-10 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-10 | 2022-06-11 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-08 | 2022-05-09 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-26 | 2022-05-27 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-05-31 | 2022-06-01 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-12 | 2022-05-13 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-10 | 2022-05-11 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-26 | 2022-05-27 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-02 | 2022-06-03 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-10 | 2022-06-11 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-05-30 | 2022-06-01 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-02 | 2022-06-04 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-23 | 2022-05-25 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-26 | 2022-05-28 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-06 | 2022-05-08 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-09 | 2022-05-11 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-10 | 2022-06-12 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-11 | 2022-06-13 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-13 | 2022-05-18 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-31 | 2022-06-05 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-06 | 2022-06-11 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-11 | 2022-06-16 | 1

## Plan_D_16
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-24 | 2022-04-29 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-29 | 2022-04-30 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-19 | 2022-03-20 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-18 | 2022-03-19 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-29 | 2022-04-30 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-08 | 2022-04-10 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-30 | 2022-04-01 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-18 | 2022-03-20 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-26 | 2022-03-28 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-15 | 2022-03-17 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-08 | 2022-03-10 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-04 | 2022-05-06 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-03 | 2022-05-05 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-30 | 2022-05-05 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-05 | 2022-05-06 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-22 | 2022-03-23 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-28 | 2022-03-29 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-28 | 2022-03-29 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-05 | 2022-05-06 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-05 | 2022-04-07 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-30 | 2022-05-02 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-21 | 2022-03-23 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-23 | 2022-03-25 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-28 | 2022-05-30 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-22 | 2022-05-24 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-07 | 2022-05-12 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-13 | 2022-05-14 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-30 | 2022-03-31 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-07 | 2022-04-08 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-26 | 2022-03-27 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-30 | 2022-03-31 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-07 | 2022-04-08 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-13 | 2022-05-14 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-22 | 2022-04-24 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-23 | 2022-04-25 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-02 | 2022-04-04 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-20 | 2022-04-22 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-24 | 2022-03-26 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-29 | 2022-03-31 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-12 | 2022-05-14 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-28 | 2022-05-30 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-03 | 2022-04-08 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-09 | 2022-04-14 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-14 | 2022-05-19 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-19 | 2022-05-20 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-02 | 2022-04-03 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-09 | 2022-04-10 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-15 | 2022-04-16 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-04 | 2022-04-05 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-09 | 2022-04-10 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-15 | 2022-04-16 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-19 | 2022-05-20 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-17 | 2022-05-19 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-14 | 2022-04-16 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-11 | 2022-04-13 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-08 | 2022-04-10 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-05 | 2022-04-07 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-02 | 2022-04-04 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-05 | 2022-06-07 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-19 | 2022-05-21 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-06 | 2022-04-11 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-12 | 2022-04-17 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-19 | 2022-04-24 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-20 | 2022-05-25 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-25 | 2022-05-26 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-13 | 2022-04-14 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-19 | 2022-04-20 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-04-25 | 2022-04-26 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-13 | 2022-04-14 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-17 | 2022-04-18 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-19 | 2022-04-20 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-04-25 | 2022-04-26 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-25 | 2022-05-26 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-04-27 | 2022-04-29 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-04-30 | 2022-05-02 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-17 | 2022-04-19 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-19 | 2022-04-21 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-15 | 2022-04-17 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-12 | 2022-04-14 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-31 | 2022-06-02 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-09 | 2022-06-11 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-18 | 2022-04-23 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-25 | 2022-04-30 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-20 | 2022-05-25 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-26 | 2022-05-31 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-04 | 2022-06-05 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-27 | 2022-04-28 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-02 | 2022-05-03 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-28 | 2022-05-29 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-23 | 2022-04-24 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-23 | 2022-04-24 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-02 | 2022-05-03 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-28 | 2022-05-29 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-04 | 2022-06-05 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-25 | 2022-05-27 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-25 | 2022-05-27 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-09 | 2022-05-11 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-22 | 2022-05-24 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-25 | 2022-04-27 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-07 | 2022-05-09 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-02 | 2022-06-04 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-03 | 2022-06-05 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-01 | 2022-05-06 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-07 | 2022-05-12 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-01 | 2022-06-06 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-06 | 2022-06-11 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-11 | 2022-06-12 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-11 | 2022-05-12 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-30 | 2022-05-31 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-06 | 2022-06-07 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-10 | 2022-05-11 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-09 | 2022-05-10 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-30 | 2022-05-31 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-06 | 2022-06-07 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-11 | 2022-06-12 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-09 | 2022-06-11 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-06 | 2022-06-08 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-14 | 2022-05-16 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-15 | 2022-05-17 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-10 | 2022-05-12 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-06 | 2022-05-08 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-12 | 2022-06-14 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-12 | 2022-06-14 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-14 | 2022-05-19 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-31 | 2022-06-05 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-07 | 2022-06-12 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-12 | 2022-06-17 | 2

## Plan_D_17
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-26 | 2022-03-31 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-13 | 2022-04-14 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-30 | 2022-03-31 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-30 | 2022-03-31 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-23 | 2022-04-24 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-18 | 2022-03-20 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-21 | 2022-03-23 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-15 | 2022-03-17 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-31 | 2022-04-02 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-03 | 2022-04-05 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-21 | 2022-03-26 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-02 | 2022-04-07 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-26 | 2022-05-01 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-01 | 2022-05-02 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-18 | 2022-03-19 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-27 | 2022-03-28 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-08 | 2022-04-09 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-18 | 2022-03-19 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-16 | 2022-03-17 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-28 | 2022-03-29 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-10 | 2022-04-11 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-01 | 2022-05-02 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-07 | 2022-04-09 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-10 | 2022-04-12 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-26 | 2022-03-28 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-26 | 2022-03-28 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-01 | 2022-05-03 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-04 | 2022-05-06 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-02 | 2022-04-07 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-11 | 2022-04-16 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-02 | 2022-05-07 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-07 | 2022-05-08 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-08 | 2022-04-09 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-19 | 2022-04-20 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-26 | 2022-03-27 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-10 | 2022-04-11 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-19 | 2022-04-20 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-07 | 2022-05-08 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-16 | 2022-04-18 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-19 | 2022-04-21 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-13 | 2022-04-15 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-07 | 2022-04-09 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-29 | 2022-03-31 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-01 | 2022-04-03 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-07 | 2022-05-09 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-10 | 2022-05-12 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-27 | 2022-04-01 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-14 | 2022-04-19 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-20 | 2022-04-25 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-08 | 2022-05-13 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-18 | 2022-05-19 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-01 | 2022-04-02 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-23 | 2022-04-24 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-28 | 2022-04-29 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-01 | 2022-04-02 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-05 | 2022-04-06 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-21 | 2022-04-22 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-28 | 2022-04-29 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-18 | 2022-05-19 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-25 | 2022-04-27 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-28 | 2022-04-30 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-22 | 2022-04-24 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-19 | 2022-04-21 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-04 | 2022-04-06 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-10 | 2022-04-12 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-13 | 2022-05-15 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-16 | 2022-05-18 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-08 | 2022-04-13 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-25 | 2022-04-30 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-03 | 2022-05-08 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-20 | 2022-05-25 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-26 | 2022-05-27 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-15 | 2022-04-16 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-05 | 2022-05-06 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-10 | 2022-05-11 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-15 | 2022-04-16 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-13 | 2022-04-14 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-04 | 2022-05-05 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-13 | 2022-05-14 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-31 | 2022-06-01 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-19 | 2022-05-21 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-22 | 2022-05-24 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-30 | 2022-05-02 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-03 | 2022-05-05 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-13 | 2022-04-15 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-16 | 2022-04-18 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-25 | 2022-05-27 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-05-28 | 2022-05-30 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-17 | 2022-04-22 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-09 | 2022-05-14 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-14 | 2022-05-19 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-01 | 2022-06-06 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-06 | 2022-06-07 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-11 | 2022-05-12 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-15 | 2022-05-16 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-24 | 2022-05-25 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-12 | 2022-05-13 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-09 | 2022-05-10 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-20 | 2022-05-21 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-25 | 2022-05-26 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-06 | 2022-06-07 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-31 | 2022-06-02 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-03 | 2022-06-05 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-14 | 2022-05-16 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-17 | 2022-05-19 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-22 | 2022-04-24 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-25 | 2022-04-27 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-06 | 2022-06-08 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-09 | 2022-06-11 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-15 | 2022-05-20 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-21 | 2022-05-26 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-26 | 2022-05-31 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-07 | 2022-06-12 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-12 | 2022-06-13 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-23 | 2022-05-24 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-28 | 2022-05-29 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-02 | 2022-06-03 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-22 | 2022-05-23 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-20 | 2022-05-21 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-27 | 2022-05-28 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-04 | 2022-06-05 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-12 | 2022-06-13 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-02 | 2022-06-04 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-05 | 2022-06-07 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-30 | 2022-06-01 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-27 | 2022-05-29 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-20 | 2022-05-22 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-23 | 2022-05-25 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-12 | 2022-06-14 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-12 | 2022-06-14 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-27 | 2022-06-01 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-02 | 2022-06-07 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-08 | 2022-06-13 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-13 | 2022-06-18 | 1

## Plan_D_18
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-10 | 2022-04-15 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-16 | 2022-04-17 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-21 | 2022-03-22 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-18 | 2022-03-19 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-16 | 2022-04-17 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-14 | 2022-04-16 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-22 | 2022-04-24 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-04-11 | 2022-04-13 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-25 | 2022-03-27 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-13 | 2022-03-15 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-01 | 2022-06-03 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-26 | 2022-04-28 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-18 | 2022-04-23 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-23 | 2022-04-24 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-23 | 2022-03-24 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-29 | 2022-03-30 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-29 | 2022-03-30 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-23 | 2022-04-24 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-01 | 2022-04-03 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-01 | 2022-04-03 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-22 | 2022-03-24 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-17 | 2022-03-19 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-17 | 2022-03-19 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-11 | 2022-05-13 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-19 | 2022-05-21 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-24 | 2022-04-29 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-04-29 | 2022-04-30 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-24 | 2022-03-25 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-31 | 2022-04-01 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-06 | 2022-04-07 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-26 | 2022-03-27 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-06 | 2022-04-07 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-04-29 | 2022-04-30 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-04 | 2022-05-06 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-07 | 2022-04-09 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-04 | 2022-04-06 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-04 | 2022-04-06 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-28 | 2022-03-30 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-27 | 2022-03-29 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-22 | 2022-05-24 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-10 | 2022-05-12 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-03 | 2022-04-08 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-16 | 2022-04-21 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-04-30 | 2022-05-05 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-05 | 2022-05-06 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-04 | 2022-04-05 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-08 | 2022-04-09 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-21 | 2022-04-22 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-02 | 2022-04-03 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-08 | 2022-04-09 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-21 | 2022-04-22 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-05 | 2022-05-06 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-02 | 2022-05-04 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-28 | 2022-04-30 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-20 | 2022-04-22 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-17 | 2022-04-19 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-07 | 2022-04-09 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-10 | 2022-04-12 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-13 | 2022-05-15 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-25 | 2022-05-27 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-06 | 2022-04-11 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-12 | 2022-04-17 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-22 | 2022-04-27 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-06 | 2022-05-11 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-28 | 2022-05-29 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-12 | 2022-04-13 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-26 | 2022-04-27 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-22 | 2022-05-23 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-19 | 2022-04-20 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-12 | 2022-04-13 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-26 | 2022-04-27 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-22 | 2022-05-23 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-28 | 2022-05-29 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-04-30 | 2022-05-02 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-07 | 2022-05-09 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-23 | 2022-04-25 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-25 | 2022-04-27 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-14 | 2022-04-16 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-19 | 2022-04-21 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-16 | 2022-05-18 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-14 | 2022-06-16 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-30 | 2022-05-05 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-06 | 2022-05-11 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-24 | 2022-05-29 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-30 | 2022-06-04 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-05 | 2022-06-06 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-09 | 2022-05-10 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-16 | 2022-05-17 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-30 | 2022-05-31 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-10 | 2022-05-11 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-08 | 2022-05-09 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-14 | 2022-05-15 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-30 | 2022-05-31 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-05 | 2022-06-06 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-31 | 2022-06-02 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-03 | 2022-06-05 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-14 | 2022-05-16 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-28 | 2022-05-30 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-05 | 2022-05-07 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-08 | 2022-05-10 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-05 | 2022-06-07 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-09 | 2022-06-11 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-12 | 2022-05-17 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-17 | 2022-05-22 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-01 | 2022-06-06 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-06 | 2022-06-11 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-13 | 2022-06-14 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-19 | 2022-05-20 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-25 | 2022-05-26 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-07 | 2022-06-08 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-17 | 2022-05-18 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-19 | 2022-05-20 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-25 | 2022-05-26 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-07 | 2022-06-08 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-13 | 2022-06-14 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-06 | 2022-06-08 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-08 | 2022-06-10 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-25 | 2022-05-27 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-28 | 2022-05-30 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-22 | 2022-05-24 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-18 | 2022-05-20 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-11 | 2022-06-13 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-14 | 2022-06-16 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-20 | 2022-05-25 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-26 | 2022-05-31 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-08 | 2022-06-13 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-14 | 2022-06-19 | 2

## Plan_D_19
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-23 | 2022-03-28 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-03 | 2022-04-04 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-24 | 2022-03-25 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-18 | 2022-03-19 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-03-28 | 2022-03-29 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-18 | 2022-03-20 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-21 | 2022-03-23 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-15 | 2022-03-17 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-28 | 2022-03-30 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-03-31 | 2022-04-02 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-17 | 2022-03-22 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-25 | 2022-03-30 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-16 | 2022-04-21 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-21 | 2022-04-22 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-16 | 2022-03-17 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-22 | 2022-03-23 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-30 | 2022-03-31 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-26 | 2022-03-27 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-01 | 2022-04-02 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-22 | 2022-04-23 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-03 | 2022-04-05 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-06 | 2022-04-08 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-22 | 2022-03-24 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-21 | 2022-04-23 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-04-24 | 2022-04-26 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-31 | 2022-04-05 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-05 | 2022-04-10 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-28 | 2022-05-03 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-08 | 2022-05-09 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-26 | 2022-03-27 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-05 | 2022-04-06 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-10 | 2022-04-11 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-28 | 2022-03-29 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-05 | 2022-04-06 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-18 | 2022-04-19 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-04 | 2022-05-05 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-10 | 2022-04-12 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-13 | 2022-04-15 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-05 | 2022-04-07 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-08 | 2022-04-10 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-25 | 2022-03-27 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-28 | 2022-03-30 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-03 | 2022-05-05 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-06 | 2022-05-08 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-29 | 2022-04-03 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-07 | 2022-04-12 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-25 | 2022-04-30 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-10 | 2022-05-15 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-18 | 2022-05-19 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-03 | 2022-04-04 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-16 | 2022-04-17 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-30 | 2022-05-01 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-07 | 2022-04-08 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-07 | 2022-04-08 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-16 | 2022-04-17 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-02 | 2022-05-03 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-18 | 2022-05-19 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-30 | 2022-05-02 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-09 | 2022-05-11 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-16 | 2022-04-18 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-27 | 2022-04-29 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-11 | 2022-04-13 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-14 | 2022-04-16 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-15 | 2022-05-17 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-18 | 2022-05-20 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-11 | 2022-04-16 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-17 | 2022-04-22 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-04 | 2022-05-09 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-20 | 2022-05-25 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-26 | 2022-05-27 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-25 | 2022-04-26 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-06 | 2022-05-07 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-10 | 2022-05-11 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-29 | 2022-04-30 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-28 | 2022-04-29 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-02 | 2022-05-03 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-12 | 2022-05-13 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-25 | 2022-05-26 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-12 | 2022-05-14 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-21 | 2022-05-23 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-26 | 2022-04-28 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-29 | 2022-05-01 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-23 | 2022-04-25 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-20 | 2022-04-22 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-25 | 2022-05-27 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-05-28 | 2022-05-30 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-05-01 | 2022-05-06 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-07 | 2022-05-12 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-14 | 2022-05-19 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-28 | 2022-06-02 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-02 | 2022-06-03 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-16 | 2022-05-17 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-20 | 2022-05-21 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-27 | 2022-05-28 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-14 | 2022-05-15 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-14 | 2022-05-15 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-21 | 2022-05-22 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-23 | 2022-05-24 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-02 | 2022-06-03 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-31 | 2022-06-02 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-03 | 2022-06-05 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-12 | 2022-05-14 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-15 | 2022-05-17 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-06 | 2022-05-08 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-09 | 2022-05-11 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-06 | 2022-06-08 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-09 | 2022-06-11 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-17 | 2022-05-22 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-23 | 2022-05-28 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-03 | 2022-06-08 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-09 | 2022-06-14 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-14 | 2022-06-15 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-22 | 2022-05-23 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-30 | 2022-05-31 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-08 | 2022-06-09 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-28 | 2022-05-29 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-24 | 2022-05-25 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-29 | 2022-05-30 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-08 | 2022-06-09 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-14 | 2022-06-15 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-12 | 2022-06-14 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-08 | 2022-06-10 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-28 | 2022-05-30 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-31 | 2022-06-02 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-22 | 2022-05-24 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-25 | 2022-05-27 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-15 | 2022-06-17 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-14 | 2022-06-16 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-29 | 2022-06-03 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-04 | 2022-06-09 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-10 | 2022-06-15 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-15 | 2022-06-20 | 2

## Plan_D_2
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-21 | 2022-04-26 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-28 | 2022-04-29 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-21 | 2022-03-22 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-21 | 2022-03-22 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-30 | 2022-05-01 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-18 | 2022-03-20 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-21 | 2022-03-23 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-15 | 2022-03-17 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-04-26 | 2022-04-28 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-29 | 2022-05-01 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-04 | 2022-05-09 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-09 | 2022-05-10 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-19 | 2022-03-20 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-23 | 2022-03-24 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-31 | 2022-04-01 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-19 | 2022-03-20 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-16 | 2022-03-17 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-23 | 2022-03-24 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-29 | 2022-03-30 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-09 | 2022-05-10 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-27 | 2022-03-29 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-03-30 | 2022-04-01 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-09 | 2022-05-11 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-12 | 2022-05-14 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-20 | 2022-03-25 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-26 | 2022-03-31 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-01 | 2022-04-06 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-10 | 2022-05-15 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-15 | 2022-05-16 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-02 | 2022-04-03 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-08 | 2022-04-09 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-27 | 2022-03-28 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-25 | 2022-03-26 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-08 | 2022-04-09 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-15 | 2022-05-16 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-06 | 2022-04-08 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-09 | 2022-04-11 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-02 | 2022-04-04 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-31 | 2022-04-02 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-25 | 2022-03-27 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-28 | 2022-03-30 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-15 | 2022-05-17 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-18 | 2022-05-20 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-03 | 2022-04-08 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-09 | 2022-04-14 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-16 | 2022-05-21 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-21 | 2022-05-22 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-05 | 2022-04-06 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-11 | 2022-04-12 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-19 | 2022-04-20 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-03 | 2022-04-04 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-05 | 2022-04-06 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-10 | 2022-04-11 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-16 | 2022-04-17 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-21 | 2022-05-22 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-14 | 2022-04-16 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-17 | 2022-04-19 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-09 | 2022-04-11 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-12 | 2022-04-14 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-03 | 2022-04-05 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-06 | 2022-04-08 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-21 | 2022-05-23 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-24 | 2022-05-26 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-07 | 2022-04-12 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-14 | 2022-04-19 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-20 | 2022-04-25 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-23 | 2022-05-28 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-28 | 2022-05-29 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-12 | 2022-04-13 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-22 | 2022-04-23 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-04 | 2022-05-05 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-14 | 2022-04-15 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-14 | 2022-04-15 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-26 | 2022-04-27 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-07 | 2022-05-08 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-28 | 2022-05-29 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-02 | 2022-05-04 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-05 | 2022-05-07 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-20 | 2022-04-22 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-23 | 2022-04-25 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-15 | 2022-04-17 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-18 | 2022-04-20 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-28 | 2022-05-30 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-05-31 | 2022-06-02 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-15 | 2022-04-20 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-28 | 2022-05-03 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-11 | 2022-05-16 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-29 | 2022-06-03 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-03 | 2022-06-04 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-24 | 2022-04-25 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-11 | 2022-05-12 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-19 | 2022-05-20 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-20 | 2022-04-21 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-21 | 2022-04-22 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-05 | 2022-05-06 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-17 | 2022-05-18 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-03 | 2022-06-04 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-03 | 2022-06-05 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-16 | 2022-05-18 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-03 | 2022-05-05 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-06 | 2022-05-08 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-21 | 2022-04-23 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-24 | 2022-04-26 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-06 | 2022-06-08 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-05 | 2022-06-07 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-26 | 2022-05-01 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-17 | 2022-05-22 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-22 | 2022-05-27 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-04 | 2022-06-09 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-09 | 2022-06-10 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-02 | 2022-05-03 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-23 | 2022-05-24 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-05-30 | 2022-05-31 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-03 | 2022-05-04 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-01 | 2022-05-02 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-24 | 2022-05-25 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-01 | 2022-06-02 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-09 | 2022-06-10 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-05-29 | 2022-05-31 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-01 | 2022-06-03 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-26 | 2022-05-28 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-23 | 2022-05-25 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-09 | 2022-05-11 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-12 | 2022-05-14 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-09 | 2022-06-11 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-09 | 2022-06-11 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-04 | 2022-05-09 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-28 | 2022-06-02 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-03 | 2022-06-08 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-10 | 2022-06-15 | 1

## Plan_D_20
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-14 | 2022-03-19 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-24 | 2022-03-29 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-29 | 2022-04-30 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-19 | 2022-03-20 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-27 | 2022-03-28 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-08 | 2022-03-09 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-04-01 | 2022-04-02 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-20 | 2022-04-21 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-21 | 2022-03-23 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-26 | 2022-03-28 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-19 | 2022-03-21 | 4
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-10 | 2022-03-12 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-04-04 | 2022-04-06 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-03-29 | 2022-03-31 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-20 | 2022-03-25 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-02 | 2022-04-07 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-10 | 2022-05-15 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-16 | 2022-05-17 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-16 | 2022-03-17 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-28 | 2022-03-29 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-07 | 2022-04-08 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-29 | 2022-03-30 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-10 | 2022-04-11 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-15 | 2022-05-16 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-06 | 2022-05-08 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-10 | 2022-05-12 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-07 | 2022-04-09 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-04-10 | 2022-04-12 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-04-03 | 2022-04-05 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-15 | 2022-03-17 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-19 | 2022-05-21 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-20 | 2022-05-22 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-30 | 2022-04-04 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-11 | 2022-04-16 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-17 | 2022-05-22 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-22 | 2022-05-23 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-05 | 2022-04-06 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-18 | 2022-04-19 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-23 | 2022-03-24 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-07 | 2022-04-08 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-21 | 2022-04-22 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-22 | 2022-05-23 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-18 | 2022-04-20 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-21 | 2022-04-23 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-15 | 2022-04-17 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-08 | 2022-04-10 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-25 | 2022-03-27 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-23 | 2022-03-25 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-23 | 2022-05-25 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-26 | 2022-05-28 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-08 | 2022-04-13 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-22 | 2022-04-27 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-23 | 2022-05-28 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-28 | 2022-05-29 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-03-31 | 2022-04-01 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-18 | 2022-04-19 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-27 | 2022-04-28 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-04 | 2022-04-05 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-03 | 2022-04-04 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-15 | 2022-04-16 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-27 | 2022-04-28 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-28 | 2022-05-29 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-12 | 2022-05-14 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-27 | 2022-04-29 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-22 | 2022-04-24 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-14 | 2022-04-16 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-03-31 | 2022-04-02 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-01 | 2022-04-03 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-29 | 2022-05-31 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-01 | 2022-06-03 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-05 | 2022-04-10 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-19 | 2022-04-24 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-29 | 2022-05-04 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-29 | 2022-06-03 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-03 | 2022-06-04 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-13 | 2022-04-14 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-24 | 2022-04-25 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-07 | 2022-05-08 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-10 | 2022-04-11 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-13 | 2022-04-14 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-24 | 2022-04-25 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-08 | 2022-05-09 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-03 | 2022-06-04 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-22 | 2022-05-24 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-13 | 2022-05-15 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-07 | 2022-05-09 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-02 | 2022-05-04 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-25 | 2022-04-27 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-12 | 2022-04-14 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-09 | 2022-06-11 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-03 | 2022-06-05 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-14 | 2022-04-19 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-25 | 2022-04-30 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-09 | 2022-05-14 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-04 | 2022-06-09 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-09 | 2022-06-10 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-01 | 2022-05-02 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-13 | 2022-05-14 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-17 | 2022-05-18 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-03 | 2022-05-04 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-30 | 2022-05-01 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-13 | 2022-05-14 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-19 | 2022-05-20 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-09 | 2022-06-10 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-26 | 2022-05-28 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-15 | 2022-05-17 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-04-30 | 2022-05-02 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-03 | 2022-05-05 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-24 | 2022-04-26 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-19 | 2022-04-21 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-13 | 2022-06-15 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-10 | 2022-06-12 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-04 | 2022-05-09 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-16 | 2022-05-21 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-22 | 2022-05-27 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-10 | 2022-06-15 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-15 | 2022-06-16 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-25 | 2022-05-26 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-01 | 2022-06-02 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-06 | 2022-06-07 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-09 | 2022-05-10 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-10 | 2022-05-11 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-01 | 2022-06-02 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-06 | 2022-06-07 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-15 | 2022-06-16 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-06 | 2022-06-08 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-12 | 2022-06-14 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-04 | 2022-06-06 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-29 | 2022-05-31 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-16 | 2022-05-18 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-09 | 2022-05-11 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-16 | 2022-06-18 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-16 | 2022-06-18 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-29 | 2022-06-03 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-05 | 2022-06-10 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-11 | 2022-06-16 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-16 | 2022-06-21 | 1

## Plan_D_21
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-24 | 2022-04-29 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-05-03 | 2022-05-04 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-19 | 2022-03-20 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-05-03 | 2022-05-04 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-18 | 2022-03-20 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-21 | 2022-03-23 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-15 | 2022-03-17 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-04-29 | 2022-05-01 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-02 | 2022-05-04 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-23 | 2022-03-28 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-08 | 2022-05-13 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-16 | 2022-05-17 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-22 | 2022-03-23 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-29 | 2022-03-30 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-16 | 2022-03-17 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-18 | 2022-03-19 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-29 | 2022-03-30 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-14 | 2022-05-15 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-28 | 2022-03-30 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-03-31 | 2022-04-02 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-13 | 2022-05-15 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-16 | 2022-05-18 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-30 | 2022-04-04 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-17 | 2022-05-22 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-22 | 2022-05-23 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-26 | 2022-03-27 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-03 | 2022-04-04 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-09 | 2022-04-10 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-27 | 2022-03-28 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-04 | 2022-04-05 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-22 | 2022-05-23 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-04 | 2022-04-06 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-07 | 2022-04-09 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-03-30 | 2022-04-01 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-02 | 2022-04-04 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-24 | 2022-03-26 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-27 | 2022-03-29 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-22 | 2022-05-24 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-25 | 2022-05-27 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-31 | 2022-04-05 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-06 | 2022-04-11 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-14 | 2022-04-19 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-23 | 2022-05-28 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-28 | 2022-05-29 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-06 | 2022-04-07 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-12 | 2022-04-13 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-25 | 2022-04-26 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-07 | 2022-04-08 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-05 | 2022-04-06 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-11 | 2022-04-12 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-19 | 2022-04-20 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-28 | 2022-05-29 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-19 | 2022-04-21 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-22 | 2022-04-24 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-11 | 2022-04-13 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-14 | 2022-04-16 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-05 | 2022-04-07 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-08 | 2022-04-10 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-28 | 2022-05-30 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-31 | 2022-06-02 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-08 | 2022-04-13 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-13 | 2022-04-18 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-30 | 2022-05-05 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-29 | 2022-06-03 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-03 | 2022-06-04 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-15 | 2022-04-16 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-23 | 2022-04-24 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-08 | 2022-05-09 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-16 | 2022-04-17 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-13 | 2022-04-14 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-23 | 2022-04-24 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-07 | 2022-05-08 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-03 | 2022-06-04 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-05 | 2022-05-07 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-08 | 2022-05-10 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-26 | 2022-04-28 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-27 | 2022-04-29 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-13 | 2022-04-15 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-24 | 2022-04-26 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-03 | 2022-06-05 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-06 | 2022-06-08 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-19 | 2022-04-24 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-26 | 2022-05-01 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-10 | 2022-05-15 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-04 | 2022-06-09 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-09 | 2022-06-10 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-25 | 2022-04-26 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-12 | 2022-05-13 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-18 | 2022-05-19 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-01 | 2022-05-02 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-27 | 2022-04-28 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-09 | 2022-05-10 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-20 | 2022-05-21 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-09 | 2022-06-10 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-19 | 2022-05-21 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-15 | 2022-05-17 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-06 | 2022-05-08 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-09 | 2022-05-11 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-30 | 2022-05-02 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-03 | 2022-05-05 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-11 | 2022-06-13 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-14 | 2022-06-16 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-04 | 2022-05-09 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-25 | 2022-05-30 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-06 | 2022-06-11 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-11 | 2022-06-16 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-16 | 2022-06-17 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-10 | 2022-05-11 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-30 | 2022-05-31 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-11 | 2022-06-12 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-12 | 2022-05-13 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-16 | 2022-05-17 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-30 | 2022-05-31 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-11 | 2022-06-12 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-16 | 2022-06-17 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-11 | 2022-06-13 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-14 | 2022-06-16 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-30 | 2022-06-01 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-02 | 2022-06-04 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-12 | 2022-05-14 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-18 | 2022-05-20 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-17 | 2022-06-19 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-17 | 2022-06-19 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-17 | 2022-05-22 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-31 | 2022-06-05 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-12 | 2022-06-17 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-17 | 2022-06-22 | 1

## Plan_D_22
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-09 | 2022-04-14 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-15 | 2022-04-16 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-14 | 2022-03-15 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-08 | 2022-03-09 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-19 | 2022-03-20 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-23 | 2022-04-24 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-13 | 2022-04-15 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-12 | 2022-04-14 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-12 | 2022-05-14 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-15 | 2022-04-17 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-03 | 2022-05-08 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-12 | 2022-05-13 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-29 | 2022-03-30 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-16 | 2022-03-17 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-23 | 2022-03-24 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-28 | 2022-03-29 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-09 | 2022-05-10 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-20 | 2022-05-22 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-09 | 2022-05-11 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-21 | 2022-03-23 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-18 | 2022-03-20 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-24 | 2022-05-26 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-24 | 2022-05-26 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-17 | 2022-05-22 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-22 | 2022-05-23 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-26 | 2022-03-27 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-30 | 2022-03-31 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-08 | 2022-04-09 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-25 | 2022-03-26 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-05 | 2022-04-06 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-22 | 2022-05-23 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-06 | 2022-05-08 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-23 | 2022-04-25 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-03-30 | 2022-04-01 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-30 | 2022-04-01 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-27 | 2022-03-29 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-27 | 2022-03-29 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-31 | 2022-06-02 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-31 | 2022-06-02 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-03 | 2022-04-08 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-19 | 2022-04-24 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-23 | 2022-05-28 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-28 | 2022-05-29 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-02 | 2022-04-03 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-09 | 2022-04-10 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-28 | 2022-04-29 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-04 | 2022-04-05 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-10 | 2022-04-11 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-24 | 2022-04-25 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-28 | 2022-05-29 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-20 | 2022-05-22 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-06 | 2022-05-08 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-08 | 2022-04-10 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-08 | 2022-04-10 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-02 | 2022-04-04 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-02 | 2022-04-04 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-28 | 2022-05-30 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-28 | 2022-05-30 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-06 | 2022-04-11 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-21 | 2022-04-26 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-03 | 2022-05-08 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-29 | 2022-06-03 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-03 | 2022-06-04 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-12 | 2022-04-13 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-26 | 2022-04-27 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-19 | 2022-05-20 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-11 | 2022-04-12 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-13 | 2022-04-14 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-26 | 2022-04-27 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-19 | 2022-05-20 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-03 | 2022-06-04 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-12 | 2022-05-14 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-09 | 2022-05-11 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-26 | 2022-04-28 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-26 | 2022-04-28 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-18 | 2022-04-20 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-16 | 2022-04-18 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-04 | 2022-06-06 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-07 | 2022-06-09 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-14 | 2022-04-19 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-27 | 2022-05-02 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-30 | 2022-06-04 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-04 | 2022-06-09 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-10 | 2022-06-11 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-20 | 2022-04-21 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-05 | 2022-05-06 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-05 | 2022-06-06 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-19 | 2022-04-20 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-21 | 2022-04-22 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-05 | 2022-05-06 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-05 | 2022-06-06 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-10 | 2022-06-11 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-05 | 2022-06-07 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-08 | 2022-06-10 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-03 | 2022-05-05 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-03 | 2022-05-05 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-19 | 2022-04-21 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-21 | 2022-04-23 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-15 | 2022-06-17 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-10 | 2022-06-12 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-25 | 2022-04-30 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-11 | 2022-05-16 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-06 | 2022-06-11 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-12 | 2022-06-17 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-17 | 2022-06-18 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-04-30 | 2022-05-01 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-16 | 2022-05-17 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-12 | 2022-06-13 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-04-30 | 2022-05-01 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-12 | 2022-05-13 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-16 | 2022-05-17 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-12 | 2022-06-13 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-17 | 2022-06-18 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-11 | 2022-06-13 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-14 | 2022-06-16 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-16 | 2022-05-18 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-16 | 2022-05-18 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-04-30 | 2022-05-02 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-04-30 | 2022-05-02 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-18 | 2022-06-20 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-18 | 2022-06-20 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-14 | 2022-05-19 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-23 | 2022-05-28 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-13 | 2022-06-18 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-18 | 2022-06-23 | 1

## Plan_D_23
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-06 | 2022-04-11 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-11 | 2022-04-12 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-08 | 2022-03-09 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-11 | 2022-04-12 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-09 | 2022-04-11 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-01 | 2022-04-03 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-14 | 2022-05-16 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-13 | 2022-04-15 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-19 | 2022-04-24 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-30 | 2022-05-01 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-18 | 2022-03-19 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-22 | 2022-03-23 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-27 | 2022-03-28 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-28 | 2022-03-29 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-25 | 2022-04-26 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-26 | 2022-04-28 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-27 | 2022-05-29 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-21 | 2022-03-23 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-18 | 2022-03-20 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-02 | 2022-06-04 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-02 | 2022-06-04 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-30 | 2022-04-04 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-01 | 2022-05-06 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-07 | 2022-05-08 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-24 | 2022-03-25 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-30 | 2022-03-31 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-06 | 2022-04-07 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-30 | 2022-03-31 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-04 | 2022-04-05 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-07 | 2022-05-08 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-25 | 2022-04-27 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-05 | 2022-04-07 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-03 | 2022-04-05 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-30 | 2022-04-01 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-27 | 2022-03-29 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-27 | 2022-03-29 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-08 | 2022-05-10 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-06 | 2022-05-08 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-31 | 2022-04-05 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-05 | 2022-04-10 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-11 | 2022-04-16 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-08 | 2022-05-13 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-26 | 2022-05-27 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-09 | 2022-04-10 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-15 | 2022-04-16 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-24 | 2022-05-25 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-07 | 2022-04-08 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-05 | 2022-04-06 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-15 | 2022-04-16 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-20 | 2022-04-21 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-26 | 2022-05-27 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-05 | 2022-05-07 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-11 | 2022-05-13 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-17 | 2022-04-19 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-17 | 2022-04-19 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-06 | 2022-04-08 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-08 | 2022-04-10 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-21 | 2022-05-23 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-15 | 2022-05-17 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-12 | 2022-04-17 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-17 | 2022-04-22 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-25 | 2022-05-30 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-31 | 2022-06-05 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-05 | 2022-06-06 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-23 | 2022-04-24 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-27 | 2022-04-28 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-31 | 2022-06-01 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-23 | 2022-04-24 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-21 | 2022-04-22 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-27 | 2022-04-28 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-31 | 2022-06-01 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-05 | 2022-06-06 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-30 | 2022-06-01 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-30 | 2022-06-01 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-01 | 2022-05-03 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-23 | 2022-04-25 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-20 | 2022-04-22 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-20 | 2022-04-22 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-05 | 2022-06-07 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-05 | 2022-06-07 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-24 | 2022-04-29 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-29 | 2022-05-04 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-01 | 2022-06-06 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-06 | 2022-06-11 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-11 | 2022-06-12 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-02 | 2022-05-03 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-09 | 2022-05-10 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-07 | 2022-06-08 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-29 | 2022-04-30 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-03 | 2022-05-04 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-05 | 2022-05-06 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-07 | 2022-06-08 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-11 | 2022-06-12 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-08 | 2022-06-10 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-08 | 2022-06-10 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-17 | 2022-05-19 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-18 | 2022-05-20 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-29 | 2022-05-01 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-02 | 2022-05-04 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-16 | 2022-06-18 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-11 | 2022-06-13 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-05 | 2022-05-10 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-11 | 2022-05-16 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-08 | 2022-06-13 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-13 | 2022-06-18 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-18 | 2022-06-19 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-10 | 2022-05-11 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-16 | 2022-05-17 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-13 | 2022-06-14 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-15 | 2022-05-16 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-14 | 2022-05-15 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-23 | 2022-05-24 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-13 | 2022-06-14 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-18 | 2022-06-19 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-13 | 2022-06-15 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-16 | 2022-06-18 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-25 | 2022-05-27 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-24 | 2022-05-26 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-22 | 2022-05-24 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-11 | 2022-05-13 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-19 | 2022-06-21 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-19 | 2022-06-21 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-17 | 2022-05-22 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-25 | 2022-05-30 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-14 | 2022-06-19 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-19 | 2022-06-24 | 2

## Plan_D_24
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-19 | 2022-03-24 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-25 | 2022-04-26 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-22 | 2022-03-23 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-22 | 2022-03-23 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-23 | 2022-04-24 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-18 | 2022-03-20 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-21 | 2022-03-23 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-15 | 2022-03-17 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-24 | 2022-03-26 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-03-27 | 2022-03-29 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-11 | 2022-03-16 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-17 | 2022-03-22 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-25 | 2022-03-30 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-01 | 2022-05-06 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-06 | 2022-05-07 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-26 | 2022-03-27 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-03 | 2022-04-04 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-20 | 2022-03-21 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-16 | 2022-03-17 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-26 | 2022-03-27 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-03 | 2022-04-04 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-08 | 2022-05-09 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-30 | 2022-04-01 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-02 | 2022-04-04 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-22 | 2022-03-24 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-25 | 2022-03-27 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-16 | 2022-03-18 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-19 | 2022-03-21 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-06 | 2022-05-08 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-09 | 2022-05-11 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-23 | 2022-03-28 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-31 | 2022-04-05 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-06 | 2022-04-11 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-14 | 2022-05-19 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-19 | 2022-05-20 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-29 | 2022-03-30 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-05 | 2022-04-06 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-11 | 2022-04-12 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-30 | 2022-03-31 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-28 | 2022-03-29 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-05 | 2022-04-06 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-11 | 2022-04-12 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-19 | 2022-05-20 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-11 | 2022-04-13 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-14 | 2022-04-16 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-05 | 2022-04-07 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-08 | 2022-04-10 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-28 | 2022-03-30 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-31 | 2022-04-02 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-19 | 2022-05-21 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-22 | 2022-05-24 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-31 | 2022-04-05 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-06 | 2022-04-11 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-12 | 2022-04-17 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-21 | 2022-05-26 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-26 | 2022-05-27 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-08 | 2022-04-09 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-21 | 2022-04-22 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-27 | 2022-04-28 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-13 | 2022-04-14 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-09 | 2022-04-10 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-14 | 2022-04-15 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-23 | 2022-04-24 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-26 | 2022-05-27 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-17 | 2022-04-19 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-20 | 2022-04-22 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-11 | 2022-04-13 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-14 | 2022-04-16 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-05 | 2022-04-07 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-08 | 2022-04-10 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-26 | 2022-05-28 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-29 | 2022-05-31 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-14 | 2022-04-19 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-22 | 2022-04-27 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-28 | 2022-05-03 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-28 | 2022-06-02 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-02 | 2022-06-03 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-19 | 2022-04-20 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-03 | 2022-05-04 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-21 | 2022-05-22 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-19 | 2022-04-20 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-21 | 2022-04-22 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-03 | 2022-05-04 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-10 | 2022-05-11 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-02 | 2022-06-03 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-03 | 2022-05-05 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-12 | 2022-05-14 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-27 | 2022-04-29 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-30 | 2022-05-02 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-23 | 2022-04-25 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-19 | 2022-04-21 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-02 | 2022-06-04 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-05 | 2022-06-07 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-24 | 2022-04-29 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-22 | 2022-05-27 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-27 | 2022-06-01 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-03 | 2022-06-08 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-09 | 2022-06-10 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-29 | 2022-04-30 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-28 | 2022-05-29 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-05 | 2022-06-06 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-01 | 2022-05-02 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-29 | 2022-04-30 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-28 | 2022-05-29 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-05 | 2022-06-06 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-11 | 2022-06-12 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-08 | 2022-06-10 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-11 | 2022-06-13 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-27 | 2022-05-29 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-30 | 2022-06-01 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-15 | 2022-05-17 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-29 | 2022-05-01 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-14 | 2022-06-16 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-17 | 2022-06-19 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-08 | 2022-05-13 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-02 | 2022-06-07 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-08 | 2022-06-13 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-14 | 2022-06-19 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-19 | 2022-06-20 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-14 | 2022-05-15 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-07 | 2022-06-08 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-13 | 2022-06-14 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-13 | 2022-05-14 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-15 | 2022-05-16 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-07 | 2022-06-08 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-13 | 2022-06-14 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-19 | 2022-06-20 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-13 | 2022-06-15 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-16 | 2022-06-18 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-07 | 2022-06-09 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-10 | 2022-06-12 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-13 | 2022-05-15 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-16 | 2022-05-18 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-20 | 2022-06-22 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-19 | 2022-06-21 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-16 | 2022-05-21 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-09 | 2022-06-14 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-15 | 2022-06-20 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-20 | 2022-06-25 | 2

## Plan_D_25
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-04-09 | 2022-04-14 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-22 | 2022-04-27 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-29 | 2022-04-30 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-04-14 | 2022-04-15 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-08 | 2022-03-09 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-04-14 | 2022-04-15 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-29 | 2022-04-30 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-24 | 2022-04-26 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-26 | 2022-04-28 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-04-28 | 2022-04-30 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-02 | 2022-05-04 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-15 | 2022-03-20 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-15 | 2022-04-20 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-02 | 2022-05-07 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-07 | 2022-05-08 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-26 | 2022-04-27 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-21 | 2022-04-22 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-07 | 2022-05-08 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-20 | 2022-05-22 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-20 | 2022-05-22 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-20 | 2022-03-22 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-20 | 2022-03-22 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-17 | 2022-03-19 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-17 | 2022-03-19 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-27 | 2022-05-29 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-23 | 2022-05-25 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-24 | 2022-03-29 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-28 | 2022-05-03 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-08 | 2022-05-13 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-19 | 2022-05-20 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-30 | 2022-03-31 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-03 | 2022-05-04 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-23 | 2022-03-24 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-29 | 2022-03-30 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-09 | 2022-05-10 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-19 | 2022-05-20 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-03 | 2022-05-05 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-10 | 2022-05-12 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-19 | 2022-04-21 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-29 | 2022-03-31 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-26 | 2022-03-28 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-26 | 2022-03-28 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-13 | 2022-05-15 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-17 | 2022-05-19 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-01 | 2022-04-06 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-21 | 2022-05-26 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-26 | 2022-05-31 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-31 | 2022-06-01 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-03-31 | 2022-04-01 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-10 | 2022-04-11 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-26 | 2022-05-27 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-02 | 2022-04-03 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-06 | 2022-04-07 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-26 | 2022-05-27 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-31 | 2022-06-01 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-26 | 2022-05-28 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-29 | 2022-05-31 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-15 | 2022-04-17 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-06 | 2022-04-08 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-03-31 | 2022-04-02 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-01 | 2022-04-03 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-31 | 2022-06-02 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-04 | 2022-06-06 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-03 | 2022-04-08 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-18 | 2022-04-23 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-27 | 2022-06-01 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-02 | 2022-06-07 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-07 | 2022-06-08 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-10 | 2022-04-11 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-23 | 2022-04-24 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-02 | 2022-06-03 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-08 | 2022-04-09 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-08 | 2022-04-09 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-23 | 2022-04-24 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-02 | 2022-06-03 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-07 | 2022-06-08 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-01 | 2022-06-03 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-03 | 2022-06-05 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-05 | 2022-05-07 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-23 | 2022-04-25 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-09 | 2022-04-11 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-09 | 2022-04-11 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-07 | 2022-06-09 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-07 | 2022-06-09 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-11 | 2022-04-16 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-24 | 2022-04-29 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-03 | 2022-06-08 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-08 | 2022-06-13 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-13 | 2022-06-14 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-18 | 2022-04-19 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-02 | 2022-05-03 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-09 | 2022-06-10 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-27 | 2022-04-28 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-16 | 2022-04-17 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-09 | 2022-05-10 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-09 | 2022-06-10 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-13 | 2022-06-14 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-10 | 2022-06-12 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-10 | 2022-06-12 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-04-29 | 2022-05-01 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-07 | 2022-05-09 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-17 | 2022-04-19 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-20 | 2022-04-22 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-13 | 2022-06-15 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-13 | 2022-06-15 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-05 | 2022-05-10 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-11 | 2022-05-16 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-10 | 2022-06-15 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-15 | 2022-06-20 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-20 | 2022-06-21 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-13 | 2022-05-14 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-17 | 2022-05-18 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-15 | 2022-06-16 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-11 | 2022-05-12 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-11 | 2022-05-12 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-17 | 2022-05-18 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-15 | 2022-06-16 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-20 | 2022-06-21 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-18 | 2022-06-20 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-18 | 2022-06-20 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-16 | 2022-05-18 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-23 | 2022-05-25 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-13 | 2022-05-15 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-10 | 2022-05-12 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-21 | 2022-06-23 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-21 | 2022-06-23 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-14 | 2022-05-19 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-20 | 2022-05-25 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-16 | 2022-06-21 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-21 | 2022-06-26 | 1

## Plan_D_26
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-12 | 2022-04-17 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-17 | 2022-04-18 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-19 | 2022-03-20 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-19 | 2022-03-20 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-17 | 2022-04-18 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-18 | 2022-04-20 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-23 | 2022-04-25 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-13 | 2022-06-15 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-09 | 2022-06-11 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-18 | 2022-04-23 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-24 | 2022-04-25 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-29 | 2022-03-30 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-27 | 2022-03-28 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-29 | 2022-04-30 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-20 | 2022-04-22 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-22 | 2022-04-24 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-22 | 2022-03-24 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-22 | 2022-03-24 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-19 | 2022-03-21 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-19 | 2022-03-21 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-25 | 2022-04-27 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-10 | 2022-05-12 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-01 | 2022-05-06 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-08 | 2022-05-09 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-24 | 2022-03-25 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-31 | 2022-04-01 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-09 | 2022-04-10 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-30 | 2022-03-31 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-09 | 2022-04-10 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-10 | 2022-05-11 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-20 | 2022-05-22 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-19 | 2022-05-21 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-16 | 2022-04-18 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-30 | 2022-04-01 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-27 | 2022-03-29 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-27 | 2022-03-29 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-22 | 2022-05-24 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-24 | 2022-05-26 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-06 | 2022-04-11 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-21 | 2022-04-26 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-13 | 2022-05-18 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-18 | 2022-05-19 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-04 | 2022-04-05 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-11 | 2022-04-12 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-26 | 2022-04-27 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-02 | 2022-04-03 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-24 | 2022-04-25 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-26 | 2022-04-27 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-18 | 2022-05-19 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-25 | 2022-05-27 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-13 | 2022-05-15 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-04 | 2022-05-06 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-30 | 2022-05-02 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-28 | 2022-04-30 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-27 | 2022-04-29 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-31 | 2022-06-02 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-28 | 2022-05-30 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-05 | 2022-04-10 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-03 | 2022-05-08 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-09 | 2022-05-14 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-22 | 2022-05-27 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-31 | 2022-06-01 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-14 | 2022-04-15 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-13 | 2022-05-14 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-21 | 2022-05-22 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-13 | 2022-04-14 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-11 | 2022-04-12 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-13 | 2022-05-14 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-15 | 2022-05-16 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-31 | 2022-06-01 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-16 | 2022-05-18 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-16 | 2022-05-18 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-10 | 2022-05-12 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-13 | 2022-05-15 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-10 | 2022-04-12 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-10 | 2022-04-12 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-31 | 2022-06-02 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-12 | 2022-06-14 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-15 | 2022-04-20 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-23 | 2022-05-28 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-29 | 2022-06-03 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-10 | 2022-06-15 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-15 | 2022-06-16 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-22 | 2022-04-23 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-28 | 2022-05-29 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-03 | 2022-06-04 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-22 | 2022-04-23 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-20 | 2022-04-21 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-28 | 2022-05-29 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-03 | 2022-06-04 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-15 | 2022-06-16 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-06 | 2022-06-08 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-10 | 2022-06-12 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-28 | 2022-05-30 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-03 | 2022-06-05 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-07 | 2022-05-09 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-07 | 2022-05-09 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-19 | 2022-06-21 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-15 | 2022-06-17 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-24 | 2022-04-29 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-29 | 2022-06-03 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-04 | 2022-06-09 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-16 | 2022-06-21 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-21 | 2022-06-22 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-01 | 2022-05-02 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-09 | 2022-06-10 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-13 | 2022-06-14 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-04 | 2022-05-05 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-04 | 2022-05-05 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-09 | 2022-06-10 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-13 | 2022-06-14 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-21 | 2022-06-22 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-18 | 2022-06-20 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-16 | 2022-06-18 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-03 | 2022-06-05 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-06 | 2022-06-08 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-01 | 2022-05-03 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-04 | 2022-05-06 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-22 | 2022-06-24 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-22 | 2022-06-24 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-04 | 2022-06-09 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-10 | 2022-06-15 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-17 | 2022-06-22 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-22 | 2022-06-27 | 2

## Plan_D_27
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-18 | 2022-04-23 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-29 | 2022-04-30 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-19 | 2022-03-20 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-18 | 2022-03-19 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-05-02 | 2022-05-03 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-21 | 2022-03-23 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-19 | 2022-03-21 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 4
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-04-30 | 2022-05-02 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-27 | 2022-04-29 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-03 | 2022-05-08 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-08 | 2022-05-09 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-29 | 2022-03-30 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-16 | 2022-03-17 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-29 | 2022-03-30 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-08 | 2022-05-09 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-30 | 2022-04-01 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-03-27 | 2022-03-29 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-22 | 2022-03-24 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-24 | 2022-03-26 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-18 | 2022-03-20 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-15 | 2022-03-17 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-14 | 2022-05-16 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-11 | 2022-05-13 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-09 | 2022-05-14 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-14 | 2022-05-15 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-31 | 2022-04-01 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-06 | 2022-04-07 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-26 | 2022-03-27 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-06 | 2022-04-07 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-14 | 2022-05-15 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-08 | 2022-04-10 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-17 | 2022-04-19 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-02 | 2022-04-04 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-02 | 2022-04-04 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-25 | 2022-03-27 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-30 | 2022-04-01 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-17 | 2022-05-19 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-18 | 2022-05-20 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-03 | 2022-04-08 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-09 | 2022-04-14 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-16 | 2022-05-21 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-21 | 2022-05-22 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-04 | 2022-04-05 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-10 | 2022-04-11 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-24 | 2022-04-25 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-02 | 2022-04-03 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-03 | 2022-04-04 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-08 | 2022-04-09 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-22 | 2022-04-23 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-21 | 2022-05-22 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-24 | 2022-04-26 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-30 | 2022-05-02 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-15 | 2022-04-17 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-08 | 2022-04-10 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-05 | 2022-04-07 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-05 | 2022-04-07 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-24 | 2022-05-26 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-25 | 2022-05-27 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-06 | 2022-04-11 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-12 | 2022-04-17 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-27 | 2022-05-02 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-22 | 2022-05-27 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-27 | 2022-05-28 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-13 | 2022-04-14 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-17 | 2022-04-18 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-05 | 2022-05-06 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-11 | 2022-04-12 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-13 | 2022-04-14 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-17 | 2022-04-18 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-06 | 2022-05-07 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-27 | 2022-05-28 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-04 | 2022-05-06 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-21 | 2022-05-23 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-18 | 2022-04-20 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-21 | 2022-04-23 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-11 | 2022-04-13 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-12 | 2022-04-14 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-31 | 2022-06-02 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-05-28 | 2022-05-30 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-15 | 2022-04-20 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-21 | 2022-04-26 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-10 | 2022-05-15 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-28 | 2022-06-02 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-02 | 2022-06-03 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-24 | 2022-04-25 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-04-26 | 2022-04-27 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-17 | 2022-05-18 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-20 | 2022-04-21 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-20 | 2022-04-21 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-04-26 | 2022-04-27 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-17 | 2022-05-18 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-02 | 2022-06-03 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-15 | 2022-05-17 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-27 | 2022-05-29 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-07 | 2022-05-09 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-04-27 | 2022-04-29 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-20 | 2022-04-22 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-24 | 2022-04-26 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-03 | 2022-06-05 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-06 | 2022-06-08 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-25 | 2022-04-30 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-16 | 2022-05-21 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-23 | 2022-05-28 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-03 | 2022-06-08 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-08 | 2022-06-09 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-04-30 | 2022-05-01 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-24 | 2022-05-25 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-05-29 | 2022-05-30 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-01 | 2022-05-02 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-03 | 2022-05-04 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-24 | 2022-05-25 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-05-31 | 2022-06-01 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-08 | 2022-06-09 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-06 | 2022-06-08 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-03 | 2022-06-05 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-31 | 2022-06-02 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-22 | 2022-05-24 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-11 | 2022-05-13 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-07 | 2022-05-09 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-09 | 2022-06-11 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-09 | 2022-06-11 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-04 | 2022-05-09 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-29 | 2022-06-03 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-04 | 2022-06-09 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-09 | 2022-06-14 | 2

## Plan_D_28
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-22 | 2022-03-27 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-03-29 | 2022-03-30 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-18 | 2022-03-19 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-03-27 | 2022-03-28 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-18 | 2022-03-20 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-21 | 2022-03-23 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-15 | 2022-03-17 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-27 | 2022-03-29 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-03-30 | 2022-04-01 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-21 | 2022-03-26 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-03-30 | 2022-04-04 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-15 | 2022-04-16 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-16 | 2022-03-17 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-23 | 2022-03-24 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-14 | 2022-04-15 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-25 | 2022-03-26 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-02 | 2022-04-03 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-26 | 2022-04-27 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-02 | 2022-04-04 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-05 | 2022-04-07 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-08 | 2022-04-10 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-04-11 | 2022-04-13 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-28 | 2022-04-02 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-03 | 2022-04-08 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-17 | 2022-04-22 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-30 | 2022-05-05 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-05 | 2022-05-06 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-04-02 | 2022-04-03 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-16 | 2022-04-17 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-22 | 2022-04-23 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-04-04 | 2022-04-05 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-04-05 | 2022-04-06 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-09 | 2022-04-10 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-23 | 2022-04-24 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-05 | 2022-05-06 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-22 | 2022-04-24 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-25 | 2022-04-27 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-14 | 2022-04-16 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-17 | 2022-04-19 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-02 | 2022-04-04 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-05 | 2022-04-07 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-05 | 2022-05-07 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-08 | 2022-05-10 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-11 | 2022-04-16 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-18 | 2022-04-23 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-24 | 2022-04-29 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-11 | 2022-05-16 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-18 | 2022-05-19 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-20 | 2022-04-21 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-30 | 2022-05-01 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-09 | 2022-05-10 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-21 | 2022-04-22 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-18 | 2022-04-19 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-26 | 2022-04-27 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-03 | 2022-05-04 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-18 | 2022-05-19 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-29 | 2022-05-01 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-02 | 2022-05-04 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-23 | 2022-04-25 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-26 | 2022-04-28 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-16 | 2022-04-18 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-19 | 2022-04-21 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-16 | 2022-05-18 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-19 | 2022-05-21 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-23 | 2022-04-28 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-08 | 2022-05-13 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-18 | 2022-05-23 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-24 | 2022-05-29 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-31 | 2022-06-01 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-28 | 2022-04-29 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-13 | 2022-05-14 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-23 | 2022-05-24 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-28 | 2022-04-29 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-30 | 2022-05-01 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-15 | 2022-05-16 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-27 | 2022-05-28 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-06 | 2022-06-07 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-23 | 2022-05-25 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-26 | 2022-05-28 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-13 | 2022-05-15 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-13 | 2022-05-15 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-29 | 2022-05-01 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-05-02 | 2022-05-04 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-29 | 2022-05-31 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-01 | 2022-06-03 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-05-01 | 2022-05-06 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-16 | 2022-05-21 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-30 | 2022-06-04 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-11 | 2022-06-16 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-16 | 2022-06-17 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-08 | 2022-05-09 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-29 | 2022-05-30 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-04 | 2022-06-05 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-16 | 2022-05-17 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-11 | 2022-05-12 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-21 | 2022-05-22 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-04 | 2022-06-05 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-16 | 2022-06-17 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-04 | 2022-06-06 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-07 | 2022-06-09 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-21 | 2022-05-23 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-24 | 2022-05-26 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-06 | 2022-05-08 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-09 | 2022-05-11 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-16 | 2022-06-18 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-19 | 2022-06-21 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-24 | 2022-05-29 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-30 | 2022-06-04 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-05 | 2022-06-10 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-17 | 2022-06-22 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-22 | 2022-06-23 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-29 | 2022-05-30 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-08 | 2022-06-09 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-10 | 2022-06-11 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-06-02 | 2022-06-03 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-31 | 2022-06-01 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-06 | 2022-06-07 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-12 | 2022-06-13 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-22 | 2022-06-23 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-10 | 2022-06-12 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-13 | 2022-06-15 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-04 | 2022-06-06 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-07 | 2022-06-09 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-29 | 2022-05-31 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-01 | 2022-06-03 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-22 | 2022-06-24 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-22 | 2022-06-24 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-06 | 2022-06-11 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-12 | 2022-06-17 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-18 | 2022-06-23 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-23 | 2022-06-28 | 2

## Plan_D_29
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-31 | 2022-04-05 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-05 | 2022-04-06 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-19 | 2022-03-20 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-05 | 2022-04-06 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-15 | 2022-04-17 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-17 | 2022-04-19 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-21 | 2022-05-23 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-18 | 2022-05-20 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-07 | 2022-04-12 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-12 | 2022-04-13 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-23 | 2022-03-24 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-29 | 2022-03-30 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-29 | 2022-03-30 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-12 | 2022-04-13 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-29 | 2022-03-31 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-30 | 2022-05-02 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-21 | 2022-03-23 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-18 | 2022-03-20 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-21 | 2022-06-23 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-11 | 2022-06-13 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-30 | 2022-04-04 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-17 | 2022-04-22 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-03 | 2022-05-04 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-26 | 2022-03-27 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-08 | 2022-04-09 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-15 | 2022-04-16 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-25 | 2022-03-26 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-08 | 2022-04-09 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-21 | 2022-04-22 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-04-22 | 2022-04-23 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-12 | 2022-04-14 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-11 | 2022-05-13 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-03-30 | 2022-04-01 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-01 | 2022-04-03 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-26 | 2022-03-28 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-26 | 2022-03-28 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-14 | 2022-05-16 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-14 | 2022-05-16 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-05 | 2022-04-10 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-11 | 2022-04-16 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-02 | 2022-05-07 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-08 | 2022-05-13 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-15 | 2022-05-16 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-15 | 2022-04-16 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-17 | 2022-04-18 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-08 | 2022-05-09 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-10 | 2022-04-11 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-10 | 2022-04-11 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-17 | 2022-04-18 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-08 | 2022-05-09 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-15 | 2022-05-16 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-24 | 2022-05-26 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-25 | 2022-05-27 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-18 | 2022-04-20 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-20 | 2022-04-22 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-13 | 2022-04-15 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-10 | 2022-04-12 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-27 | 2022-05-29 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-07 | 2022-06-09 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-18 | 2022-04-23 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-25 | 2022-04-30 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-10 | 2022-05-15 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-18 | 2022-05-23 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-27 | 2022-05-28 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-25 | 2022-04-26 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-30 | 2022-05-01 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-25 | 2022-05-26 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-24 | 2022-04-25 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-23 | 2022-04-24 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-30 | 2022-05-01 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-17 | 2022-05-18 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-27 | 2022-05-28 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-03 | 2022-06-05 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-22 | 2022-05-24 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-04 | 2022-05-06 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-08 | 2022-05-10 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-23 | 2022-04-25 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-23 | 2022-04-25 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-05 | 2022-06-07 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-15 | 2022-06-17 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-26 | 2022-05-01 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-01 | 2022-05-06 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-31 | 2022-06-05 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-06 | 2022-06-11 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-16 | 2022-06-17 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-02 | 2022-05-03 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-13 | 2022-05-14 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-11 | 2022-06-12 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-04 | 2022-05-05 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-10 | 2022-05-11 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-19 | 2022-05-20 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-11 | 2022-06-12 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-16 | 2022-06-17 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-08 | 2022-06-10 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-12 | 2022-06-14 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-06 | 2022-05-08 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-09 | 2022-05-11 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-01 | 2022-05-03 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-03 | 2022-05-05 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-15 | 2022-06-17 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-21 | 2022-06-23 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-14 | 2022-05-19 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-26 | 2022-05-31 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-12 | 2022-06-17 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-18 | 2022-06-23 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-23 | 2022-06-24 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-31 | 2022-06-01 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-05 | 2022-06-06 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-18 | 2022-06-19 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-23 | 2022-05-24 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-06-04 | 2022-06-05 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-09 | 2022-06-10 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-18 | 2022-06-19 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-23 | 2022-06-24 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-18 | 2022-06-20 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-18 | 2022-06-20 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-31 | 2022-06-02 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-31 | 2022-06-02 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-28 | 2022-05-30 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-19 | 2022-05-21 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-24 | 2022-06-26 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-24 | 2022-06-26 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-07 | 2022-06-12 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-13 | 2022-06-18 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-19 | 2022-06-24 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-24 | 2022-06-29 | 1

## Plan_D_3
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-30 | 2022-04-04 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-05 | 2022-04-06 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-21 | 2022-03-22 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-08 | 2022-03-09 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-21 | 2022-03-22 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-05 | 2022-04-06 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-23 | 2022-03-25 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-23 | 2022-03-25 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-15 | 2022-03-17 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-19 | 2022-03-21 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-10 | 2022-03-12 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-04-25 | 2022-04-27 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-13 | 2022-05-15 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-18 | 2022-03-23 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-25 | 2022-03-30 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-06 | 2022-04-11 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-13 | 2022-04-14 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-18 | 2022-03-19 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-23 | 2022-03-24 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-10 | 2022-04-11 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-18 | 2022-03-19 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-23 | 2022-03-24 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-02 | 2022-04-03 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-14 | 2022-04-15 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-09 | 2022-04-11 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-06 | 2022-04-08 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-26 | 2022-03-28 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-26 | 2022-03-28 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-18 | 2022-03-20 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-16 | 2022-03-18 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-02 | 2022-05-04 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-19 | 2022-05-21 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-24 | 2022-03-29 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-11 | 2022-04-16 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-17 | 2022-04-22 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-04-23 | 2022-04-24 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-30 | 2022-03-31 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-31 | 2022-04-01 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-16 | 2022-04-17 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-26 | 2022-03-27 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-02 | 2022-04-03 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-16 | 2022-04-17 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-04-23 | 2022-04-24 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-20 | 2022-04-22 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-16 | 2022-04-18 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-03 | 2022-04-05 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-01 | 2022-04-03 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-29 | 2022-03-31 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-30 | 2022-04-01 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-04-26 | 2022-04-28 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-01 | 2022-05-03 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-31 | 2022-04-05 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-05 | 2022-04-10 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-18 | 2022-04-23 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-04-24 | 2022-04-29 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-09 | 2022-05-10 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-10 | 2022-04-11 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-18 | 2022-04-19 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-25 | 2022-04-26 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-08 | 2022-04-09 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-08 | 2022-04-09 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-18 | 2022-04-19 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-25 | 2022-04-26 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-15 | 2022-05-16 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-23 | 2022-04-25 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-28 | 2022-04-30 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-12 | 2022-04-14 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-12 | 2022-04-14 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-09 | 2022-04-11 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-05 | 2022-04-07 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-16 | 2022-05-18 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-12 | 2022-05-14 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-12 | 2022-04-17 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-24 | 2022-04-29 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-30 | 2022-05-05 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-20 | 2022-05-25 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-25 | 2022-05-26 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-29 | 2022-04-30 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-03 | 2022-05-04 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-05 | 2022-05-06 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-29 | 2022-04-30 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-21 | 2022-04-22 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-03 | 2022-05-04 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-07 | 2022-05-08 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-30 | 2022-05-31 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-07 | 2022-05-09 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-10 | 2022-05-12 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-29 | 2022-05-01 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-04 | 2022-05-06 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-17 | 2022-04-19 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-20 | 2022-04-22 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-27 | 2022-05-29 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-05-25 | 2022-05-27 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-30 | 2022-05-05 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-06 | 2022-05-11 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-11 | 2022-05-16 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-31 | 2022-06-05 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-05 | 2022-06-06 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-10 | 2022-05-11 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-11 | 2022-05-12 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-17 | 2022-05-18 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-07 | 2022-05-08 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-05 | 2022-05-06 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-12 | 2022-05-13 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-17 | 2022-05-18 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-05 | 2022-06-06 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-06 | 2022-06-08 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-05 | 2022-06-07 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-01 | 2022-06-03 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-15 | 2022-05-17 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-06 | 2022-05-08 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-09 | 2022-05-11 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-08 | 2022-06-10 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-09 | 2022-06-11 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-14 | 2022-05-19 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-19 | 2022-05-24 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-25 | 2022-05-30 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-06 | 2022-06-11 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-11 | 2022-06-12 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-20 | 2022-05-21 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-24 | 2022-05-25 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-01 | 2022-06-02 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-23 | 2022-05-24 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-22 | 2022-05-23 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-27 | 2022-05-28 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-05-31 | 2022-06-01 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-11 | 2022-06-12 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-05-30 | 2022-06-01 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-02 | 2022-06-04 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-28 | 2022-05-30 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-24 | 2022-05-26 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-19 | 2022-05-21 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-22 | 2022-05-24 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-12 | 2022-06-14 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-12 | 2022-06-14 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-26 | 2022-05-31 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-01 | 2022-06-06 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-07 | 2022-06-12 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-12 | 2022-06-17 | 2

## Plan_D_30
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-20 | 2022-04-25 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-26 | 2022-04-27 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-18 | 2022-03-19 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-26 | 2022-04-27 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-27 | 2022-03-29 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-23 | 2022-03-25 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-04-28 | 2022-04-30 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-27 | 2022-04-29 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-27 | 2022-05-02 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-12 | 2022-05-13 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-16 | 2022-03-17 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-22 | 2022-03-23 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-27 | 2022-03-28 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-28 | 2022-03-29 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-09 | 2022-05-10 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-06 | 2022-05-08 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-05 | 2022-05-07 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-05-02 | 2022-05-04 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-04-03 | 2022-04-05 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-23 | 2022-03-25 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-16 | 2022-03-18 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-14 | 2022-05-16 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-27 | 2022-05-29 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-08 | 2022-04-13 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-13 | 2022-05-18 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-22 | 2022-05-23 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-30 | 2022-03-31 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-03 | 2022-05-04 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-30 | 2022-03-31 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-21 | 2022-04-22 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-22 | 2022-05-23 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-20 | 2022-04-22 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-16 | 2022-04-18 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-09 | 2022-04-11 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-11 | 2022-04-13 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-06 | 2022-04-08 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-31 | 2022-04-02 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-30 | 2022-06-01 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-24 | 2022-05-26 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-02 | 2022-04-07 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-07 | 2022-05-12 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-23 | 2022-05-28 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-28 | 2022-05-29 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-05 | 2022-04-06 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-07 | 2022-04-08 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-15 | 2022-05-16 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-03 | 2022-04-04 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-03 | 2022-04-04 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-10 | 2022-04-11 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-16 | 2022-05-17 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-28 | 2022-05-29 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-13 | 2022-05-15 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-13 | 2022-06-15 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-21 | 2022-04-23 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-15 | 2022-04-17 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-07 | 2022-04-09 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-12 | 2022-04-14 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-19 | 2022-06-21 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-16 | 2022-06-18 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-06 | 2022-04-11 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-12 | 2022-04-17 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-20 | 2022-05-25 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-29 | 2022-06-03 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-04 | 2022-06-05 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-13 | 2022-04-14 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-17 | 2022-04-18 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-01 | 2022-06-02 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-11 | 2022-04-12 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-12 | 2022-04-13 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-17 | 2022-04-18 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-01 | 2022-06-02 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-04 | 2022-06-05 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-30 | 2022-06-01 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-25 | 2022-05-27 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-22 | 2022-05-24 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-16 | 2022-05-18 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-05-10 | 2022-05-12 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-24 | 2022-04-26 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-06 | 2022-06-08 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-03 | 2022-06-05 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-14 | 2022-04-19 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-19 | 2022-04-24 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-03 | 2022-06-08 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-08 | 2022-06-13 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-17 | 2022-06-18 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-24 | 2022-04-25 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-20 | 2022-05-21 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-12 | 2022-06-13 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-22 | 2022-04-23 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-24 | 2022-04-25 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-20 | 2022-05-21 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-11 | 2022-06-12 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-17 | 2022-06-18 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-10 | 2022-06-12 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-10 | 2022-06-12 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-19 | 2022-05-21 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-17 | 2022-05-19 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-09 | 2022-05-11 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-23 | 2022-04-25 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-15 | 2022-06-17 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-22 | 2022-06-24 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-25 | 2022-04-30 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-26 | 2022-05-31 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-13 | 2022-06-18 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-19 | 2022-06-24 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-24 | 2022-06-25 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-05 | 2022-05-06 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-13 | 2022-06-14 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-19 | 2022-06-20 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-03 | 2022-05-04 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-05 | 2022-05-06 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-10 | 2022-06-11 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-19 | 2022-06-20 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-24 | 2022-06-25 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-22 | 2022-06-24 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-18 | 2022-06-20 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-03 | 2022-06-05 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-07 | 2022-06-09 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-04-30 | 2022-05-02 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-21 | 2022-05-23 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-25 | 2022-06-27 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-25 | 2022-06-27 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-06 | 2022-05-11 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-14 | 2022-06-19 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-20 | 2022-06-25 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-25 | 2022-06-30 | 1

## Plan_D_31
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-09 | 2022-04-14 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-15 | 2022-04-16 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-08 | 2022-03-09 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-16 | 2022-04-17 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-24 | 2022-04-26 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-21 | 2022-04-23 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-08 | 2022-03-10 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-08 | 2022-03-10 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-18 | 2022-05-20 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-26 | 2022-05-28 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-24 | 2022-03-29 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-20 | 2022-04-25 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-25 | 2022-04-26 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-16 | 2022-03-17 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-22 | 2022-03-23 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-30 | 2022-03-31 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-29 | 2022-03-30 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-25 | 2022-04-26 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-02 | 2022-05-04 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-22 | 2022-04-24 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-18 | 2022-04-20 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-04-01 | 2022-04-03 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-18 | 2022-03-20 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-24 | 2022-03-26 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-03 | 2022-06-05 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-20 | 2022-05-22 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-26 | 2022-03-31 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-01 | 2022-04-06 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-26 | 2022-05-01 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-08 | 2022-05-09 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-24 | 2022-03-25 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-31 | 2022-04-01 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-08 | 2022-04-09 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-26 | 2022-03-27 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-25 | 2022-03-26 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-01 | 2022-04-02 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-08 | 2022-04-09 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-08 | 2022-05-09 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-06 | 2022-04-08 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-06 | 2022-04-08 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-03 | 2022-04-05 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-31 | 2022-04-02 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-29 | 2022-03-31 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-25 | 2022-03-27 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-07 | 2022-05-09 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-05 | 2022-05-07 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-30 | 2022-04-04 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-14 | 2022-04-19 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-04 | 2022-05-09 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-18 | 2022-05-23 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-30 | 2022-05-31 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-05 | 2022-04-06 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-27 | 2022-04-28 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-15 | 2022-05-16 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-04 | 2022-04-05 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-06 | 2022-04-07 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-27 | 2022-04-28 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-15 | 2022-05-16 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-26 | 2022-05-27 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-16 | 2022-05-18 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-01 | 2022-06-03 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-13 | 2022-05-15 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-25 | 2022-04-27 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-09 | 2022-04-11 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-17 | 2022-04-19 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-09 | 2022-06-11 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-12 | 2022-06-14 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-07 | 2022-04-12 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-29 | 2022-05-04 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-27 | 2022-06-01 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-02 | 2022-06-07 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-10 | 2022-06-11 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-13 | 2022-04-14 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-04 | 2022-05-05 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-02 | 2022-06-03 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-14 | 2022-04-15 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-12 | 2022-04-13 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-04 | 2022-05-05 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-02 | 2022-06-03 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-12 | 2022-06-13 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-06 | 2022-06-08 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-06 | 2022-06-08 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-22 | 2022-05-24 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-10 | 2022-05-12 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-13 | 2022-04-15 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-13 | 2022-04-15 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-09 | 2022-06-11 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-23 | 2022-06-25 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-15 | 2022-04-20 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-05 | 2022-05-10 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-03 | 2022-06-08 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-13 | 2022-06-18 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-18 | 2022-06-19 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-20 | 2022-04-21 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-11 | 2022-05-12 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-08 | 2022-06-09 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-21 | 2022-04-22 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-22 | 2022-04-23 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-11 | 2022-05-12 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-11 | 2022-06-12 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-18 | 2022-06-19 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-13 | 2022-06-15 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-17 | 2022-06-19 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-29 | 2022-05-31 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-13 | 2022-05-15 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-28 | 2022-04-30 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-10 | 2022-05-12 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-20 | 2022-06-22 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-20 | 2022-06-22 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-23 | 2022-04-28 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-16 | 2022-05-21 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-12 | 2022-06-17 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-20 | 2022-06-25 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-25 | 2022-06-26 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-01 | 2022-05-02 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-24 | 2022-05-25 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-20 | 2022-06-21 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-04-29 | 2022-04-30 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-04-29 | 2022-04-30 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-24 | 2022-05-25 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-20 | 2022-06-21 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-25 | 2022-06-26 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-17 | 2022-06-19 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-23 | 2022-06-25 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-23 | 2022-05-25 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-25 | 2022-05-27 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-01 | 2022-05-03 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-04-28 | 2022-04-30 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-26 | 2022-06-28 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-26 | 2022-06-28 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-10 | 2022-05-15 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-25 | 2022-05-30 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-21 | 2022-06-26 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-26 | 2022-07-01 | 2

## Plan_D_32
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-14 | 2022-04-19 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-26 | 2022-04-27 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-26 | 2022-04-27 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-20 | 2022-04-22 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-23 | 2022-03-25 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-01 | 2022-05-03 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-01 | 2022-05-03 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-29 | 2022-05-04 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-25 | 2022-05-26 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-16 | 2022-03-17 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-23 | 2022-03-24 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-28 | 2022-03-29 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-16 | 2022-03-17 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-18 | 2022-03-19 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-28 | 2022-03-29 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-05 | 2022-05-06 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-16 | 2022-05-18 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-17 | 2022-05-19 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-05-14 | 2022-05-16 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-18 | 2022-03-20 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-28 | 2022-05-30 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-25 | 2022-05-27 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-26 | 2022-05-31 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-02 | 2022-06-03 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-24 | 2022-03-25 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-31 | 2022-04-01 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-06 | 2022-04-07 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-26 | 2022-03-27 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-25 | 2022-03-26 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-13 | 2022-04-14 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-02 | 2022-06-03 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-17 | 2022-04-19 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-16 | 2022-04-18 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-03-30 | 2022-04-01 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-30 | 2022-04-01 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-27 | 2022-03-29 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-27 | 2022-03-29 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-03 | 2022-06-05 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-01 | 2022-06-03 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-02 | 2022-04-07 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-08 | 2022-04-13 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-12 | 2022-05-17 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-03 | 2022-06-08 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-08 | 2022-06-09 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-08 | 2022-04-09 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-22 | 2022-04-23 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-29 | 2022-05-30 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-08 | 2022-04-09 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-10 | 2022-04-11 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-14 | 2022-04-15 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-29 | 2022-05-30 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-08 | 2022-06-09 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-24 | 2022-05-26 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-31 | 2022-06-02 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-19 | 2022-04-21 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-13 | 2022-04-15 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-07 | 2022-04-09 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-07 | 2022-04-09 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-12 | 2022-06-14 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-09 | 2022-06-11 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-11 | 2022-04-16 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-25 | 2022-04-30 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-01 | 2022-06-06 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-09 | 2022-06-14 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-14 | 2022-06-15 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-18 | 2022-04-19 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-14 | 2022-05-15 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-06 | 2022-06-07 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-18 | 2022-04-19 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-16 | 2022-04-17 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-14 | 2022-05-15 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-06 | 2022-06-07 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-14 | 2022-06-15 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-07 | 2022-06-09 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-06 | 2022-06-08 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-05 | 2022-05-07 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-04 | 2022-05-06 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-24 | 2022-04-26 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-24 | 2022-04-26 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-15 | 2022-06-17 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-15 | 2022-06-17 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-19 | 2022-04-24 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-16 | 2022-05-21 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-07 | 2022-06-12 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-15 | 2022-06-20 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-20 | 2022-06-21 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-24 | 2022-04-25 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-21 | 2022-05-22 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-12 | 2022-06-13 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-24 | 2022-04-25 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-30 | 2022-05-01 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-21 | 2022-05-22 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-12 | 2022-06-13 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-20 | 2022-06-21 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-12 | 2022-06-14 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-18 | 2022-06-20 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-22 | 2022-05-24 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-21 | 2022-05-23 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-12 | 2022-05-14 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-27 | 2022-04-29 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-24 | 2022-06-26 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-21 | 2022-06-23 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-01 | 2022-05-06 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-22 | 2022-05-27 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-13 | 2022-06-18 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-21 | 2022-06-26 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-26 | 2022-06-27 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-06 | 2022-05-07 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-27 | 2022-05-28 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-18 | 2022-06-19 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-08 | 2022-05-09 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-08 | 2022-05-09 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-27 | 2022-05-28 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-18 | 2022-06-19 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-26 | 2022-06-27 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-18 | 2022-06-20 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-23 | 2022-06-25 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-28 | 2022-05-30 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-04 | 2022-06-06 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-08 | 2022-05-10 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-08 | 2022-05-10 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-27 | 2022-06-29 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-27 | 2022-06-29 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-09 | 2022-05-14 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-28 | 2022-06-02 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-22 | 2022-06-27 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-27 | 2022-07-02 | 2

## Plan_D_33
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-16 | 2022-04-21 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-30 | 2022-05-01 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-21 | 2022-03-22 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-27 | 2022-04-28 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-05-15 | 2022-05-17 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-17 | 2022-04-19 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-21 | 2022-05-23 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-29 | 2022-05-31 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-05 | 2022-05-10 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-17 | 2022-05-18 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-23 | 2022-03-24 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-28 | 2022-03-29 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-28 | 2022-03-29 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-19 | 2022-05-20 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-06 | 2022-05-08 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-08 | 2022-05-10 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-26 | 2022-03-28 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-26 | 2022-03-28 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-23 | 2022-03-25 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-23 | 2022-03-25 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-14 | 2022-05-16 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-12 | 2022-05-14 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-21 | 2022-05-26 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-27 | 2022-05-28 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-31 | 2022-04-01 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-05 | 2022-04-06 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-07 | 2022-04-08 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-27 | 2022-05-28 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-22 | 2022-05-24 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-26 | 2022-05-28 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-05 | 2022-04-07 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-05-01 | 2022-05-03 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-31 | 2022-04-02 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-31 | 2022-04-02 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-11 | 2022-06-13 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-01 | 2022-06-03 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-03 | 2022-04-08 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-10 | 2022-04-15 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-28 | 2022-06-02 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-02 | 2022-06-03 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-05 | 2022-04-06 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-09 | 2022-04-10 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-18 | 2022-04-19 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-02 | 2022-04-03 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-03 | 2022-04-04 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-09 | 2022-04-10 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-21 | 2022-04-22 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-02 | 2022-06-03 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-01 | 2022-05-03 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-27 | 2022-04-29 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-19 | 2022-04-21 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-20 | 2022-04-22 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-10 | 2022-04-12 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-10 | 2022-04-12 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-15 | 2022-06-17 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-08 | 2022-06-10 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-07 | 2022-04-12 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-16 | 2022-04-21 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-22 | 2022-04-27 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-03 | 2022-06-08 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-09 | 2022-06-10 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-12 | 2022-04-13 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-22 | 2022-04-23 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-08 | 2022-05-09 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-12 | 2022-04-13 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-16 | 2022-04-17 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-28 | 2022-04-29 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-04-30 | 2022-05-01 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-11 | 2022-06-12 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-04 | 2022-05-06 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-18 | 2022-05-20 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-24 | 2022-04-26 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-28 | 2022-04-30 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-22 | 2022-04-24 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-13 | 2022-04-15 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-11 | 2022-06-13 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-14 | 2022-06-16 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-27 | 2022-05-02 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-03 | 2022-05-08 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-11 | 2022-05-16 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-15 | 2022-06-20 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-20 | 2022-06-21 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-02 | 2022-05-03 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-11 | 2022-05-12 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-07 | 2022-06-08 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-10 | 2022-05-11 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-02 | 2022-05-03 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-12 | 2022-05-13 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-07 | 2022-06-08 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-20 | 2022-06-21 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-08 | 2022-06-10 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-04 | 2022-06-06 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-27 | 2022-05-29 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-24 | 2022-05-26 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-11 | 2022-05-13 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-18 | 2022-05-20 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-21 | 2022-06-23 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-24 | 2022-06-26 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-11 | 2022-05-16 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-17 | 2022-05-22 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-09 | 2022-06-14 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-22 | 2022-06-27 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-27 | 2022-06-28 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-24 | 2022-05-25 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-14 | 2022-06-15 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-22 | 2022-06-23 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-22 | 2022-05-23 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-22 | 2022-05-23 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-14 | 2022-06-15 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-22 | 2022-06-23 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-27 | 2022-06-28 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-22 | 2022-06-24 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-25 | 2022-06-27 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-17 | 2022-06-19 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-18 | 2022-06-20 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-06-04 | 2022-06-06 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-01 | 2022-06-03 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-27 | 2022-06-29 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-28 | 2022-06-30 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-27 | 2022-06-01 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-15 | 2022-06-20 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-23 | 2022-06-28 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-28 | 2022-07-03 | 2

## Plan_D_34
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-21 | 2022-04-26 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-28 | 2022-04-29 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-19 | 2022-03-20 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-19 | 2022-03-20 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-28 | 2022-04-29 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-26 | 2022-03-28 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-26 | 2022-03-28 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-30 | 2022-06-01 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-14 | 2022-06-16 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-17 | 2022-03-22 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-23 | 2022-03-28 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-04 | 2022-05-09 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-09 | 2022-05-10 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-22 | 2022-03-23 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-28 | 2022-03-29 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-28 | 2022-03-29 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-19 | 2022-05-20 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-10 | 2022-05-12 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-24 | 2022-05-26 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-13 | 2022-04-15 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-04-13 | 2022-04-15 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-23 | 2022-03-25 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-23 | 2022-03-25 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-04 | 2022-06-06 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-07 | 2022-06-09 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-20 | 2022-05-25 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-30 | 2022-05-31 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-31 | 2022-04-01 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-08 | 2022-04-09 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-01 | 2022-04-02 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-24 | 2022-04-25 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-28 | 2022-05-29 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-27 | 2022-05-29 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-29 | 2022-05-31 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-22 | 2022-04-24 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-01 | 2022-04-03 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-29 | 2022-03-31 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-30 | 2022-04-01 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-01 | 2022-06-03 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-03 | 2022-06-05 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-29 | 2022-04-03 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-05 | 2022-04-10 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-27 | 2022-05-02 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-01 | 2022-06-06 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-09 | 2022-06-10 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-06 | 2022-04-07 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-13 | 2022-04-14 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-02 | 2022-05-03 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-06 | 2022-04-07 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-03 | 2022-04-04 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-10 | 2022-04-11 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-12 | 2022-05-13 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-09 | 2022-06-10 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-07 | 2022-06-09 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-26 | 2022-05-28 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-03 | 2022-05-05 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-10 | 2022-04-12 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-04 | 2022-04-06 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-04 | 2022-04-06 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-12 | 2022-06-14 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-10 | 2022-06-12 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-08 | 2022-04-13 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-14 | 2022-04-19 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-14 | 2022-05-19 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-10 | 2022-06-15 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-15 | 2022-06-16 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-15 | 2022-04-16 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-19 | 2022-04-20 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-25 | 2022-05-26 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-13 | 2022-04-14 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-15 | 2022-04-16 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-19 | 2022-04-20 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-07 | 2022-06-08 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-15 | 2022-06-16 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-19 | 2022-05-21 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-19 | 2022-05-21 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-09 | 2022-05-11 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-24 | 2022-04-26 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-16 | 2022-04-18 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-16 | 2022-04-18 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-15 | 2022-06-17 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-17 | 2022-06-19 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-16 | 2022-04-21 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-25 | 2022-04-30 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-08 | 2022-06-13 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-16 | 2022-06-21 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-21 | 2022-06-22 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-21 | 2022-04-22 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-04-30 | 2022-05-01 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-17 | 2022-06-18 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-21 | 2022-04-22 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-24 | 2022-04-25 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-04-30 | 2022-05-01 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-17 | 2022-06-18 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-21 | 2022-06-22 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-20 | 2022-06-22 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-18 | 2022-06-20 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-22 | 2022-05-24 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-02 | 2022-05-04 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-27 | 2022-04-29 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-21 | 2022-04-23 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-26 | 2022-06-28 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-26 | 2022-06-28 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-03 | 2022-05-08 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-10 | 2022-05-15 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-18 | 2022-06-23 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-23 | 2022-06-28 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-28 | 2022-06-29 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-15 | 2022-05-16 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-25 | 2022-05-26 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-23 | 2022-06-24 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-10 | 2022-05-11 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-15 | 2022-05-16 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-17 | 2022-05-18 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-23 | 2022-06-24 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-28 | 2022-06-29 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-23 | 2022-06-25 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-23 | 2022-06-25 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-16 | 2022-05-18 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-15 | 2022-05-17 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-12 | 2022-05-14 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-13 | 2022-05-15 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-29 | 2022-07-01 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-29 | 2022-07-01 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-17 | 2022-05-22 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-27 | 2022-06-01 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-24 | 2022-06-29 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-29 | 2022-07-04 | 2

## Plan_D_35
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-19 | 2022-04-24 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-27 | 2022-04-28 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-08 | 2022-03-09 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-19 | 2022-03-20 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-19 | 2022-03-20 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-05-02 | 2022-05-03 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-05-25 | 2022-05-27 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-05-26 | 2022-05-28 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-05-03 | 2022-05-05 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-13 | 2022-03-15 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-10 | 2022-03-12 | 4
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-10 | 2022-03-12 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-03 | 2022-06-05 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-28 | 2022-05-30 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-07 | 2022-05-12 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-25 | 2022-05-26 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-23 | 2022-03-24 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-28 | 2022-03-29 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-07 | 2022-04-08 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-25 | 2022-05-26 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-24 | 2022-04-26 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-24 | 2022-04-26 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-21 | 2022-03-23 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-18 | 2022-03-20 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-15 | 2022-05-17 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-18 | 2022-05-20 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-28 | 2022-05-03 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-31 | 2022-06-05 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-05 | 2022-06-06 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-30 | 2022-03-31 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-05 | 2022-05-06 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-27 | 2022-03-28 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-06 | 2022-05-07 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-05 | 2022-06-06 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-12 | 2022-05-14 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-11 | 2022-05-13 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-03-30 | 2022-04-01 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-30 | 2022-04-01 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-25 | 2022-03-27 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-25 | 2022-03-27 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-10 | 2022-06-12 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-09 | 2022-06-11 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-03 | 2022-04-08 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-08 | 2022-05-13 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-06 | 2022-06-11 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-11 | 2022-06-12 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-04 | 2022-04-05 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-08 | 2022-04-09 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-19 | 2022-05-20 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-02 | 2022-04-03 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-10 | 2022-04-11 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-15 | 2022-05-16 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-11 | 2022-06-12 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-14 | 2022-05-16 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-17 | 2022-05-19 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-14 | 2022-04-16 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-14 | 2022-04-16 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-02 | 2022-04-04 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-02 | 2022-04-04 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-13 | 2022-06-15 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-12 | 2022-06-14 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-06 | 2022-04-11 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-13 | 2022-04-18 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-25 | 2022-05-30 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-12 | 2022-06-17 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-17 | 2022-06-18 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-11 | 2022-04-12 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-19 | 2022-04-20 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-09 | 2022-06-10 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-13 | 2022-04-14 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-15 | 2022-04-16 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-19 | 2022-04-20 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-09 | 2022-06-10 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-17 | 2022-06-18 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-07 | 2022-06-09 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-05 | 2022-06-07 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-21 | 2022-05-23 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-08 | 2022-05-10 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-05-05 | 2022-05-07 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-11 | 2022-04-13 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-17 | 2022-06-19 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-22 | 2022-06-24 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-16 | 2022-04-21 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-22 | 2022-04-27 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-10 | 2022-06-15 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-18 | 2022-06-23 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-23 | 2022-06-24 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-23 | 2022-04-24 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-17 | 2022-05-18 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-15 | 2022-06-16 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-21 | 2022-04-22 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-23 | 2022-04-24 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-14 | 2022-05-15 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-15 | 2022-06-16 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-23 | 2022-06-24 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-18 | 2022-06-20 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-15 | 2022-06-17 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-04-30 | 2022-05-02 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-04-30 | 2022-05-02 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-27 | 2022-04-29 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-21 | 2022-04-23 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-27 | 2022-06-29 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-27 | 2022-06-29 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-30 | 2022-05-05 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-21 | 2022-05-26 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-16 | 2022-06-21 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-24 | 2022-06-29 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-29 | 2022-06-30 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-16 | 2022-05-17 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-29 | 2022-05-30 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-21 | 2022-06-22 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-12 | 2022-05-13 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-10 | 2022-05-11 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-28 | 2022-05-29 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-21 | 2022-06-22 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-29 | 2022-06-30 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-21 | 2022-06-23 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-24 | 2022-06-26 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-31 | 2022-06-02 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-31 | 2022-06-02 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-22 | 2022-05-24 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-07 | 2022-05-09 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-30 | 2022-07-02 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-30 | 2022-07-02 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-19 | 2022-05-24 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-31 | 2022-06-05 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-25 | 2022-06-30 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-30 | 2022-07-05 | 1

## Plan_D_36
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-21 | 2022-03-26 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-30 | 2022-04-04 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-06 | 2022-04-07 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-28 | 2022-03-29 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-08 | 2022-03-09 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-28 | 2022-03-29 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-06 | 2022-04-07 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-05-13 | 2022-05-15 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-05-13 | 2022-05-15 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-19 | 2022-05-21 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-19 | 2022-05-21 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-15 | 2022-03-20 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-21 | 2022-04-26 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-10 | 2022-05-15 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-15 | 2022-05-16 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-16 | 2022-03-17 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-22 | 2022-03-23 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-05-10 | 2022-05-11 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-28 | 2022-04-29 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-17 | 2022-05-18 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-01 | 2022-05-03 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-01 | 2022-05-03 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-20 | 2022-03-22 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-20 | 2022-03-22 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-17 | 2022-03-19 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-17 | 2022-03-19 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-16 | 2022-05-18 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-16 | 2022-05-18 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-24 | 2022-03-29 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-05-13 | 2022-05-18 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-18 | 2022-05-23 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-27 | 2022-05-28 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-10 | 2022-04-11 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-20 | 2022-05-21 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-30 | 2022-03-31 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-24 | 2022-05-25 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-25 | 2022-05-26 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-23 | 2022-05-25 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-23 | 2022-05-25 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-03-29 | 2022-03-31 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-29 | 2022-03-31 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-26 | 2022-03-28 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-26 | 2022-03-28 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-08 | 2022-06-10 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-08 | 2022-06-10 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-12 | 2022-04-17 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-25 | 2022-05-30 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-31 | 2022-06-05 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-10 | 2022-06-11 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-02 | 2022-04-03 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-21 | 2022-04-22 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-06-05 | 2022-06-06 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-02 | 2022-04-03 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-04 | 2022-04-05 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-30 | 2022-05-01 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-06-05 | 2022-06-06 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-10 | 2022-06-11 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-05 | 2022-06-07 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-04 | 2022-06-06 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-23 | 2022-04-25 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-23 | 2022-04-25 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-20 | 2022-04-22 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-20 | 2022-04-22 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-13 | 2022-06-15 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-13 | 2022-06-15 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-05 | 2022-04-10 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-01 | 2022-05-06 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-06 | 2022-06-11 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-12 | 2022-06-17 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-17 | 2022-06-18 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-10 | 2022-04-11 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-06 | 2022-05-07 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-12 | 2022-06-13 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-19 | 2022-04-20 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-20 | 2022-04-21 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-06 | 2022-05-07 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-12 | 2022-06-13 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-17 | 2022-06-18 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-16 | 2022-06-18 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-16 | 2022-06-18 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-07 | 2022-05-09 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-10 | 2022-05-12 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-10 | 2022-04-12 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-10 | 2022-04-12 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-22 | 2022-06-24 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-19 | 2022-06-21 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-21 | 2022-04-26 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-07 | 2022-05-12 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-13 | 2022-06-18 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-18 | 2022-06-23 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-23 | 2022-06-24 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-28 | 2022-04-29 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-16 | 2022-05-17 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-19 | 2022-06-20 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-26 | 2022-04-27 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-26 | 2022-04-27 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-13 | 2022-05-14 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-19 | 2022-06-20 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-23 | 2022-06-24 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-22 | 2022-06-24 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-19 | 2022-06-21 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-31 | 2022-06-02 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-31 | 2022-06-02 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-07 | 2022-05-09 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-26 | 2022-04-28 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-28 | 2022-06-30 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-25 | 2022-06-27 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-29 | 2022-05-04 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-21 | 2022-05-26 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-20 | 2022-06-25 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-25 | 2022-06-30 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-30 | 2022-07-01 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-04 | 2022-05-05 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-29 | 2022-05-30 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-25 | 2022-06-26 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-11 | 2022-05-12 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-08 | 2022-05-09 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-29 | 2022-05-30 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-25 | 2022-06-26 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-30 | 2022-07-01 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-25 | 2022-06-27 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-28 | 2022-06-30 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-26 | 2022-05-28 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-26 | 2022-05-28 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-04 | 2022-05-06 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-04 | 2022-05-06 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-01 | 2022-07-03 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-01 | 2022-07-03 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-27 | 2022-06-01 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-02 | 2022-06-07 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-26 | 2022-07-01 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-01 | 2022-07-06 | 2

## Plan_D_37
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-19 | 2022-03-24 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-03-26 | 2022-03-27 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-21 | 2022-03-22 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-21 | 2022-03-22 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-03-27 | 2022-03-28 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-06-12 | 2022-06-14 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-06-09 | 2022-06-11 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 4
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-16 | 2022-06-18 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-23 | 2022-06-25 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-25 | 2022-03-30 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-01 | 2022-04-06 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-24 | 2022-04-29 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-29 | 2022-04-30 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-16 | 2022-03-17 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-30 | 2022-03-31 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-06 | 2022-04-07 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-30 | 2022-03-31 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-06 | 2022-04-07 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-29 | 2022-04-30 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-14 | 2022-05-16 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-09 | 2022-05-11 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-30 | 2022-04-01 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-30 | 2022-04-01 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-23 | 2022-03-25 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-17 | 2022-03-19 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-20 | 2022-05-22 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-20 | 2022-05-22 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-01 | 2022-04-06 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-07 | 2022-04-12 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-30 | 2022-05-05 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-08 | 2022-05-09 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-09 | 2022-04-10 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-12 | 2022-04-13 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-23 | 2022-03-24 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-09 | 2022-04-10 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-12 | 2022-04-13 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-08 | 2022-05-09 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-09 | 2022-05-11 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-14 | 2022-05-16 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-06 | 2022-04-08 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-06 | 2022-04-08 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-27 | 2022-03-29 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-26 | 2022-03-28 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-17 | 2022-05-19 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-17 | 2022-05-19 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-10 | 2022-04-15 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-07 | 2022-05-12 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-12 | 2022-05-17 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-17 | 2022-05-18 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-04 | 2022-04-05 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-15 | 2022-04-16 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-16 | 2022-05-17 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-01 | 2022-04-02 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-03 | 2022-04-04 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-15 | 2022-04-16 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-13 | 2022-05-14 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-21 | 2022-05-22 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-04 | 2022-06-06 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-10 | 2022-06-12 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-15 | 2022-04-17 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-15 | 2022-04-17 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-02 | 2022-04-04 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-03 | 2022-04-05 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-13 | 2022-06-15 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-16 | 2022-06-18 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-13 | 2022-04-18 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-01 | 2022-05-06 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-18 | 2022-05-23 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-25 | 2022-05-30 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-08 | 2022-06-09 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-18 | 2022-04-19 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-21 | 2022-05-22 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-24 | 2022-05-25 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-19 | 2022-04-20 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-22 | 2022-04-23 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-14 | 2022-05-15 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-24 | 2022-05-25 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-08 | 2022-06-09 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-26 | 2022-05-28 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-26 | 2022-05-28 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-06 | 2022-05-08 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-06 | 2022-05-08 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-18 | 2022-04-20 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-18 | 2022-04-20 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-24 | 2022-06-26 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-01 | 2022-06-03 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-23 | 2022-04-28 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-24 | 2022-05-29 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-01 | 2022-06-06 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-14 | 2022-06-19 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-24 | 2022-06-25 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-10 | 2022-05-11 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-11 | 2022-06-12 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-21 | 2022-06-22 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-01 | 2022-05-02 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-01 | 2022-05-02 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-10 | 2022-06-11 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-21 | 2022-06-22 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-24 | 2022-06-25 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-07 | 2022-06-09 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-06 | 2022-06-08 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-29 | 2022-05-31 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-29 | 2022-05-31 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-28 | 2022-04-30 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-28 | 2022-04-30 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-30 | 2022-07-02 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-30 | 2022-07-02 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-18 | 2022-05-23 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-14 | 2022-06-19 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-22 | 2022-06-27 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-27 | 2022-07-02 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-02 | 2022-07-03 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-27 | 2022-05-28 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-19 | 2022-06-20 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-27 | 2022-06-28 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-29 | 2022-05-30 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-29 | 2022-05-30 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-19 | 2022-06-20 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-27 | 2022-06-28 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-02 | 2022-07-03 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-27 | 2022-06-29 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-27 | 2022-06-29 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-19 | 2022-06-21 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-19 | 2022-06-21 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-23 | 2022-05-25 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-23 | 2022-05-25 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-03 | 2022-07-05 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-03 | 2022-07-05 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-01 | 2022-06-06 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-21 | 2022-06-26 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-28 | 2022-07-03 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-03 | 2022-07-08 | 2

## Plan_D_38
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-16 | 2022-03-21 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-10 | 2022-04-15 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-16 | 2022-04-17 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-21 | 2022-03-22 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-19 | 2022-03-20 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-21 | 2022-03-22 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-15 | 2022-04-16 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-06-08 | 2022-06-10 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-06-06 | 2022-06-08 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-12 | 2022-06-14 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-12 | 2022-06-14 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-22 | 2022-03-27 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-28 | 2022-04-02 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-20 | 2022-05-25 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-06-02 | 2022-06-03 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-29 | 2022-03-30 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-13 | 2022-04-14 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-29 | 2022-03-30 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-02 | 2022-04-03 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-06-01 | 2022-06-02 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-02 | 2022-04-04 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-24 | 2022-05-26 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-27 | 2022-03-29 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-27 | 2022-03-29 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-24 | 2022-03-26 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-24 | 2022-03-26 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-17 | 2022-06-19 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-30 | 2022-06-01 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-04 | 2022-04-09 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-16 | 2022-04-21 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-06-04 | 2022-06-09 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-09 | 2022-06-10 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-24 | 2022-03-25 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-10 | 2022-04-11 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-22 | 2022-04-23 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-23 | 2022-03-24 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-10 | 2022-04-11 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-28 | 2022-04-29 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-09 | 2022-06-10 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-22 | 2022-05-24 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-06 | 2022-05-08 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-09 | 2022-04-11 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-09 | 2022-04-11 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-30 | 2022-04-01 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-05 | 2022-04-07 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-15 | 2022-06-17 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-09 | 2022-06-11 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-11 | 2022-04-16 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-03 | 2022-05-08 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-10 | 2022-06-15 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-15 | 2022-06-16 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-03-31 | 2022-04-01 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-17 | 2022-04-18 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-08 | 2022-05-09 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-03-31 | 2022-04-01 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-18 | 2022-04-19 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-08 | 2022-05-09 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-15 | 2022-06-16 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-28 | 2022-05-30 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-27 | 2022-05-29 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-16 | 2022-04-18 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-16 | 2022-04-18 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-03-31 | 2022-04-02 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-03 | 2022-04-05 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-07-01 | 2022-07-03 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-07-01 | 2022-07-03 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-03 | 2022-04-08 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-25 | 2022-04-30 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-11 | 2022-05-16 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-16 | 2022-06-21 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-21 | 2022-06-22 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-25 | 2022-04-26 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-10 | 2022-05-11 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-16 | 2022-05-17 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-12 | 2022-04-13 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-26 | 2022-04-27 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-10 | 2022-05-11 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-16 | 2022-05-17 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-21 | 2022-06-22 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-20 | 2022-05-22 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-19 | 2022-05-21 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-30 | 2022-05-02 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-30 | 2022-05-02 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-12 | 2022-04-14 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-12 | 2022-04-14 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-21 | 2022-06-23 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-21 | 2022-06-23 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-27 | 2022-05-02 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-11 | 2022-05-16 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-20 | 2022-05-25 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-22 | 2022-06-27 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-27 | 2022-06-28 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-02 | 2022-05-03 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-24 | 2022-05-25 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-25 | 2022-05-26 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-02 | 2022-05-03 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-04 | 2022-05-05 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-23 | 2022-05-24 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-30 | 2022-05-31 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-27 | 2022-06-28 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-18 | 2022-06-20 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-31 | 2022-06-02 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-16 | 2022-05-18 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-16 | 2022-05-18 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-03 | 2022-05-05 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-03 | 2022-05-05 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-27 | 2022-06-29 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-27 | 2022-06-29 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-05 | 2022-05-10 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-29 | 2022-06-03 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-18 | 2022-06-23 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-28 | 2022-07-03 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-03 | 2022-07-04 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-30 | 2022-05-31 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-04 | 2022-06-05 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-25 | 2022-06-26 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-21 | 2022-05-22 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-21 | 2022-05-22 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-04 | 2022-06-05 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-25 | 2022-06-26 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-03 | 2022-07-04 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-24 | 2022-06-26 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-24 | 2022-06-26 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-03 | 2022-06-05 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-03 | 2022-06-05 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-10 | 2022-05-12 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-10 | 2022-05-12 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-04 | 2022-07-06 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-04 | 2022-07-06 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-31 | 2022-06-05 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-06 | 2022-06-11 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-29 | 2022-07-04 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-04 | 2022-07-09 | 2

## Plan_D_39
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-06 | 2022-04-11 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-12 | 2022-04-13 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-19 | 2022-03-20 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-19 | 2022-03-20 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-12 | 2022-04-13 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-28 | 2022-03-30 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-05 | 2022-04-07 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-16 | 2022-05-18 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-17 | 2022-04-19 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-13 | 2022-04-18 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-18 | 2022-04-19 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-29 | 2022-03-30 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-28 | 2022-03-29 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-10 | 2022-05-11 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-21 | 2022-04-23 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-24 | 2022-05-26 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-21 | 2022-03-23 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-18 | 2022-03-20 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-31 | 2022-06-02 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-28 | 2022-05-30 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-30 | 2022-05-05 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-13 | 2022-05-18 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-18 | 2022-05-19 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-30 | 2022-03-31 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-13 | 2022-05-14 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-05 | 2022-05-06 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-28 | 2022-05-29 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-05 | 2022-05-07 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-24 | 2022-05-26 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-03-30 | 2022-04-01 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-31 | 2022-04-02 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-25 | 2022-03-27 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-25 | 2022-03-27 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-30 | 2022-06-01 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-27 | 2022-05-29 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-04 | 2022-04-09 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-19 | 2022-05-24 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-29 | 2022-06-03 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-06 | 2022-06-07 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-02 | 2022-04-03 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-09 | 2022-04-10 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-27 | 2022-05-28 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-02 | 2022-04-03 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-06 | 2022-04-07 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-09 | 2022-04-10 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-26 | 2022-05-27 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-05 | 2022-06-06 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-06 | 2022-06-08 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-08 | 2022-06-10 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-13 | 2022-04-15 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-13 | 2022-04-15 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-02 | 2022-04-04 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-05 | 2022-04-07 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-12 | 2022-06-14 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-21 | 2022-06-23 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-13 | 2022-04-18 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-20 | 2022-04-25 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-04 | 2022-06-09 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-11 | 2022-06-16 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-16 | 2022-06-17 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-21 | 2022-04-22 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-28 | 2022-04-29 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-10 | 2022-06-11 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-21 | 2022-04-22 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-19 | 2022-04-20 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-26 | 2022-04-27 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-10 | 2022-06-11 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-16 | 2022-06-17 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-13 | 2022-06-15 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-10 | 2022-06-12 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-13 | 2022-05-15 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-25 | 2022-04-27 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-18 | 2022-04-20 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-21 | 2022-04-23 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-20 | 2022-06-22 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-25 | 2022-06-27 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-23 | 2022-04-28 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-28 | 2022-06-02 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-11 | 2022-06-16 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-17 | 2022-06-22 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-25 | 2022-06-26 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-01 | 2022-05-02 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-13 | 2022-06-14 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-19 | 2022-06-20 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-01 | 2022-05-02 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-28 | 2022-04-29 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-07 | 2022-06-08 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-19 | 2022-06-20 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-25 | 2022-06-26 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-17 | 2022-06-19 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-16 | 2022-06-18 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-02 | 2022-06-04 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-05 | 2022-06-07 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-07 | 2022-05-09 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-28 | 2022-04-30 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-29 | 2022-07-01 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-29 | 2022-07-01 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-07 | 2022-05-12 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-17 | 2022-06-22 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-23 | 2022-06-28 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-29 | 2022-07-04 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-04 | 2022-07-05 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-06-02 | 2022-06-03 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-23 | 2022-06-24 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-29 | 2022-06-30 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-06-02 | 2022-06-03 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-12 | 2022-05-13 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-23 | 2022-06-24 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-29 | 2022-06-30 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-04 | 2022-07-05 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-02 | 2022-07-04 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-02 | 2022-07-04 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-26 | 2022-06-28 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-23 | 2022-06-25 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-06-03 | 2022-06-05 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-13 | 2022-05-15 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-05 | 2022-07-07 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-05 | 2022-07-07 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-03 | 2022-06-08 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-24 | 2022-06-29 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-30 | 2022-07-05 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-05 | 2022-07-10 | 2

## Plan_D_4
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-16 | 2022-04-21 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-21 | 2022-04-22 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-18 | 2022-03-19 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-21 | 2022-04-22 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-08 | 2022-04-10 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-26 | 2022-03-28 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-20 | 2022-03-22 | 4
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-23 | 2022-03-25 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-18 | 2022-03-20 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-03 | 2022-05-05 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-21 | 2022-04-23 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-22 | 2022-04-27 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-27 | 2022-04-28 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-30 | 2022-03-31 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-30 | 2022-03-31 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-29 | 2022-04-30 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-11 | 2022-04-13 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-02 | 2022-04-04 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-30 | 2022-04-01 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-23 | 2022-03-25 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-15 | 2022-03-17 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-09 | 2022-05-11 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-03 | 2022-05-05 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-04 | 2022-05-09 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-13 | 2022-05-14 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-26 | 2022-03-27 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-01 | 2022-04-02 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-09 | 2022-04-10 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-01 | 2022-04-02 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-05 | 2022-04-06 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-13 | 2022-05-14 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-15 | 2022-04-17 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-20 | 2022-04-22 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-13 | 2022-04-15 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-02 | 2022-04-04 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-26 | 2022-03-28 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-30 | 2022-04-01 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-09 | 2022-05-11 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-28 | 2022-05-30 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-03 | 2022-04-08 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-10 | 2022-04-15 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-14 | 2022-05-19 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-19 | 2022-05-20 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-05 | 2022-04-06 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-13 | 2022-04-14 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-19 | 2022-04-20 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-07 | 2022-04-08 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-07 | 2022-04-08 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-09 | 2022-04-10 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-19 | 2022-04-20 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-19 | 2022-05-20 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-26 | 2022-04-28 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-26 | 2022-04-28 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-16 | 2022-04-18 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-08 | 2022-04-10 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-05 | 2022-04-07 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-05 | 2022-04-07 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-21 | 2022-05-23 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-05 | 2022-06-07 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-08 | 2022-04-13 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-14 | 2022-04-19 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-10 | 2022-05-15 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-20 | 2022-05-25 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-25 | 2022-05-26 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-15 | 2022-04-16 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-23 | 2022-04-24 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-15 | 2022-05-16 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-15 | 2022-04-16 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-13 | 2022-04-14 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-23 | 2022-04-24 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-15 | 2022-05-16 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-25 | 2022-05-26 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-15 | 2022-05-17 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-18 | 2022-05-20 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-29 | 2022-05-01 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-29 | 2022-05-01 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-23 | 2022-04-25 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-18 | 2022-04-20 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-25 | 2022-05-27 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-05-25 | 2022-05-27 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-20 | 2022-04-25 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-28 | 2022-05-03 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-16 | 2022-05-21 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-26 | 2022-05-31 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-05 | 2022-06-06 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-26 | 2022-04-27 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-23 | 2022-05-24 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-29 | 2022-05-30 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-28 | 2022-04-29 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-25 | 2022-04-26 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-11 | 2022-05-12 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-29 | 2022-05-30 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-05 | 2022-06-06 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-28 | 2022-05-30 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-22 | 2022-05-24 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-15 | 2022-05-17 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-18 | 2022-05-20 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-12 | 2022-05-14 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-12 | 2022-05-14 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-05-31 | 2022-06-02 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-10 | 2022-06-12 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-30 | 2022-05-05 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-27 | 2022-06-01 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-01 | 2022-06-06 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-07 | 2022-06-12 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-12 | 2022-06-13 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-05 | 2022-05-06 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-01 | 2022-06-02 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-07 | 2022-06-08 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-07 | 2022-05-08 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-07 | 2022-05-08 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-01 | 2022-06-02 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-07 | 2022-06-08 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-12 | 2022-06-13 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-06 | 2022-06-08 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-10 | 2022-06-12 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-01 | 2022-06-03 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-03 | 2022-06-05 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-06 | 2022-05-08 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-06 | 2022-05-08 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-13 | 2022-06-15 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-13 | 2022-06-15 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-08 | 2022-05-13 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-02 | 2022-06-07 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-08 | 2022-06-13 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-13 | 2022-06-18 | 1

## Plan_D_40
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-04-17 | 2022-04-22 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-24 | 2022-04-29 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-05-06 | 2022-05-07 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-04-23 | 2022-04-24 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-08 | 2022-03-09 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-05-01 | 2022-05-02 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-05-06 | 2022-05-07 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-22 | 2022-04-24 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-05-21 | 2022-05-23 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-11 | 2022-06-13 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-11 | 2022-06-13 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-15 | 2022-03-20 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-05-04 | 2022-05-09 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-18 | 2022-05-23 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-26 | 2022-05-27 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-20 | 2022-03-21 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-05-14 | 2022-05-15 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-20 | 2022-03-21 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-05-14 | 2022-05-15 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-26 | 2022-05-27 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-09 | 2022-05-11 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-09 | 2022-05-11 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-20 | 2022-03-22 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-20 | 2022-03-22 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-17 | 2022-03-19 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-17 | 2022-03-19 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-29 | 2022-05-31 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-25 | 2022-05-27 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-23 | 2022-03-28 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-05-15 | 2022-05-20 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-06-03 | 2022-06-08 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-08 | 2022-06-09 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-23 | 2022-03-24 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-28 | 2022-03-29 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-30 | 2022-05-31 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-25 | 2022-03-26 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-28 | 2022-03-29 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-30 | 2022-05-31 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-08 | 2022-06-09 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-06-05 | 2022-06-07 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-06-02 | 2022-06-04 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-13 | 2022-04-15 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-29 | 2022-03-31 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-26 | 2022-03-28 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-26 | 2022-03-28 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-08 | 2022-06-10 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-14 | 2022-06-16 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-03-31 | 2022-04-05 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-31 | 2022-06-05 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-09 | 2022-06-14 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-16 | 2022-06-17 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-01 | 2022-04-02 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-05 | 2022-04-06 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-06-05 | 2022-06-06 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-03-31 | 2022-04-01 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-07 | 2022-04-08 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-06-05 | 2022-06-06 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-14 | 2022-06-15 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-08 | 2022-06-10 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-05 | 2022-06-07 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-14 | 2022-05-16 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-05 | 2022-04-07 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-02 | 2022-04-04 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-02 | 2022-04-04 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-14 | 2022-06-16 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-20 | 2022-06-22 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-03 | 2022-04-08 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-08 | 2022-04-13 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-10 | 2022-06-15 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-17 | 2022-06-22 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-22 | 2022-06-23 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-10 | 2022-04-11 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-13 | 2022-04-14 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-15 | 2022-06-16 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-10 | 2022-04-11 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-08 | 2022-04-09 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-13 | 2022-04-14 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-17 | 2022-06-18 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-22 | 2022-06-23 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-17 | 2022-06-19 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-17 | 2022-06-19 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-06-01 | 2022-06-03 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-13 | 2022-04-15 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-08 | 2022-04-10 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-08 | 2022-04-10 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-22 | 2022-06-24 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-25 | 2022-06-27 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-11 | 2022-04-16 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-16 | 2022-04-21 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-18 | 2022-06-23 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-23 | 2022-06-28 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-28 | 2022-06-29 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-20 | 2022-04-21 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-04-27 | 2022-04-28 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-24 | 2022-06-25 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-18 | 2022-04-19 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-19 | 2022-04-20 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-04-27 | 2022-04-28 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-24 | 2022-06-25 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-28 | 2022-06-29 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-23 | 2022-06-25 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-26 | 2022-06-28 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-30 | 2022-06-01 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-06 | 2022-05-08 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-25 | 2022-04-27 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-25 | 2022-04-27 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-29 | 2022-07-01 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-29 | 2022-07-01 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-23 | 2022-04-28 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-06 | 2022-05-11 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-25 | 2022-06-30 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-30 | 2022-07-05 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-05 | 2022-07-06 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-03 | 2022-05-04 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-17 | 2022-05-18 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-30 | 2022-07-01 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-09 | 2022-05-10 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-04 | 2022-05-05 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-17 | 2022-05-18 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-30 | 2022-07-01 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-05 | 2022-07-06 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-03 | 2022-07-05 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-02 | 2022-07-04 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-23 | 2022-05-25 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-17 | 2022-05-19 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-12 | 2022-05-14 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-05 | 2022-05-07 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-06 | 2022-07-08 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-06 | 2022-07-08 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-11 | 2022-05-16 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-22 | 2022-05-27 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-01 | 2022-07-06 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-06 | 2022-07-11 | 1

## Plan_D_41
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-25 | 2022-03-30 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-03-30 | 2022-03-31 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-14 | 2022-03-15 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-19 | 2022-03-20 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-19 | 2022-03-20 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-01 | 2022-04-02 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-23 | 2022-03-25 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-24 | 2022-03-26 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-02 | 2022-05-04 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-10 | 2022-04-12 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-04 | 2022-04-09 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-11 | 2022-04-12 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-02 | 2022-04-03 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-27 | 2022-03-28 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-11 | 2022-04-12 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-30 | 2022-05-02 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-22 | 2022-04-24 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-13 | 2022-04-15 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-26 | 2022-03-28 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-19 | 2022-03-21 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-19 | 2022-03-21 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-07 | 2022-06-09 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-09 | 2022-06-11 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-28 | 2022-04-02 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-03 | 2022-04-08 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-14 | 2022-04-19 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-04-19 | 2022-04-20 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-31 | 2022-04-01 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-07 | 2022-04-08 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-14 | 2022-04-15 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-09 | 2022-04-10 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-13 | 2022-04-14 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-02 | 2022-05-03 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-21 | 2022-05-23 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-08 | 2022-04-10 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-04 | 2022-04-06 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-05 | 2022-04-07 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-02 | 2022-04-04 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-01 | 2022-04-03 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-24 | 2022-05-26 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-28 | 2022-06-30 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-10 | 2022-04-15 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-17 | 2022-04-22 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-24 | 2022-04-29 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-04 | 2022-05-09 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-10 | 2022-05-11 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-15 | 2022-04-16 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-23 | 2022-04-24 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-05 | 2022-05-06 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-18 | 2022-04-19 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-16 | 2022-04-17 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-23 | 2022-04-24 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-05 | 2022-05-06 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-12 | 2022-05-13 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-19 | 2022-06-21 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-10 | 2022-06-12 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-22 | 2022-04-24 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-25 | 2022-04-27 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-15 | 2022-04-17 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-16 | 2022-04-18 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-21 | 2022-06-23 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-25 | 2022-06-27 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-21 | 2022-04-26 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-30 | 2022-05-05 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-06 | 2022-05-11 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-28 | 2022-06-02 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-05 | 2022-06-06 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-30 | 2022-05-01 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-11 | 2022-05-12 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-16 | 2022-05-17 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-30 | 2022-05-01 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-05-09 | 2022-05-10 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-14 | 2022-05-15 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-16 | 2022-05-17 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-02 | 2022-06-03 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-13 | 2022-05-15 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-11 | 2022-05-13 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-05 | 2022-05-07 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-05 | 2022-05-07 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-26 | 2022-04-28 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-28 | 2022-04-30 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-25 | 2022-06-27 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-06 | 2022-06-08 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-05-18 | 2022-05-23 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-24 | 2022-05-29 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-04 | 2022-06-09 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-11 | 2022-06-16 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-29 | 2022-06-30 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-24 | 2022-05-25 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-12 | 2022-06-13 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-25 | 2022-06-26 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-24 | 2022-05-25 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-06-07 | 2022-06-08 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-16 | 2022-06-17 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-19 | 2022-06-20 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-27 | 2022-06-28 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-13 | 2022-06-15 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-13 | 2022-06-15 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-01 | 2022-06-03 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-01 | 2022-06-03 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-23 | 2022-05-25 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-26 | 2022-05-28 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-18 | 2022-06-20 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-22 | 2022-06-24 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-06-08 | 2022-06-13 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-17 | 2022-06-22 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-26 | 2022-07-01 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-01 | 2022-07-06 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-06 | 2022-07-07 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-06-14 | 2022-06-15 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-22 | 2022-06-23 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-01 | 2022-07-02 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-06-17 | 2022-06-18 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-06-14 | 2022-06-15 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-24 | 2022-06-25 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-01 | 2022-07-02 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-06 | 2022-07-07 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-04 | 2022-07-06 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-04 | 2022-07-06 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-07-01 | 2022-07-03 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-07-01 | 2022-07-03 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-06-16 | 2022-06-18 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-28 | 2022-06-30 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-07 | 2022-07-09 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-07 | 2022-07-09 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-18 | 2022-06-23 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-25 | 2022-06-30 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-02 | 2022-07-07 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-07 | 2022-07-12 | 2

## Plan_D_42
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-19 | 2022-03-24 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-06 | 2022-04-07 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-08 | 2022-03-09 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-21 | 2022-03-22 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-18 | 2022-03-19 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-03-27 | 2022-03-28 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-05-29 | 2022-05-31 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-06-07 | 2022-06-09 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-26 | 2022-06-28 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-29 | 2022-07-01 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-25 | 2022-03-30 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-03 | 2022-04-08 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-15 | 2022-04-20 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-20 | 2022-04-21 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-31 | 2022-04-01 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-12 | 2022-04-13 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-04-07 | 2022-04-08 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-11 | 2022-04-12 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-26 | 2022-04-27 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-29 | 2022-05-01 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-14 | 2022-05-16 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-30 | 2022-04-01 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-30 | 2022-04-01 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-27 | 2022-03-29 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-27 | 2022-03-29 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-01 | 2022-06-03 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-25 | 2022-05-27 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-09 | 2022-04-14 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-14 | 2022-04-19 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-27 | 2022-05-02 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-09 | 2022-05-10 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-23 | 2022-03-24 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-16 | 2022-04-17 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-30 | 2022-05-01 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-25 | 2022-03-26 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-14 | 2022-04-15 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-20 | 2022-04-21 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-10 | 2022-05-11 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-28 | 2022-05-30 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-06-07 | 2022-06-09 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-14 | 2022-04-16 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-14 | 2022-04-16 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-02 | 2022-04-04 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-02 | 2022-04-04 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-07-01 | 2022-07-03 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-14 | 2022-06-16 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-21 | 2022-04-26 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-06 | 2022-05-11 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-12 | 2022-05-17 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-25 | 2022-05-26 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-02 | 2022-04-03 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-08 | 2022-05-09 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-17 | 2022-05-18 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-02 | 2022-04-03 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-03-31 | 2022-04-01 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-05-13 | 2022-05-14 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-17 | 2022-05-18 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-25 | 2022-05-26 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-12 | 2022-05-14 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-16 | 2022-05-18 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-06 | 2022-05-08 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-26 | 2022-04-28 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-05 | 2022-04-07 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-05 | 2022-04-07 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-18 | 2022-05-20 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-26 | 2022-05-28 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-03 | 2022-04-08 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-14 | 2022-05-19 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-24 | 2022-05-29 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-31 | 2022-06-05 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-08 | 2022-06-09 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-09 | 2022-04-10 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-19 | 2022-05-20 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-31 | 2022-06-01 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-08 | 2022-04-09 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-10 | 2022-04-11 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-19 | 2022-05-20 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-31 | 2022-06-01 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-11 | 2022-06-12 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-23 | 2022-06-25 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-22 | 2022-06-24 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-19 | 2022-05-21 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-22 | 2022-05-24 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-08 | 2022-04-10 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-08 | 2022-04-10 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-28 | 2022-06-30 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-25 | 2022-06-27 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-26 | 2022-05-01 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-27 | 2022-06-01 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-02 | 2022-06-07 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-12 | 2022-06-17 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-01 | 2022-07-02 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-15 | 2022-05-16 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-03 | 2022-06-04 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-24 | 2022-06-25 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-14 | 2022-05-15 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-12 | 2022-05-13 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-02 | 2022-06-03 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-21 | 2022-06-22 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-28 | 2022-06-29 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-10 | 2022-06-12 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-10 | 2022-06-12 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-04 | 2022-06-06 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-03 | 2022-06-05 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-07 | 2022-05-09 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-01 | 2022-05-03 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-17 | 2022-06-19 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-05 | 2022-07-07 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-18 | 2022-05-23 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-07 | 2022-06-12 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-25 | 2022-06-30 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-02 | 2022-07-07 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-07 | 2022-07-08 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-06-13 | 2022-06-14 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-16 | 2022-06-17 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-30 | 2022-07-01 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-06-13 | 2022-06-14 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-06-06 | 2022-06-07 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-15 | 2022-06-16 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-02 | 2022-07-03 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-07 | 2022-07-08 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-04 | 2022-07-06 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-02 | 2022-07-04 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-17 | 2022-06-19 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-20 | 2022-06-22 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-23 | 2022-05-25 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-14 | 2022-06-16 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-08 | 2022-07-10 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-07 | 2022-07-09 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-14 | 2022-06-19 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-19 | 2022-06-24 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-03 | 2022-07-08 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-08 | 2022-07-13 | 1

## Plan_D_43
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-13 | 2022-04-18 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-18 | 2022-04-19 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-19 | 2022-03-20 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-08 | 2022-03-09 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-19 | 2022-03-20 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-19 | 2022-04-20 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-05-18 | 2022-05-20 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-05-22 | 2022-05-24 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-25 | 2022-05-27 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-25 | 2022-05-27 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-19 | 2022-03-24 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-25 | 2022-03-30 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-20 | 2022-04-25 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-05 | 2022-05-06 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-29 | 2022-03-30 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-02 | 2022-04-03 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-16 | 2022-03-17 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-26 | 2022-03-27 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-30 | 2022-03-31 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-05 | 2022-05-06 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-17 | 2022-05-19 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-28 | 2022-05-30 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-24 | 2022-03-26 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-21 | 2022-03-23 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-21 | 2022-03-23 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-28 | 2022-06-30 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-21 | 2022-06-23 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-01 | 2022-04-06 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-08 | 2022-04-13 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-09 | 2022-05-14 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-22 | 2022-05-23 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-23 | 2022-03-24 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-12 | 2022-04-13 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-25 | 2022-04-26 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-08 | 2022-04-09 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-14 | 2022-04-15 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-17 | 2022-05-18 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-28 | 2022-05-30 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-20 | 2022-05-22 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-06 | 2022-04-08 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-06 | 2022-04-08 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-31 | 2022-04-02 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-31 | 2022-04-02 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-06 | 2022-06-08 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-07-01 | 2022-07-03 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-05-07 | 2022-05-12 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-19 | 2022-05-24 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-25 | 2022-05-30 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-03 | 2022-06-04 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-05 | 2022-04-06 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-22 | 2022-05-23 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-24 | 2022-05-25 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-05 | 2022-04-06 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-01 | 2022-04-02 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-05-19 | 2022-05-20 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-26 | 2022-05-27 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-03 | 2022-06-04 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-03 | 2022-06-05 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-03 | 2022-06-05 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-12 | 2022-05-14 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-05-12 | 2022-05-14 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-03 | 2022-04-05 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-03 | 2022-04-05 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-07-04 | 2022-07-06 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-07 | 2022-06-09 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-06 | 2022-04-11 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-26 | 2022-05-31 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-01 | 2022-06-06 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-07 | 2022-06-12 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-12 | 2022-06-13 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-17 | 2022-04-18 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-31 | 2022-06-01 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-06 | 2022-06-07 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-13 | 2022-04-14 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-11 | 2022-04-12 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-31 | 2022-06-01 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-06 | 2022-06-07 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-12 | 2022-06-13 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-16 | 2022-06-18 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-15 | 2022-06-17 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-31 | 2022-06-02 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-31 | 2022-06-02 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-11 | 2022-04-13 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-11 | 2022-04-13 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-30 | 2022-07-02 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-18 | 2022-06-20 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-19 | 2022-04-24 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-06-01 | 2022-06-06 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-07 | 2022-06-12 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-13 | 2022-06-18 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-01 | 2022-07-02 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-29 | 2022-04-30 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-16 | 2022-06-17 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-26 | 2022-06-27 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-27 | 2022-04-28 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-24 | 2022-04-25 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-16 | 2022-06-17 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-18 | 2022-06-19 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-01 | 2022-07-02 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-13 | 2022-06-15 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-19 | 2022-06-21 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-10 | 2022-06-12 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-10 | 2022-06-12 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-24 | 2022-04-26 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-24 | 2022-04-26 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-22 | 2022-06-24 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-27 | 2022-06-29 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-30 | 2022-05-05 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-18 | 2022-06-23 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-28 | 2022-07-03 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-03 | 2022-07-08 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-08 | 2022-07-09 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-28 | 2022-05-29 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-24 | 2022-06-25 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-03 | 2022-07-04 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-07 | 2022-05-08 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-07 | 2022-05-08 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-26 | 2022-06-27 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-03 | 2022-07-04 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-08 | 2022-07-09 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-06 | 2022-07-08 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-03 | 2022-07-05 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-24 | 2022-06-26 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-25 | 2022-06-27 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-05 | 2022-05-07 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-05 | 2022-05-07 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-08 | 2022-07-10 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-09 | 2022-07-11 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-22 | 2022-06-27 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-27 | 2022-07-02 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-04 | 2022-07-09 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-09 | 2022-07-14 | 2

## Plan_D_44
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-08 | 2022-03-13 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-30 | 2022-04-04 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-04 | 2022-04-09 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-14 | 2022-04-15 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-04-10 | 2022-04-11 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-08 | 2022-03-09 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-04-10 | 2022-04-11 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-14 | 2022-04-15 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-06-18 | 2022-06-20 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-05-26 | 2022-05-28 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-13 | 2022-03-15 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-13 | 2022-03-15 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-10 | 2022-03-12 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-10 | 2022-03-12 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-07-10 | 2022-07-12 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-21 | 2022-06-23 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-15 | 2022-03-20 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-12 | 2022-04-17 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-18 | 2022-04-23 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-23 | 2022-04-24 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-20 | 2022-03-21 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-17 | 2022-04-18 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-20 | 2022-03-21 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-17 | 2022-04-18 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-24 | 2022-04-25 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-15 | 2022-05-17 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-15 | 2022-05-17 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-20 | 2022-03-22 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-20 | 2022-03-22 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-17 | 2022-03-19 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-17 | 2022-03-19 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-18 | 2022-05-20 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-18 | 2022-05-20 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-23 | 2022-03-28 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-20 | 2022-04-25 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-26 | 2022-05-01 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-02 | 2022-05-03 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-24 | 2022-03-25 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-29 | 2022-03-30 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-25 | 2022-04-26 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-23 | 2022-03-24 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-29 | 2022-03-30 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-28 | 2022-04-29 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-06 | 2022-05-07 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-09 | 2022-05-11 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-09 | 2022-05-11 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-03-28 | 2022-03-30 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-28 | 2022-03-30 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-25 | 2022-03-27 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-25 | 2022-03-27 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-12 | 2022-05-14 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-29 | 2022-05-31 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-05 | 2022-04-10 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-02 | 2022-05-07 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-11 | 2022-05-16 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-16 | 2022-05-17 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-03-31 | 2022-04-01 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-28 | 2022-04-29 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-09 | 2022-05-10 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-03 | 2022-04-04 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-03-31 | 2022-04-01 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-30 | 2022-05-01 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-12 | 2022-05-13 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-16 | 2022-05-17 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-21 | 2022-05-23 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-12 | 2022-05-14 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-10 | 2022-04-12 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-10 | 2022-04-12 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-03 | 2022-04-05 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-03 | 2022-04-05 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-28 | 2022-05-30 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-24 | 2022-05-26 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-14 | 2022-04-19 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-02 | 2022-05-07 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-28 | 2022-06-02 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-03 | 2022-06-08 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-10 | 2022-06-11 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-19 | 2022-04-20 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-12 | 2022-05-13 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-02 | 2022-06-03 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-19 | 2022-04-20 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-22 | 2022-04-23 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-07 | 2022-05-08 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-02 | 2022-06-03 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-12 | 2022-06-13 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-12 | 2022-06-14 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-11 | 2022-06-13 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-06-09 | 2022-06-11 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-06-08 | 2022-06-10 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-06-06 | 2022-06-08 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-06-01 | 2022-06-03 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-06 | 2022-07-08 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-03 | 2022-07-05 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-26 | 2022-05-01 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-19 | 2022-05-24 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-10 | 2022-06-15 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-17 | 2022-06-22 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-23 | 2022-06-24 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-02 | 2022-05-03 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-06 | 2022-06-07 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-15 | 2022-06-16 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-04 | 2022-05-05 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-23 | 2022-05-24 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-10 | 2022-06-11 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-15 | 2022-06-16 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-23 | 2022-06-24 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-15 | 2022-06-17 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-21 | 2022-06-23 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-05 | 2022-06-07 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-31 | 2022-06-02 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-05 | 2022-05-07 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-21 | 2022-05-23 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-28 | 2022-06-30 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-25 | 2022-06-27 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-06-01 | 2022-06-06 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-11 | 2022-06-16 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-16 | 2022-06-21 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-24 | 2022-06-29 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-07 | 2022-07-08 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-06-19 | 2022-06-20 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-28 | 2022-06-29 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-04 | 2022-07-05 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-06-19 | 2022-06-20 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-06-17 | 2022-06-18 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-28 | 2022-06-29 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-04 | 2022-07-05 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-07 | 2022-07-08 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-01 | 2022-07-03 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-04 | 2022-07-06 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-28 | 2022-06-30 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-25 | 2022-06-27 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-06-18 | 2022-06-20 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-14 | 2022-06-16 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-09 | 2022-07-11 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-07 | 2022-07-09 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-25 | 2022-06-30 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-30 | 2022-07-05 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-05 | 2022-07-10 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-10 | 2022-07-15 | 1

## Plan_D_45
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-04-03 | 2022-04-08 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-05-09 | 2022-05-14 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-05-14 | 2022-05-15 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-08 | 2022-03-09 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-04-08 | 2022-04-09 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-04-08 | 2022-04-09 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-05-16 | 2022-05-17 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-27 | 2022-04-29 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-30 | 2022-05-02 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-14 | 2022-03-16 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-17 | 2022-03-19 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-10 | 2022-03-12 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-19 | 2022-06-21 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-07-05 | 2022-07-07 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-09 | 2022-04-14 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-17 | 2022-05-22 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-22 | 2022-05-23 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-14 | 2022-04-15 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-14 | 2022-04-15 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-22 | 2022-05-23 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-06-25 | 2022-06-27 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-06-25 | 2022-06-27 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-02 | 2022-04-04 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-04-05 | 2022-04-07 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-24 | 2022-03-26 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-27 | 2022-03-29 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-28 | 2022-06-30 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-28 | 2022-06-30 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-23 | 2022-03-28 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-15 | 2022-04-20 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-23 | 2022-05-28 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-28 | 2022-05-29 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-30 | 2022-03-31 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-20 | 2022-04-21 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-23 | 2022-03-24 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-25 | 2022-03-26 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-28 | 2022-03-29 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-21 | 2022-04-22 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-28 | 2022-05-29 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-06-14 | 2022-06-16 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-06-08 | 2022-06-10 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-06-05 | 2022-06-07 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-06-02 | 2022-06-04 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-05-30 | 2022-06-01 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-05-27 | 2022-05-29 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-07-02 | 2022-07-04 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-17 | 2022-06-19 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-01 | 2022-04-06 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-22 | 2022-04-27 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-29 | 2022-06-03 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-03 | 2022-06-04 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-06 | 2022-04-07 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-23 | 2022-04-24 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-03 | 2022-05-04 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-04 | 2022-04-05 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-27 | 2022-04-28 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-05 | 2022-05-06 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-03 | 2022-06-04 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-24 | 2022-05-26 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-21 | 2022-05-23 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-18 | 2022-05-20 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-05-15 | 2022-05-17 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-05-12 | 2022-05-14 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-05-09 | 2022-05-11 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-16 | 2022-06-18 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-06 | 2022-06-08 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-08 | 2022-04-13 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-28 | 2022-05-03 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-06 | 2022-05-11 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-04 | 2022-06-09 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-16 | 2022-06-17 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-16 | 2022-04-17 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-13 | 2022-05-14 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-12 | 2022-06-13 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-18 | 2022-04-19 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-17 | 2022-04-18 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-10 | 2022-05-11 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-12 | 2022-06-13 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-14 | 2022-06-15 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-28 | 2022-05-30 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-25 | 2022-05-27 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-06 | 2022-05-08 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-03 | 2022-05-05 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-30 | 2022-05-02 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-27 | 2022-04-29 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-09 | 2022-06-11 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-12 | 2022-06-14 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-19 | 2022-04-24 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-17 | 2022-05-22 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-13 | 2022-06-18 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-18 | 2022-06-23 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-02 | 2022-07-03 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-25 | 2022-04-26 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-25 | 2022-05-26 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-28 | 2022-06-29 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-28 | 2022-04-29 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-26 | 2022-04-27 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-25 | 2022-05-26 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-28 | 2022-06-29 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-30 | 2022-07-01 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-22 | 2022-06-24 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-22 | 2022-06-24 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-11 | 2022-06-13 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-22 | 2022-05-24 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-04-24 | 2022-04-26 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-19 | 2022-05-21 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-02 | 2022-07-04 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-08 | 2022-07-10 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-29 | 2022-05-04 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-26 | 2022-05-31 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-29 | 2022-07-04 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-05 | 2022-07-10 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-10 | 2022-07-11 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-06-22 | 2022-06-23 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-26 | 2022-06-27 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-05 | 2022-07-06 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-06-20 | 2022-06-21 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-06-18 | 2022-06-19 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-24 | 2022-06-25 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-05 | 2022-07-06 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-10 | 2022-07-11 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-05 | 2022-07-07 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-08 | 2022-07-10 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-31 | 2022-06-02 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-03 | 2022-06-05 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-16 | 2022-05-18 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-13 | 2022-05-15 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-11 | 2022-07-13 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-11 | 2022-07-13 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-23 | 2022-06-28 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-30 | 2022-07-05 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-06 | 2022-07-11 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-11 | 2022-07-16 | 2

## Plan_D_46
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-15 | 2022-04-20 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-21 | 2022-04-22 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-08 | 2022-03-09 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-21 | 2022-04-22 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-06-10 | 2022-06-12 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-06-03 | 2022-06-05 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-19 | 2022-06-21 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-12 | 2022-06-14 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-26 | 2022-05-01 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-01 | 2022-05-02 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-22 | 2022-03-23 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-27 | 2022-03-28 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-16 | 2022-03-17 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-29 | 2022-03-30 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-01 | 2022-05-02 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-12 | 2022-05-14 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-12 | 2022-05-14 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-05-06 | 2022-05-08 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-22 | 2022-03-24 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-19 | 2022-03-21 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-19 | 2022-03-21 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-16 | 2022-05-18 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-22 | 2022-05-24 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-03 | 2022-05-08 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-21 | 2022-05-22 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-26 | 2022-03-27 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-30 | 2022-03-31 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-05 | 2022-04-06 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-05 | 2022-04-06 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-11 | 2022-05-12 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-27 | 2022-05-29 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-23 | 2022-05-25 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-05-02 | 2022-05-04 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-05-02 | 2022-05-04 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-01 | 2022-04-03 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-01 | 2022-04-03 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-31 | 2022-06-02 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-01 | 2022-06-03 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-03 | 2022-04-08 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-08 | 2022-04-13 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-25 | 2022-05-30 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-01 | 2022-06-02 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-07 | 2022-04-08 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-10 | 2022-04-11 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-19 | 2022-04-20 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-02 | 2022-04-03 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-03 | 2022-04-04 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-15 | 2022-04-16 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-24 | 2022-04-25 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-01 | 2022-06-02 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-26 | 2022-06-28 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-27 | 2022-06-29 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-09 | 2022-04-11 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-09 | 2022-04-11 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-04 | 2022-04-06 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-04 | 2022-04-06 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-30 | 2022-07-02 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-07-02 | 2022-07-04 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-09 | 2022-04-14 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-23 | 2022-04-28 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-30 | 2022-05-05 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-06 | 2022-06-11 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-26 | 2022-06-27 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-17 | 2022-04-18 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-08 | 2022-05-09 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-14 | 2022-05-15 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-14 | 2022-04-15 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-17 | 2022-04-18 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-08 | 2022-05-09 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-11 | 2022-05-12 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-24 | 2022-06-25 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-27 | 2022-05-29 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-23 | 2022-06-25 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-19 | 2022-05-21 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-19 | 2022-05-21 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-14 | 2022-04-16 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-14 | 2022-04-16 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-29 | 2022-07-01 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-06 | 2022-07-08 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-18 | 2022-04-23 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-10 | 2022-05-15 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-15 | 2022-05-20 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-29 | 2022-07-04 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-04 | 2022-07-05 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-28 | 2022-04-29 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-15 | 2022-05-16 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-20 | 2022-05-21 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-29 | 2022-04-30 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-24 | 2022-04-25 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-18 | 2022-05-19 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-30 | 2022-05-31 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-04 | 2022-07-05 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-24 | 2022-06-26 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-20 | 2022-06-22 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-15 | 2022-05-17 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-16 | 2022-06-18 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-07 | 2022-05-09 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-23 | 2022-04-25 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-05 | 2022-07-07 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-09 | 2022-07-11 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-18 | 2022-05-23 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-24 | 2022-05-29 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-01 | 2022-06-06 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-05 | 2022-07-10 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-11 | 2022-07-12 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-06-20 | 2022-06-21 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-28 | 2022-06-29 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-02 | 2022-07-03 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-28 | 2022-05-29 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-28 | 2022-05-29 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-28 | 2022-06-29 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-06 | 2022-07-07 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-11 | 2022-07-12 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-09 | 2022-07-11 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-03 | 2022-07-05 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-09 | 2022-06-11 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-13 | 2022-06-15 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-06-06 | 2022-06-08 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-06 | 2022-06-08 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-12 | 2022-07-14 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-12 | 2022-07-14 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-23 | 2022-06-28 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-07-01 | 2022-07-06 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-07 | 2022-07-12 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-12 | 2022-07-17 | 2

## Plan_D_47
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-04-12 | 2022-04-17 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-05-11 | 2022-05-16 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-05-18 | 2022-05-19 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-04-17 | 2022-04-18 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-08 | 2022-03-09 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-04-17 | 2022-04-18 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-05-18 | 2022-05-19 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-06-03 | 2022-06-05 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-06-03 | 2022-06-05 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-13 | 2022-03-15 | 4
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-13 | 2022-03-15 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-10 | 2022-03-12 | 4
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-10 | 2022-03-12 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-10 | 2022-06-12 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-10 | 2022-06-12 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-15 | 2022-03-20 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-18 | 2022-04-23 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-19 | 2022-05-24 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-27 | 2022-05-28 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-23 | 2022-04-24 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-16 | 2022-03-17 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-23 | 2022-04-24 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-24 | 2022-05-25 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-15 | 2022-05-17 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-12 | 2022-05-14 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-20 | 2022-04-22 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-21 | 2022-03-23 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-18 | 2022-03-20 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-26 | 2022-05-28 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-26 | 2022-05-28 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-23 | 2022-03-28 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-27 | 2022-05-02 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-29 | 2022-06-03 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-03 | 2022-06-04 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-28 | 2022-03-29 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-05 | 2022-05-06 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-26 | 2022-03-27 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-28 | 2022-03-29 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-14 | 2022-05-15 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-04 | 2022-06-05 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-29 | 2022-05-31 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-08 | 2022-05-10 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-07 | 2022-04-09 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-07 | 2022-04-09 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-01 | 2022-04-03 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-01 | 2022-04-03 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-06 | 2022-06-08 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-30 | 2022-07-02 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-27 | 2022-04-01 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-29 | 2022-05-04 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-29 | 2022-06-03 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-05 | 2022-06-10 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-12 | 2022-06-13 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-03 | 2022-04-04 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-07 | 2022-05-08 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-06-08 | 2022-06-09 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-01 | 2022-04-02 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-01 | 2022-04-02 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-05-10 | 2022-05-11 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-06-08 | 2022-06-09 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-14 | 2022-06-15 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-14 | 2022-06-16 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-06 | 2022-06-08 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-18 | 2022-05-20 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-05-18 | 2022-05-20 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-04 | 2022-04-06 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-04 | 2022-04-06 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-21 | 2022-06-23 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-27 | 2022-06-29 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-05 | 2022-04-10 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-13 | 2022-05-18 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-11 | 2022-06-16 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-16 | 2022-06-21 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-24 | 2022-06-25 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-14 | 2022-04-15 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-24 | 2022-05-25 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-18 | 2022-06-19 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-12 | 2022-04-13 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-14 | 2022-04-15 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-26 | 2022-05-27 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-18 | 2022-06-19 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-22 | 2022-06-23 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-21 | 2022-06-23 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-17 | 2022-06-19 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-23 | 2022-05-25 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-23 | 2022-05-25 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-10 | 2022-04-12 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-10 | 2022-04-12 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-28 | 2022-06-30 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-01 | 2022-07-03 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-16 | 2022-04-21 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-06-05 | 2022-06-10 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-19 | 2022-06-24 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-26 | 2022-07-01 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-03 | 2022-07-04 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-03 | 2022-05-04 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-14 | 2022-06-15 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-26 | 2022-06-27 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-03 | 2022-05-04 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-29 | 2022-04-30 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-11 | 2022-06-12 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-26 | 2022-06-27 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-03 | 2022-07-04 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-24 | 2022-06-26 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-25 | 2022-06-27 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-14 | 2022-06-16 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-18 | 2022-06-20 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-14 | 2022-05-16 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-21 | 2022-04-23 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-03 | 2022-07-05 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-04 | 2022-07-06 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-04 | 2022-05-09 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-25 | 2022-06-30 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-07-01 | 2022-07-06 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-07 | 2022-07-12 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-12 | 2022-07-13 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-11 | 2022-05-12 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-07-01 | 2022-07-02 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-07 | 2022-07-08 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-16 | 2022-05-17 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-12 | 2022-05-13 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-07-01 | 2022-07-02 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-07 | 2022-07-08 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-12 | 2022-07-13 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-10 | 2022-07-12 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-10 | 2022-07-12 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-07-06 | 2022-07-08 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-07-07 | 2022-07-09 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-30 | 2022-06-01 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-09 | 2022-05-11 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-13 | 2022-07-15 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-13 | 2022-07-15 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-23 | 2022-05-28 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-07-02 | 2022-07-07 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-08 | 2022-07-13 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-13 | 2022-07-18 | 2

## Plan_D_48
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-18 | 2022-04-23 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-25 | 2022-04-26 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-18 | 2022-03-19 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-21 | 2022-03-22 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-26 | 2022-04-27 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-06-07 | 2022-06-09 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-06-08 | 2022-06-10 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-13 | 2022-06-15 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-10 | 2022-06-12 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-19 | 2022-03-24 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-24 | 2022-03-29 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-12 | 2022-05-17 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-06-05 | 2022-06-06 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-27 | 2022-03-28 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-04 | 2022-04-05 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-27 | 2022-03-28 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-04 | 2022-04-05 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-06-07 | 2022-06-08 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-06-14 | 2022-06-16 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-21 | 2022-05-23 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-24 | 2022-03-26 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-21 | 2022-03-23 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-21 | 2022-03-23 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-20 | 2022-06-22 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-17 | 2022-06-19 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-30 | 2022-04-04 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-05 | 2022-04-10 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-06-08 | 2022-06-13 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-19 | 2022-06-20 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-24 | 2022-03-25 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-09 | 2022-04-10 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-13 | 2022-04-14 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-23 | 2022-03-24 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-25 | 2022-03-26 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-06 | 2022-04-07 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-15 | 2022-04-16 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-19 | 2022-06-20 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-06-03 | 2022-06-05 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-24 | 2022-05-26 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-04 | 2022-04-06 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-04 | 2022-04-06 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-27 | 2022-03-29 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-29 | 2022-03-31 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-20 | 2022-06-22 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-17 | 2022-06-19 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-11 | 2022-04-16 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-24 | 2022-04-29 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-20 | 2022-06-25 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-25 | 2022-06-26 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-02 | 2022-04-03 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-24 | 2022-04-25 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-30 | 2022-05-01 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-01 | 2022-04-02 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-03-31 | 2022-04-01 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-22 | 2022-04-23 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-30 | 2022-05-01 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-25 | 2022-06-26 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-13 | 2022-05-15 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-31 | 2022-06-02 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-18 | 2022-04-20 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-18 | 2022-04-20 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-01 | 2022-04-03 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-01 | 2022-04-03 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-26 | 2022-06-28 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-27 | 2022-06-29 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-03 | 2022-04-08 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-25 | 2022-04-30 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-14 | 2022-05-19 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-26 | 2022-07-01 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-07-01 | 2022-07-02 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-11 | 2022-04-12 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-20 | 2022-05-21 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-11 | 2022-06-12 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-11 | 2022-04-12 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-09 | 2022-04-10 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-18 | 2022-05-19 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-11 | 2022-06-12 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-01 | 2022-07-02 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-27 | 2022-05-29 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-22 | 2022-05-24 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-17 | 2022-05-19 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-30 | 2022-05-02 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-15 | 2022-04-17 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-15 | 2022-04-17 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-11 | 2022-07-13 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-03 | 2022-07-05 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-12 | 2022-04-17 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-21 | 2022-05-26 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-12 | 2022-06-17 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-02 | 2022-07-07 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-07 | 2022-07-08 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-17 | 2022-04-18 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-16 | 2022-06-17 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-22 | 2022-06-23 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-17 | 2022-04-18 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-18 | 2022-05-19 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-16 | 2022-06-17 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-22 | 2022-06-23 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-07 | 2022-07-08 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-30 | 2022-07-02 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-30 | 2022-07-02 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-11 | 2022-06-13 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-05 | 2022-06-07 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-14 | 2022-05-16 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-10 | 2022-05-12 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-07 | 2022-07-09 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-08 | 2022-07-10 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-20 | 2022-05-25 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-18 | 2022-06-23 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-26 | 2022-07-01 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-08 | 2022-07-13 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-13 | 2022-07-14 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-25 | 2022-05-26 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-27 | 2022-06-28 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-03 | 2022-07-04 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-27 | 2022-05-28 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-27 | 2022-05-28 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-27 | 2022-06-28 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-05 | 2022-07-06 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-13 | 2022-07-14 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-10 | 2022-07-12 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-04 | 2022-07-06 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-23 | 2022-06-25 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-23 | 2022-06-25 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-27 | 2022-05-29 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-31 | 2022-06-02 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-14 | 2022-07-16 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-14 | 2022-07-16 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-05 | 2022-06-10 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-07-02 | 2022-07-07 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-09 | 2022-07-14 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-14 | 2022-07-19 | 2

## Plan_D_49
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-21 | 2022-03-26 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-05-03 | 2022-05-08 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-05-12 | 2022-05-13 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-04-04 | 2022-04-05 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-08 | 2022-03-09 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-29 | 2022-03-30 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-05-09 | 2022-05-10 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-03 | 2022-04-05 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-28 | 2022-04-30 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-23 | 2022-05-25 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-20 | 2022-06-22 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-15 | 2022-03-20 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-08 | 2022-04-13 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-15 | 2022-05-20 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-21 | 2022-05-22 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-20 | 2022-03-21 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-13 | 2022-04-14 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-23 | 2022-03-24 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-13 | 2022-04-14 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-21 | 2022-05-22 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-17 | 2022-04-19 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-08 | 2022-05-10 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-23 | 2022-03-25 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-23 | 2022-03-25 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-20 | 2022-03-22 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-20 | 2022-03-22 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-13 | 2022-06-15 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-26 | 2022-05-28 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-22 | 2022-04-27 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-23 | 2022-05-28 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-03 | 2022-06-04 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-26 | 2022-03-27 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-31 | 2022-04-01 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-30 | 2022-05-01 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-24 | 2022-03-25 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-30 | 2022-03-31 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-28 | 2022-04-29 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-07 | 2022-06-08 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-06-07 | 2022-06-09 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-16 | 2022-05-18 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-03-30 | 2022-04-01 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-30 | 2022-04-01 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-27 | 2022-03-29 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-27 | 2022-03-29 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-23 | 2022-06-25 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-25 | 2022-06-27 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-27 | 2022-04-01 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-01 | 2022-04-06 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-02 | 2022-05-07 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-11 | 2022-06-16 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-20 | 2022-06-21 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-01 | 2022-04-02 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-07 | 2022-04-08 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-17 | 2022-05-18 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-03 | 2022-04-04 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-07 | 2022-04-08 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-25 | 2022-05-26 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-20 | 2022-06-21 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-10 | 2022-06-12 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-07 | 2022-06-09 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-08 | 2022-04-10 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-08 | 2022-04-10 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-05 | 2022-04-07 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-02 | 2022-04-04 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-28 | 2022-06-30 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-29 | 2022-07-01 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-04 | 2022-04-09 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-10 | 2022-04-15 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-03 | 2022-06-08 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-21 | 2022-06-26 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-26 | 2022-06-27 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-11 | 2022-04-12 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-15 | 2022-04-16 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-23 | 2022-06-24 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-09 | 2022-04-10 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-09 | 2022-04-10 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-15 | 2022-04-16 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-23 | 2022-06-24 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-29 | 2022-06-30 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-17 | 2022-06-19 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-10 | 2022-06-12 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-20 | 2022-04-22 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-20 | 2022-05-22 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-13 | 2022-04-15 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-13 | 2022-04-15 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-05 | 2022-07-07 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-02 | 2022-07-04 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-15 | 2022-04-20 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-10 | 2022-05-15 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-26 | 2022-07-01 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-02 | 2022-07-07 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-07 | 2022-07-08 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-25 | 2022-04-26 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-15 | 2022-05-16 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-02 | 2022-07-03 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-25 | 2022-04-26 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-02 | 2022-05-03 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-19 | 2022-05-20 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-02 | 2022-07-03 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-07 | 2022-07-08 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-07-02 | 2022-07-04 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-05 | 2022-07-07 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-30 | 2022-06-01 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-31 | 2022-06-02 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-27 | 2022-05-29 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-23 | 2022-05-25 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-12 | 2022-07-14 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-09 | 2022-07-11 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-09 | 2022-05-14 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-20 | 2022-05-25 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-07-04 | 2022-07-09 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-09 | 2022-07-14 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-14 | 2022-07-15 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-14 | 2022-05-15 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-25 | 2022-05-26 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-09 | 2022-07-10 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-23 | 2022-05-24 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-23 | 2022-05-24 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-26 | 2022-06-27 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-09 | 2022-07-10 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-14 | 2022-07-15 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-09 | 2022-07-11 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-12 | 2022-07-14 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-03 | 2022-06-05 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-03 | 2022-06-05 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-14 | 2022-05-16 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-20 | 2022-05-22 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-15 | 2022-07-17 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-15 | 2022-07-17 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-29 | 2022-06-03 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-27 | 2022-07-02 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-10 | 2022-07-15 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-15 | 2022-07-20 | 1

## Plan_D_5
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-17 | 2022-04-22 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-05-07 | 2022-05-08 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-19 | 2022-03-20 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-19 | 2022-03-20 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-05-07 | 2022-05-08 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-29 | 2022-03-31 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-14 | 2022-04-16 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-04-25 | 2022-04-27 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-22 | 2022-04-24 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-08 | 2022-05-13 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-13 | 2022-05-14 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-22 | 2022-03-23 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-29 | 2022-03-30 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-22 | 2022-03-23 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-29 | 2022-03-30 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-13 | 2022-05-14 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-08 | 2022-04-10 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-09 | 2022-04-11 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-06 | 2022-04-08 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-22 | 2022-03-24 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-19 | 2022-03-21 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-19 | 2022-03-21 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-21 | 2022-05-23 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-18 | 2022-05-20 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-25 | 2022-03-30 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-03-31 | 2022-04-05 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-14 | 2022-05-19 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-19 | 2022-05-20 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-24 | 2022-03-25 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-31 | 2022-04-01 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-05 | 2022-04-06 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-08 | 2022-04-09 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-19 | 2022-05-20 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-16 | 2022-04-18 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-07 | 2022-05-09 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-02 | 2022-04-04 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-31 | 2022-04-02 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-27 | 2022-03-29 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-26 | 2022-03-28 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-27 | 2022-05-29 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-05-21 | 2022-05-23 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-29 | 2022-04-03 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-06 | 2022-04-11 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-12 | 2022-04-17 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-20 | 2022-05-25 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-25 | 2022-05-26 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-05 | 2022-04-06 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-11 | 2022-04-12 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-21 | 2022-04-22 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-03 | 2022-04-04 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-03 | 2022-04-04 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-11 | 2022-04-12 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-21 | 2022-04-22 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-25 | 2022-05-26 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-18 | 2022-05-20 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-28 | 2022-04-30 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-19 | 2022-04-21 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-11 | 2022-04-13 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-05 | 2022-04-07 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-03 | 2022-04-05 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-25 | 2022-05-27 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-28 | 2022-05-30 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-06 | 2022-04-11 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-18 | 2022-04-23 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-24 | 2022-04-29 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-26 | 2022-05-31 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-31 | 2022-06-01 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-19 | 2022-04-20 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-23 | 2022-04-24 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-22 | 2022-05-23 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-16 | 2022-04-17 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-13 | 2022-04-14 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-23 | 2022-04-24 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-22 | 2022-05-23 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-31 | 2022-06-01 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-15 | 2022-05-17 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-04-30 | 2022-05-02 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-23 | 2022-04-25 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-26 | 2022-04-28 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-20 | 2022-04-22 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-12 | 2022-04-14 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-03 | 2022-06-05 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-05-31 | 2022-06-02 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-24 | 2022-04-29 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-04-30 | 2022-05-05 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-27 | 2022-06-01 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-01 | 2022-06-06 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-06-06 | 2022-06-07 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-29 | 2022-04-30 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-05 | 2022-05-06 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-02 | 2022-06-03 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-01 | 2022-05-02 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-30 | 2022-05-01 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-05 | 2022-05-06 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-02 | 2022-06-03 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-06-06 | 2022-06-07 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-01 | 2022-06-03 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-05 | 2022-06-07 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-05 | 2022-05-07 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-12 | 2022-05-14 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-03 | 2022-05-05 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-01 | 2022-05-03 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-06-08 | 2022-06-10 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-06-11 | 2022-06-13 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-02 | 2022-05-07 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-08 | 2022-05-13 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-03 | 2022-06-08 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-08 | 2022-06-13 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-13 | 2022-06-14 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-09 | 2022-05-10 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-15 | 2022-05-16 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-08 | 2022-06-09 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-11 | 2022-05-12 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-11 | 2022-05-12 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-15 | 2022-05-16 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-08 | 2022-06-09 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-13 | 2022-06-14 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-11 | 2022-06-13 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-08 | 2022-06-10 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-13 | 2022-05-15 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-24 | 2022-05-26 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-10 | 2022-05-12 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-09 | 2022-05-11 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-14 | 2022-06-16 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-14 | 2022-06-16 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-14 | 2022-05-19 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-20 | 2022-05-25 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-09 | 2022-06-14 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-14 | 2022-06-19 | 2

## Plan_D_50
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-19 | 2022-03-24 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-24 | 2022-03-29 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-12 | 2022-04-13 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-27 | 2022-03-28 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-04-11 | 2022-04-12 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-23 | 2022-04-24 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-30 | 2022-04-01 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-30 | 2022-04-01 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-12 | 2022-05-14 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-12 | 2022-05-14 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-04-01 | 2022-04-06 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-28 | 2022-05-03 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-18 | 2022-05-23 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-29 | 2022-05-30 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-04-07 | 2022-04-08 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-05-22 | 2022-05-23 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-16 | 2022-03-17 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-04-15 | 2022-04-16 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-05-22 | 2022-05-23 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-29 | 2022-05-30 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-03 | 2022-05-05 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-19 | 2022-05-21 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-23 | 2022-04-25 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-04-06 | 2022-04-08 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-24 | 2022-03-26 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-04-03 | 2022-04-05 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-13 | 2022-06-15 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-31 | 2022-06-02 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-17 | 2022-04-22 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-05-25 | 2022-05-30 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-31 | 2022-06-05 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-12 | 2022-06-13 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-26 | 2022-04-27 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-06-01 | 2022-06-02 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-23 | 2022-03-24 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-23 | 2022-04-24 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-06-03 | 2022-06-04 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-09 | 2022-06-10 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-06-04 | 2022-06-06 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-30 | 2022-06-01 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-05-25 | 2022-05-27 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-22 | 2022-04-24 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-27 | 2022-03-29 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-27 | 2022-03-29 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-09 | 2022-06-11 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-09 | 2022-06-11 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-05-06 | 2022-05-11 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-06-08 | 2022-06-13 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-14 | 2022-06-19 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-22 | 2022-06-23 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-02 | 2022-04-03 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-11 | 2022-05-12 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-06-15 | 2022-06-16 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-03-31 | 2022-04-01 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-05-11 | 2022-05-12 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-06-14 | 2022-06-15 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-22 | 2022-06-23 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-22 | 2022-06-24 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-23 | 2022-06-25 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-15 | 2022-05-17 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-05-15 | 2022-05-17 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-06 | 2022-04-08 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-02 | 2022-04-04 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-26 | 2022-06-28 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-26 | 2022-06-28 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-03 | 2022-04-08 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-20 | 2022-05-25 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-17 | 2022-06-22 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-28 | 2022-07-03 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-07-03 | 2022-07-04 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-08 | 2022-04-09 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-27 | 2022-05-28 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-24 | 2022-06-25 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-09 | 2022-04-10 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-10 | 2022-04-11 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-27 | 2022-05-28 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-24 | 2022-06-25 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-03 | 2022-07-04 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-07-03 | 2022-07-05 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-29 | 2022-07-01 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-28 | 2022-05-30 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-25 | 2022-05-27 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-09 | 2022-04-11 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-09 | 2022-04-11 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-06 | 2022-07-08 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-07 | 2022-07-09 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-11 | 2022-04-16 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-28 | 2022-06-02 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-26 | 2022-07-01 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-04 | 2022-07-09 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-09 | 2022-07-10 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-16 | 2022-04-17 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-05 | 2022-06-06 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-01 | 2022-07-02 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-25 | 2022-04-26 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-17 | 2022-04-18 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-05 | 2022-06-06 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-01 | 2022-07-02 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-09 | 2022-07-10 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-07-01 | 2022-07-03 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-04 | 2022-07-06 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-17 | 2022-06-19 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-04 | 2022-06-06 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-20 | 2022-05-22 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-16 | 2022-04-18 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-10 | 2022-07-12 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-13 | 2022-07-15 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-04-29 | 2022-05-04 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-11 | 2022-06-16 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-07-02 | 2022-07-07 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-10 | 2022-07-15 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-15 | 2022-07-16 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-04 | 2022-05-05 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-16 | 2022-06-17 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-07 | 2022-07-08 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-05 | 2022-05-06 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-06 | 2022-05-07 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-18 | 2022-06-19 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-07 | 2022-07-08 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-15 | 2022-07-16 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-10 | 2022-07-12 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-13 | 2022-07-15 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-20 | 2022-06-22 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-17 | 2022-06-19 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-22 | 2022-05-24 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-04 | 2022-05-06 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-16 | 2022-07-18 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-16 | 2022-07-18 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-09 | 2022-05-14 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-20 | 2022-06-25 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-11 | 2022-07-16 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-16 | 2022-07-21 | 1

## Plan_D_51
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-28 | 2022-04-02 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-02 | 2022-04-03 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-08 | 2022-03-09 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-07 | 2022-04-08 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-07-01 | 2022-07-03 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-07-01 | 2022-07-03 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-07-08 | 2022-07-10 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-07-04 | 2022-07-06 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-22 | 2022-03-27 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-08 | 2022-04-13 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-14 | 2022-04-15 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-27 | 2022-03-28 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-28 | 2022-03-29 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-23 | 2022-03-24 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-01 | 2022-04-02 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-14 | 2022-04-15 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-05-25 | 2022-05-27 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-09 | 2022-05-11 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-24 | 2022-03-26 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-21 | 2022-03-23 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-21 | 2022-03-23 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-28 | 2022-05-30 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-29 | 2022-05-31 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-30 | 2022-04-04 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-04 | 2022-04-09 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-15 | 2022-04-20 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-23 | 2022-05-24 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-04-04 | 2022-04-05 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-17 | 2022-04-18 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-23 | 2022-04-24 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-04-04 | 2022-04-05 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-26 | 2022-03-27 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-17 | 2022-04-18 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-23 | 2022-04-24 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-20 | 2022-05-21 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-06-17 | 2022-06-19 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-06-17 | 2022-06-19 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-04 | 2022-04-06 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-04 | 2022-04-06 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-01 | 2022-04-03 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-01 | 2022-04-03 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-24 | 2022-06-26 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-20 | 2022-06-22 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-13 | 2022-04-18 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-20 | 2022-04-25 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-25 | 2022-04-30 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-26 | 2022-05-31 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-25 | 2022-06-26 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-30 | 2022-05-01 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-04 | 2022-05-05 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-06-01 | 2022-06-02 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-21 | 2022-04-22 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-05-02 | 2022-05-03 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-05-07 | 2022-05-08 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-09 | 2022-05-10 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-27 | 2022-06-28 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-12 | 2022-05-14 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-10 | 2022-05-12 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-25 | 2022-04-27 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-25 | 2022-04-27 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-18 | 2022-04-20 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-18 | 2022-04-20 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-06 | 2022-06-08 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-01 | 2022-06-03 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-05-03 | 2022-05-08 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-12 | 2022-05-17 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-03 | 2022-06-08 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-29 | 2022-07-04 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-07-04 | 2022-07-05 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-05-13 | 2022-05-14 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-29 | 2022-05-30 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-08 | 2022-06-09 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-05-09 | 2022-05-10 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-05-13 | 2022-05-14 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-24 | 2022-05-25 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-08 | 2022-06-09 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-04 | 2022-07-05 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-13 | 2022-06-15 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-13 | 2022-06-15 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-21 | 2022-05-23 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-18 | 2022-05-20 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-05-16 | 2022-05-18 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-05-13 | 2022-05-15 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-04 | 2022-07-06 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-07 | 2022-07-09 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-05-17 | 2022-05-22 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-06-03 | 2022-06-08 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-11 | 2022-06-16 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-05 | 2022-07-10 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-10 | 2022-07-11 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-26 | 2022-05-27 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-12 | 2022-06-13 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-17 | 2022-06-18 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-25 | 2022-05-26 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-22 | 2022-05-23 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-12 | 2022-06-13 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-22 | 2022-06-23 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-10 | 2022-07-11 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-24 | 2022-06-26 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-20 | 2022-06-22 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-10 | 2022-06-12 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-09 | 2022-06-11 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-26 | 2022-05-28 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-22 | 2022-05-24 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-14 | 2022-07-16 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-10 | 2022-07-12 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-28 | 2022-06-02 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-17 | 2022-06-22 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-23 | 2022-06-28 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-11 | 2022-07-16 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-16 | 2022-07-17 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-06-05 | 2022-06-06 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-26 | 2022-06-27 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-29 | 2022-06-30 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-06-19 | 2022-06-20 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-06-06 | 2022-06-07 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-22 | 2022-06-23 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-06 | 2022-07-07 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-16 | 2022-07-17 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-11 | 2022-07-13 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-13 | 2022-07-15 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-28 | 2022-06-30 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-27 | 2022-06-29 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-06-04 | 2022-06-06 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-02 | 2022-06-04 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-17 | 2022-07-19 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-16 | 2022-07-18 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-23 | 2022-06-28 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-07-05 | 2022-07-10 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-11 | 2022-07-16 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-17 | 2022-07-22 | 1

## Plan_D_52
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-20 | 2022-03-25 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-03-29 | 2022-03-30 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-08 | 2022-03-09 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-22 | 2022-03-23 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-22 | 2022-03-23 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-03-25 | 2022-03-26 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-05-31 | 2022-06-02 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-05-30 | 2022-06-01 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-12 | 2022-06-14 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-12 | 2022-06-14 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-12 | 2022-03-17 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-18 | 2022-03-23 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-26 | 2022-03-31 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-02 | 2022-04-07 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-30 | 2022-05-01 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-19 | 2022-03-20 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-26 | 2022-03-27 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-06 | 2022-04-07 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-24 | 2022-03-25 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-07 | 2022-04-08 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-13 | 2022-04-14 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-15 | 2022-04-17 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-04 | 2022-05-06 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-23 | 2022-03-25 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-23 | 2022-03-25 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-20 | 2022-03-22 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-20 | 2022-03-22 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-07 | 2022-05-09 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-07 | 2022-05-09 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-24 | 2022-03-29 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-30 | 2022-04-04 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-26 | 2022-05-01 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-13 | 2022-05-18 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-21 | 2022-05-22 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-04-04 | 2022-04-05 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-09 | 2022-04-10 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-04 | 2022-05-05 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-04-01 | 2022-04-02 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-04-04 | 2022-04-05 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-09 | 2022-04-10 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-01 | 2022-05-02 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-21 | 2022-05-22 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-06-02 | 2022-06-04 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-03 | 2022-05-05 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-04 | 2022-04-06 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-04 | 2022-04-06 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-01 | 2022-04-03 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-01 | 2022-04-03 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-08 | 2022-06-10 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-08 | 2022-06-10 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-05 | 2022-04-10 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-11 | 2022-04-16 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-21 | 2022-05-26 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-05 | 2022-06-10 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-19 | 2022-06-20 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-13 | 2022-04-14 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-20 | 2022-04-21 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-06-09 | 2022-06-10 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-11 | 2022-04-12 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-11 | 2022-04-12 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-20 | 2022-04-21 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-06-07 | 2022-06-08 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-10 | 2022-06-11 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-24 | 2022-06-26 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-28 | 2022-05-30 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-16 | 2022-04-18 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-18 | 2022-04-20 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-10 | 2022-04-12 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-10 | 2022-04-12 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-07-01 | 2022-07-03 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-27 | 2022-06-29 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-14 | 2022-04-19 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-24 | 2022-05-29 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-11 | 2022-06-16 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-20 | 2022-06-25 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-07-03 | 2022-07-04 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-22 | 2022-04-23 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-29 | 2022-05-30 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-16 | 2022-06-17 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-05-02 | 2022-05-03 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-22 | 2022-04-23 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-06-12 | 2022-06-13 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-16 | 2022-06-17 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-03 | 2022-07-04 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-22 | 2022-06-24 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-18 | 2022-06-20 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-06-15 | 2022-06-17 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-06-15 | 2022-06-17 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-05-21 | 2022-05-23 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-19 | 2022-04-21 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-04 | 2022-07-06 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-04 | 2022-07-06 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-05-17 | 2022-05-22 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-06-14 | 2022-06-19 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-26 | 2022-07-01 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-05 | 2022-07-10 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-10 | 2022-07-11 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-24 | 2022-05-25 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-19 | 2022-06-20 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-05 | 2022-07-06 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-26 | 2022-05-27 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-27 | 2022-05-28 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-21 | 2022-06-22 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-05 | 2022-07-06 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-10 | 2022-07-11 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-07-07 | 2022-07-09 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-09 | 2022-07-11 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-21 | 2022-06-23 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-19 | 2022-06-21 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-22 | 2022-05-24 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-24 | 2022-05-26 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-12 | 2022-07-14 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-12 | 2022-07-14 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-31 | 2022-06-05 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-22 | 2022-06-27 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-07-07 | 2022-07-12 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-12 | 2022-07-17 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-17 | 2022-07-18 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-06-05 | 2022-06-06 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-27 | 2022-06-28 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-12 | 2022-07-13 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-06-05 | 2022-06-06 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-06-07 | 2022-06-08 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-27 | 2022-06-28 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-12 | 2022-07-13 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-17 | 2022-07-18 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-15 | 2022-07-17 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-15 | 2022-07-17 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-27 | 2022-06-29 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-30 | 2022-07-02 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-06-05 | 2022-06-07 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-05 | 2022-06-07 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-18 | 2022-07-20 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-18 | 2022-07-20 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-08 | 2022-06-13 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-28 | 2022-07-03 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-13 | 2022-07-18 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-18 | 2022-07-23 | 1

## Plan_D_53
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-01 | 2022-04-06 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-06 | 2022-04-07 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-08 | 2022-03-09 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-18 | 2022-03-19 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-16 | 2022-04-17 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-05-20 | 2022-05-22 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-05-17 | 2022-05-19 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-28 | 2022-03-30 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-13 | 2022-03-15 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-10 | 2022-03-12 | 4
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-10 | 2022-03-12 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-30 | 2022-06-01 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-06 | 2022-06-08 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-20 | 2022-03-25 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-25 | 2022-03-30 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-17 | 2022-04-22 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-22 | 2022-04-23 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-25 | 2022-03-26 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-05 | 2022-04-06 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-29 | 2022-03-30 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-02 | 2022-04-03 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-28 | 2022-04-29 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-29 | 2022-05-01 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-18 | 2022-05-20 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-06 | 2022-04-08 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-04-06 | 2022-04-08 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-04-02 | 2022-04-04 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-04-03 | 2022-04-05 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-18 | 2022-06-20 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-30 | 2022-06-01 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-07 | 2022-04-12 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-18 | 2022-04-23 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-01 | 2022-05-06 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-07 | 2022-05-08 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-23 | 2022-03-24 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-14 | 2022-04-15 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-29 | 2022-04-30 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-23 | 2022-03-24 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-25 | 2022-03-26 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-20 | 2022-04-21 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-27 | 2022-04-28 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-13 | 2022-05-14 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-13 | 2022-05-15 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-12 | 2022-05-14 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-05-09 | 2022-05-11 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-05-09 | 2022-05-11 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-05-06 | 2022-05-08 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-05-06 | 2022-05-08 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-15 | 2022-05-17 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-10 | 2022-06-12 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-26 | 2022-05-01 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-05 | 2022-05-10 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-15 | 2022-05-20 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-01 | 2022-06-02 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-03-31 | 2022-04-01 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-01 | 2022-05-02 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-10 | 2022-05-11 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-02 | 2022-04-03 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-03-31 | 2022-04-01 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-05-01 | 2022-05-02 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-16 | 2022-05-17 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-01 | 2022-06-02 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-27 | 2022-05-29 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-27 | 2022-05-29 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-23 | 2022-05-25 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-05-23 | 2022-05-25 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-09 | 2022-04-11 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-09 | 2022-04-11 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-03 | 2022-06-05 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-03 | 2022-06-05 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-05 | 2022-04-10 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-25 | 2022-05-30 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-02 | 2022-06-07 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-23 | 2022-06-28 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-30 | 2022-07-01 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-14 | 2022-04-15 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-30 | 2022-05-31 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-14 | 2022-06-15 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-16 | 2022-04-17 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-05-08 | 2022-05-09 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-30 | 2022-05-31 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-14 | 2022-06-15 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-30 | 2022-07-01 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-30 | 2022-07-02 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-28 | 2022-06-30 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-06-18 | 2022-06-20 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-06-26 | 2022-06-28 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-24 | 2022-04-26 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-06-09 | 2022-06-11 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-06 | 2022-07-08 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-03 | 2022-07-05 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-05-14 | 2022-05-19 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-06-08 | 2022-06-13 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-19 | 2022-06-24 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-01 | 2022-07-06 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-11 | 2022-07-12 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-26 | 2022-05-27 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-28 | 2022-06-29 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-04 | 2022-07-05 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-23 | 2022-05-24 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-23 | 2022-05-24 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-28 | 2022-06-29 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-03 | 2022-07-04 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-08 | 2022-07-09 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-24 | 2022-06-26 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-04 | 2022-07-06 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-21 | 2022-06-23 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-22 | 2022-06-24 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-06-12 | 2022-06-14 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-06-06 | 2022-06-08 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-13 | 2022-07-15 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-07 | 2022-07-09 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-06-01 | 2022-06-06 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-07-01 | 2022-07-06 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-07-08 | 2022-07-13 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-13 | 2022-07-18 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-18 | 2022-07-19 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-06-21 | 2022-06-22 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-07-06 | 2022-07-07 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-13 | 2022-07-14 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-06-21 | 2022-06-22 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-06-19 | 2022-06-20 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-07-06 | 2022-07-07 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-13 | 2022-07-14 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-18 | 2022-07-19 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-14 | 2022-07-16 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-16 | 2022-07-18 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-07-09 | 2022-07-11 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-07-10 | 2022-07-12 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-06-15 | 2022-06-17 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-15 | 2022-06-17 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-19 | 2022-07-21 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-19 | 2022-07-21 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-25 | 2022-06-30 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-07-07 | 2022-07-12 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-14 | 2022-07-19 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-19 | 2022-07-24 | 1

## Plan_D_54
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-19 | 2022-04-24 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-27 | 2022-04-28 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-25 | 2022-03-26 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-08 | 2022-03-09 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-15 | 2022-03-16 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-21 | 2022-03-22 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-29 | 2022-04-30 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-18 | 2022-03-20 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-21 | 2022-03-23 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-15 | 2022-03-17 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-07 | 2022-03-09 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-07 | 2022-03-09 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-04-24 | 2022-04-26 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-27 | 2022-04-29 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-27 | 2022-04-01 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-22 | 2022-05-27 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-27 | 2022-05-28 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-23 | 2022-03-24 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-01 | 2022-04-02 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-18 | 2022-03-19 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-23 | 2022-03-24 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-01 | 2022-04-02 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-30 | 2022-05-31 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-01 | 2022-04-03 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-04 | 2022-04-06 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-27 | 2022-03-29 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-15 | 2022-03-17 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-18 | 2022-03-20 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-05-27 | 2022-05-29 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-05-30 | 2022-06-01 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-24 | 2022-03-29 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-02 | 2022-04-07 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-06-03 | 2022-06-08 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-21 | 2022-06-22 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-27 | 2022-03-28 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-29 | 2022-03-30 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-24 | 2022-04-25 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-26 | 2022-03-27 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-28 | 2022-03-29 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-04 | 2022-04-05 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-22 | 2022-04-23 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-08 | 2022-06-09 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-07 | 2022-04-09 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-10 | 2022-04-12 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-02 | 2022-04-04 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-05 | 2022-04-07 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-30 | 2022-04-01 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-27 | 2022-03-29 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-08 | 2022-06-10 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-11 | 2022-06-13 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-30 | 2022-04-04 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-05 | 2022-04-10 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-25 | 2022-04-30 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-22 | 2022-06-27 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-27 | 2022-06-28 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-06 | 2022-04-07 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-18 | 2022-04-19 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-23 | 2022-05-24 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-09 | 2022-04-10 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-04 | 2022-04-05 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-10 | 2022-04-11 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-03 | 2022-05-04 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-27 | 2022-06-28 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-30 | 2022-05-02 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-03 | 2022-05-05 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-13 | 2022-04-15 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-16 | 2022-04-18 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-08 | 2022-04-10 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-11 | 2022-04-13 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-27 | 2022-06-29 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-30 | 2022-07-02 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-11 | 2022-04-16 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-01 | 2022-05-06 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-30 | 2022-06-04 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-29 | 2022-07-04 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-07-04 | 2022-07-05 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-25 | 2022-04-26 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-06 | 2022-05-07 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-05 | 2022-06-06 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-23 | 2022-04-24 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-05-01 | 2022-05-02 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-08 | 2022-05-09 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-21 | 2022-06-22 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-04 | 2022-07-05 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-04 | 2022-06-06 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-14 | 2022-06-16 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-06 | 2022-05-08 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-09 | 2022-05-11 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-19 | 2022-04-21 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-16 | 2022-04-18 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-04 | 2022-07-06 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-07 | 2022-07-09 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-05-04 | 2022-05-09 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-10 | 2022-05-15 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-07-01 | 2022-07-06 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-06 | 2022-07-11 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-11 | 2022-07-12 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-10 | 2022-05-11 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-15 | 2022-05-16 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-06 | 2022-07-07 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-12 | 2022-05-13 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-09 | 2022-05-10 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-17 | 2022-05-18 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-08 | 2022-07-09 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-11 | 2022-07-12 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-07-10 | 2022-07-12 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-06 | 2022-07-08 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-15 | 2022-05-17 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-18 | 2022-05-20 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-12 | 2022-05-14 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-09 | 2022-05-11 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-13 | 2022-07-15 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-12 | 2022-07-14 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-16 | 2022-05-21 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-28 | 2022-06-02 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-07-09 | 2022-07-14 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-14 | 2022-07-19 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-19 | 2022-07-20 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-21 | 2022-05-22 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-02 | 2022-06-03 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-14 | 2022-07-15 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-23 | 2022-05-24 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-25 | 2022-05-26 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-10 | 2022-06-11 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-14 | 2022-07-15 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-19 | 2022-07-20 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-16 | 2022-07-18 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-15 | 2022-07-17 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-17 | 2022-06-19 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-20 | 2022-06-22 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-21 | 2022-05-23 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-24 | 2022-05-26 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-19 | 2022-07-21 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-19 | 2022-07-21 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-09 | 2022-06-14 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-15 | 2022-06-20 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-15 | 2022-07-20 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-20 | 2022-07-25 | 1

## Plan_D_55
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-14 | 2022-03-19 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-29 | 2022-05-04 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-05-15 | 2022-05-16 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-08 | 2022-03-09 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-05-15 | 2022-05-16 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-26 | 2022-03-28 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-06-04 | 2022-06-06 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-16 | 2022-06-18 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-16 | 2022-06-18 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-18 | 2022-03-23 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-05-10 | 2022-05-15 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-06-07 | 2022-06-12 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-06-12 | 2022-06-13 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-24 | 2022-03-25 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-05-19 | 2022-05-20 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-23 | 2022-03-24 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-05-19 | 2022-05-20 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-06-12 | 2022-06-13 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-06-07 | 2022-06-09 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-30 | 2022-06-01 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-23 | 2022-03-25 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-23 | 2022-03-25 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-20 | 2022-03-22 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-20 | 2022-03-22 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-12 | 2022-06-14 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-12 | 2022-06-14 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-20 | 2022-03-25 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-26 | 2022-03-31 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-05-22 | 2022-05-27 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-06-17 | 2022-06-22 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-22 | 2022-06-23 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-27 | 2022-03-28 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-31 | 2022-04-01 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-06-15 | 2022-06-16 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-27 | 2022-03-28 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-16 | 2022-04-17 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-06-15 | 2022-06-16 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-22 | 2022-06-23 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-06-22 | 2022-06-24 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-06-20 | 2022-06-22 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-03-31 | 2022-04-02 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-01 | 2022-04-03 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-29 | 2022-03-31 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-26 | 2022-03-28 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-27 | 2022-06-29 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-07-04 | 2022-07-06 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-30 | 2022-04-04 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-23 | 2022-04-28 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-06-18 | 2022-06-23 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-23 | 2022-06-28 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-28 | 2022-06-29 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-06 | 2022-04-07 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-28 | 2022-04-29 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-06-24 | 2022-06-25 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-04 | 2022-04-05 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-04 | 2022-04-05 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-30 | 2022-05-01 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-06-24 | 2022-06-25 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-29 | 2022-06-30 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-23 | 2022-06-25 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-25 | 2022-06-27 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-28 | 2022-04-30 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-28 | 2022-04-30 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-06 | 2022-04-08 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-06 | 2022-04-08 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-07-01 | 2022-07-03 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-28 | 2022-06-30 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-07 | 2022-04-12 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-01 | 2022-05-06 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-26 | 2022-07-01 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-07-01 | 2022-07-06 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-07-07 | 2022-07-08 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-22 | 2022-04-23 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-10 | 2022-05-11 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-07-01 | 2022-07-02 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-22 | 2022-04-23 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-19 | 2022-04-20 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-10 | 2022-05-11 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-07-01 | 2022-07-02 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-07 | 2022-07-08 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-07-04 | 2022-07-06 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-07-01 | 2022-07-03 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-06 | 2022-05-08 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-06 | 2022-05-08 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-12 | 2022-04-14 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-12 | 2022-04-14 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-07 | 2022-07-09 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-07 | 2022-07-09 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-24 | 2022-04-29 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-21 | 2022-05-26 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-07-02 | 2022-07-07 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-08 | 2022-07-13 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-13 | 2022-07-14 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-08 | 2022-05-09 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-27 | 2022-05-28 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-09 | 2022-07-10 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-08 | 2022-05-09 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-29 | 2022-04-30 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-27 | 2022-05-28 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-09 | 2022-07-10 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-13 | 2022-07-14 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-07-12 | 2022-07-14 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-11 | 2022-07-13 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-26 | 2022-05-28 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-26 | 2022-05-28 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-01 | 2022-05-03 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-01 | 2022-05-03 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-18 | 2022-07-20 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-18 | 2022-07-20 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-16 | 2022-05-21 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-01 | 2022-06-06 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-07-10 | 2022-07-15 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-15 | 2022-07-20 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-20 | 2022-07-21 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-29 | 2022-05-30 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-06 | 2022-06-07 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-15 | 2022-07-16 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-21 | 2022-05-22 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-29 | 2022-05-30 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-06 | 2022-06-07 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-15 | 2022-07-16 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-20 | 2022-07-21 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-15 | 2022-07-17 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-15 | 2022-07-17 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-06 | 2022-06-08 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-09 | 2022-06-11 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-21 | 2022-05-23 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-21 | 2022-05-23 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-21 | 2022-07-23 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-21 | 2022-07-23 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-30 | 2022-06-04 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-07 | 2022-06-12 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-16 | 2022-07-21 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-21 | 2022-07-26 | 2

## Plan_D_56
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-24 | 2022-03-29 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-08 | 2022-04-09 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-21 | 2022-03-22 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-08 | 2022-04-09 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-06-20 | 2022-06-22 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-06-16 | 2022-06-18 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-24 | 2022-06-26 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-23 | 2022-06-25 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-19 | 2022-03-24 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-30 | 2022-04-04 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-12 | 2022-04-17 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-18 | 2022-04-19 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-16 | 2022-03-17 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-27 | 2022-03-28 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-14 | 2022-04-15 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-27 | 2022-03-28 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-17 | 2022-04-18 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-21 | 2022-04-22 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-06-08 | 2022-06-10 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-06-08 | 2022-06-10 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-24 | 2022-03-26 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-24 | 2022-03-26 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-21 | 2022-03-23 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-21 | 2022-03-23 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-07-09 | 2022-07-11 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-11 | 2022-06-13 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-06 | 2022-04-11 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-18 | 2022-04-23 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-23 | 2022-04-28 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-04-28 | 2022-04-29 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-24 | 2022-03-25 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-12 | 2022-04-13 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-23 | 2022-04-24 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-23 | 2022-03-24 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-12 | 2022-04-13 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-23 | 2022-04-24 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-02 | 2022-05-03 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-28 | 2022-04-30 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-27 | 2022-04-29 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-11 | 2022-04-13 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-11 | 2022-04-13 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-05 | 2022-04-07 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-05 | 2022-04-07 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-04-30 | 2022-05-02 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-27 | 2022-06-29 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-15 | 2022-04-20 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-26 | 2022-05-01 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-04 | 2022-05-09 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-31 | 2022-06-01 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-03-31 | 2022-04-01 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-09 | 2022-05-10 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-23 | 2022-05-24 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-02 | 2022-04-03 | 6
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-03-31 | 2022-04-01 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-21 | 2022-04-22 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-21 | 2022-05-22 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-31 | 2022-06-01 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-13 | 2022-05-15 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-01 | 2022-05-03 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-20 | 2022-04-22 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-20 | 2022-04-22 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-02 | 2022-04-04 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-02 | 2022-04-04 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-29 | 2022-05-31 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-21 | 2022-05-23 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-03 | 2022-04-08 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-14 | 2022-05-19 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-25 | 2022-05-30 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-08 | 2022-06-13 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-06-14 | 2022-06-15 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-10 | 2022-04-11 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-19 | 2022-05-20 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-04 | 2022-06-05 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-10 | 2022-04-11 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-15 | 2022-04-16 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-21 | 2022-05-22 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-09 | 2022-06-10 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-06-16 | 2022-06-17 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-02 | 2022-06-04 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-02 | 2022-06-04 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-20 | 2022-05-22 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-23 | 2022-05-25 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-08 | 2022-04-10 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-08 | 2022-04-10 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-21 | 2022-06-23 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-06-28 | 2022-06-30 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-05-30 | 2022-06-04 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-06-06 | 2022-06-11 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-13 | 2022-06-18 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-06-19 | 2022-06-24 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-14 | 2022-07-15 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-06-20 | 2022-06-21 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-07-01 | 2022-07-02 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-10 | 2022-07-11 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-06-20 | 2022-06-21 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-06-11 | 2022-06-12 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-25 | 2022-06-26 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-05 | 2022-07-06 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-14 | 2022-07-15 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-07-02 | 2022-07-04 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-06 | 2022-07-08 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-17 | 2022-06-19 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-14 | 2022-06-16 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-06-11 | 2022-06-13 | 4
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-06-05 | 2022-06-07 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-09 | 2022-07-11 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-16 | 2022-07-18 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-06-26 | 2022-07-01 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-07-03 | 2022-07-08 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-07-11 | 2022-07-16 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-16 | 2022-07-21 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-21 | 2022-07-22 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-07-01 | 2022-07-02 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-07-09 | 2022-07-10 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-16 | 2022-07-17 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-07-03 | 2022-07-04 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-07-03 | 2022-07-04 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-07-08 | 2022-07-09 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-16 | 2022-07-17 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-21 | 2022-07-22 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-19 | 2022-07-21 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-19 | 2022-07-21 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-07-14 | 2022-07-16 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-07-12 | 2022-07-14 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-07-06 | 2022-07-08 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-07-03 | 2022-07-05 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-22 | 2022-07-24 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-22 | 2022-07-24 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-07-04 | 2022-07-09 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-07-10 | 2022-07-15 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-17 | 2022-07-22 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-22 | 2022-07-27 | 2

## Plan_D_57
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-14 | 2022-03-19 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-20 | 2022-03-25 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-03-31 | 2022-04-01 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-19 | 2022-03-20 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-19 | 2022-03-20 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-03-31 | 2022-04-01 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-12 | 2022-04-14 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-05-03 | 2022-05-05 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-06 | 2022-06-08 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-04 | 2022-06-06 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-24 | 2022-03-29 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-29 | 2022-04-03 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-03 | 2022-04-08 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-09 | 2022-04-10 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-04-04 | 2022-04-05 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-06 | 2022-04-07 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-04-02 | 2022-04-03 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-06 | 2022-04-07 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-09 | 2022-04-10 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-06-22 | 2022-06-24 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-06-20 | 2022-06-22 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-29 | 2022-03-31 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-29 | 2022-03-31 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-26 | 2022-03-28 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-26 | 2022-03-28 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-26 | 2022-06-28 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-29 | 2022-07-01 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-12 | 2022-04-17 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-22 | 2022-04-27 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-06-12 | 2022-06-17 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-25 | 2022-06-26 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-22 | 2022-04-23 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-29 | 2022-04-30 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-23 | 2022-03-24 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-23 | 2022-03-24 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-22 | 2022-04-23 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-01 | 2022-05-02 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-23 | 2022-06-24 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-06-19 | 2022-06-21 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-07-08 | 2022-07-10 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-17 | 2022-04-19 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-17 | 2022-04-19 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-06 | 2022-04-08 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-06 | 2022-04-08 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-07-14 | 2022-07-16 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-07-14 | 2022-07-16 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-06 | 2022-04-11 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-29 | 2022-05-04 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-07 | 2022-05-12 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-26 | 2022-07-01 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-07-02 | 2022-07-03 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-12 | 2022-04-13 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-05 | 2022-05-06 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-14 | 2022-05-15 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-13 | 2022-04-14 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-19 | 2022-04-20 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-05-04 | 2022-05-05 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-17 | 2022-05-18 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-07-02 | 2022-07-03 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-31 | 2022-06-02 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-31 | 2022-06-02 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-04 | 2022-05-06 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-05-06 | 2022-05-08 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-11 | 2022-04-13 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-14 | 2022-04-16 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-07-05 | 2022-07-07 | 3
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-07-02 | 2022-07-04 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-20 | 2022-04-25 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-09 | 2022-05-14 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-18 | 2022-05-23 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-07-03 | 2022-07-08 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-07-08 | 2022-07-09 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-27 | 2022-04-28 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-18 | 2022-05-19 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-24 | 2022-05-25 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-28 | 2022-04-29 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-30 | 2022-05-01 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-16 | 2022-05-17 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-24 | 2022-05-25 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-08 | 2022-07-09 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-03 | 2022-06-05 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-15 | 2022-06-17 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-14 | 2022-05-16 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-14 | 2022-05-16 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-25 | 2022-04-27 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-25 | 2022-04-27 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-11 | 2022-07-13 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-11 | 2022-07-13 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-05-02 | 2022-05-07 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-20 | 2022-05-25 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-29 | 2022-06-03 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-09 | 2022-07-14 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-15 | 2022-07-16 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-12 | 2022-05-13 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-27 | 2022-05-28 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-06-08 | 2022-06-09 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-08 | 2022-05-09 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-12 | 2022-05-13 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-07 | 2022-06-08 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-06-11 | 2022-06-12 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-15 | 2022-07-16 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-16 | 2022-06-18 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-06-23 | 2022-06-25 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-12 | 2022-06-14 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-12 | 2022-06-14 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-06-09 | 2022-06-11 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-06-09 | 2022-06-11 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-17 | 2022-07-19 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-17 | 2022-07-19 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-13 | 2022-05-18 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-12 | 2022-06-17 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-06-20 | 2022-06-25 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-17 | 2022-07-22 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-22 | 2022-07-23 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-21 | 2022-05-22 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-07-10 | 2022-07-11 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-17 | 2022-07-18 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-19 | 2022-05-20 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-06-30 | 2022-07-01 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-07-04 | 2022-07-05 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-17 | 2022-07-18 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-22 | 2022-07-23 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-20 | 2022-07-22 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-20 | 2022-07-22 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-07-08 | 2022-07-10 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-07-03 | 2022-07-05 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-06-29 | 2022-07-01 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-26 | 2022-06-28 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-23 | 2022-07-25 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-23 | 2022-07-25 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-07-06 | 2022-07-11 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-07-12 | 2022-07-17 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-18 | 2022-07-23 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-23 | 2022-07-28 | 2

## Plan_D_58
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-04-05 | 2022-04-10 | 1
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-11 | 2022-04-16 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-05-08 | 2022-05-09 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-04-10 | 2022-04-11 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-08 | 2022-03-09 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-04-11 | 2022-04-12 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-16 | 2022-04-17 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-06-05 | 2022-06-07 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-06-03 | 2022-06-05 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-14 | 2022-03-16 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-08 | 2022-06-10 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-12 | 2022-06-14 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-15 | 2022-03-20 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-15 | 2022-04-20 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-12 | 2022-05-17 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-17 | 2022-05-18 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-22 | 2022-03-23 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-21 | 2022-04-22 | 5
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-20 | 2022-04-21 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-17 | 2022-05-18 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-06-27 | 2022-06-29 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-06-22 | 2022-06-24 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-06-18 | 2022-06-20 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-06-18 | 2022-06-20 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-06-15 | 2022-06-17 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-04-08 | 2022-04-10 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-07-03 | 2022-07-05 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-07-06 | 2022-07-08 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-23 | 2022-03-28 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-24 | 2022-04-29 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-18 | 2022-05-23 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-25 | 2022-05-26 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-23 | 2022-03-24 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-28 | 2022-03-29 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-15 | 2022-05-16 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-25 | 2022-03-26 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-28 | 2022-03-29 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-15 | 2022-05-16 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-03 | 2022-06-04 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-05-24 | 2022-05-26 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-18 | 2022-05-20 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-03-31 | 2022-04-02 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-03-29 | 2022-03-31 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-24 | 2022-03-26 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-27 | 2022-03-29 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-05-26 | 2022-05-28 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-01 | 2022-06-03 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-03-31 | 2022-04-05 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-06-11 | 2022-06-16 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-19 | 2022-06-24 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-25 | 2022-06-26 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-01 | 2022-04-02 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-05 | 2022-04-06 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-06-23 | 2022-06-24 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-03-31 | 2022-04-01 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-02 | 2022-04-03 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-05 | 2022-04-06 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-06-23 | 2022-06-24 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-25 | 2022-06-26 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-21 | 2022-06-23 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-26 | 2022-06-28 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-05 | 2022-04-07 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-06 | 2022-04-08 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-03 | 2022-04-05 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-01 | 2022-04-03 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-30 | 2022-07-02 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-07-08 | 2022-07-10 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-08 | 2022-04-13 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-21 | 2022-04-26 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-25 | 2022-06-30 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-07-04 | 2022-07-09 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-07-09 | 2022-07-10 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-14 | 2022-04-15 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-26 | 2022-04-27 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-30 | 2022-07-01 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-14 | 2022-04-15 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-16 | 2022-04-17 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-28 | 2022-04-29 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-30 | 2022-07-01 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-09 | 2022-07-10 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-07-02 | 2022-07-04 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-07-05 | 2022-07-07 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-27 | 2022-05-29 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-29 | 2022-05-31 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-05-22 | 2022-05-24 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-13 | 2022-04-15 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-15 | 2022-07-17 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-14 | 2022-07-16 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-17 | 2022-04-22 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-04 | 2022-05-09 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-07-05 | 2022-07-10 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-11 | 2022-07-16 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-16 | 2022-07-17 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-04-23 | 2022-04-24 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-10 | 2022-06-11 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-11 | 2022-07-12 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-04-30 | 2022-05-01 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-04-30 | 2022-05-01 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-09 | 2022-05-10 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-11 | 2022-07-12 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-16 | 2022-07-17 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-07-11 | 2022-07-13 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-12 | 2022-07-14 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-29 | 2022-07-01 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-06 | 2022-06-08 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-19 | 2022-05-21 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-04-22 | 2022-04-24 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-17 | 2022-07-19 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-21 | 2022-07-23 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-01 | 2022-05-06 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-12 | 2022-06-17 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-07-12 | 2022-07-17 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-18 | 2022-07-23 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-23 | 2022-07-24 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-06-02 | 2022-06-03 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-21 | 2022-06-22 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-18 | 2022-07-19 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-29 | 2022-05-30 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-29 | 2022-05-30 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-21 | 2022-06-22 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-18 | 2022-07-19 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-23 | 2022-07-24 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-18 | 2022-07-20 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-20 | 2022-07-22 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-07-09 | 2022-07-11 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-24 | 2022-06-26 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-06-14 | 2022-06-16 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-06 | 2022-05-08 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-24 | 2022-07-26 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-23 | 2022-07-25 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-06 | 2022-06-11 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-27 | 2022-07-02 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-19 | 2022-07-24 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-24 | 2022-07-29 | 2

## Plan_D_59
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-04-05 | 2022-04-10 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-05-05 | 2022-05-10 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-05-14 | 2022-05-15 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-04-13 | 2022-04-14 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-04-16 | 2022-04-17 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-05-11 | 2022-05-12 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-05-25 | 2022-05-27 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-05-28 | 2022-05-30 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-15 | 2022-06-17 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-30 | 2022-06-01 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-05-11 | 2022-05-16 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-19 | 2022-05-24 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-28 | 2022-05-29 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-05-16 | 2022-05-17 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-16 | 2022-03-17 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-05-16 | 2022-05-17 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-25 | 2022-05-26 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-06-09 | 2022-06-11 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-06-05 | 2022-06-07 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-01 | 2022-04-03 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-22 | 2022-03-24 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-20 | 2022-03-22 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-19 | 2022-03-21 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-11 | 2022-06-13 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-16 | 2022-06-18 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-23 | 2022-03-28 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-05-22 | 2022-05-27 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-30 | 2022-06-04 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-09 | 2022-06-10 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-24 | 2022-03-25 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-31 | 2022-04-01 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-06-05 | 2022-06-06 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-23 | 2022-03-24 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-31 | 2022-04-01 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-06-05 | 2022-06-06 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-09 | 2022-06-10 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-06-05 | 2022-06-07 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-06-19 | 2022-06-21 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-05-20 | 2022-05-22 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-05-09 | 2022-05-11 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-08 | 2022-04-10 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-09 | 2022-04-11 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-06-24 | 2022-06-26 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-06-30 | 2022-07-02 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-01 | 2022-04-06 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-06-08 | 2022-06-13 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-20 | 2022-06-25 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-26 | 2022-06-27 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-05 | 2022-04-06 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-21 | 2022-04-22 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-06-15 | 2022-06-16 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-04 | 2022-04-05 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-06 | 2022-04-07 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-10 | 2022-04-11 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-06-15 | 2022-06-16 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-26 | 2022-06-27 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-21 | 2022-06-23 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-27 | 2022-06-29 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-26 | 2022-05-28 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-06 | 2022-04-08 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-04 | 2022-04-06 | 4
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-03-31 | 2022-04-02 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-07-07 | 2022-07-09 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-07-06 | 2022-07-08 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-07 | 2022-04-12 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-22 | 2022-04-27 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-24 | 2022-06-29 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-30 | 2022-07-05 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-07-07 | 2022-07-08 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-12 | 2022-04-13 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-29 | 2022-04-30 | 5
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-29 | 2022-06-30 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-19 | 2022-04-20 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-20 | 2022-04-21 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-29 | 2022-04-30 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-29 | 2022-06-30 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-07 | 2022-07-08 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-07-03 | 2022-07-05 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-07-04 | 2022-07-06 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-30 | 2022-05-02 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-16 | 2022-05-18 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-21 | 2022-04-23 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-21 | 2022-04-23 | 3
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-15 | 2022-07-17 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-11 | 2022-07-13 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-22 | 2022-04-27 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-06-04 | 2022-06-09 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-30 | 2022-07-05 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-08 | 2022-07-13 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-17 | 2022-07-18 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-05 | 2022-05-06 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-13 | 2022-06-14 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-05 | 2022-07-06 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-01 | 2022-05-02 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-03 | 2022-05-04 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-13 | 2022-06-14 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-05 | 2022-07-06 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-16 | 2022-07-17 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-07-14 | 2022-07-16 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-11 | 2022-07-13 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-18 | 2022-06-20 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-12 | 2022-06-14 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-31 | 2022-06-02 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-22 | 2022-05-24 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-22 | 2022-07-24 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-19 | 2022-07-21 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-28 | 2022-06-02 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-14 | 2022-06-19 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-07-11 | 2022-07-16 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-19 | 2022-07-24 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-24 | 2022-07-25 | 5
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-06-03 | 2022-06-04 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-07-13 | 2022-07-14 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-19 | 2022-07-20 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-06-07 | 2022-06-08 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-06-03 | 2022-06-04 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-07-13 | 2022-07-14 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-18 | 2022-07-19 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-24 | 2022-07-25 | 6
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-17 | 2022-07-19 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-22 | 2022-07-24 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-24 | 2022-06-26 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-29 | 2022-07-01 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-06-08 | 2022-06-10 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-02 | 2022-06-04 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-25 | 2022-07-27 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-25 | 2022-07-27 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-17 | 2022-06-22 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-07-14 | 2022-07-19 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-20 | 2022-07-25 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-25 | 2022-07-30 | 1

## Plan_D_6
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 2
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 1
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-04-03 | 2022-04-08 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-09 | 2022-04-14 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-30 | 2022-05-01 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-07 | 2022-03-08 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-04-08 | 2022-04-09 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-04-10 | 2022-04-11 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-30 | 2022-05-01 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-26 | 2022-04-28 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-26 | 2022-04-28 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-06-25 | 2022-06-27 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-02 | 2022-05-04 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 2
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-15 | 2022-03-20 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-04-12 | 2022-04-17 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-05-01 | 2022-05-06 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-05-06 | 2022-05-07 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-15 | 2022-03-16 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-27 | 2022-04-28 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-27 | 2022-04-28 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-05-06 | 2022-05-07 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-17 | 2022-04-19 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-05-08 | 2022-05-10 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-04-05 | 2022-04-07 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-04-05 | 2022-04-07 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-30 | 2022-04-01 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-30 | 2022-04-01 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-03 | 2022-06-05 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-03 | 2022-06-05 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-18 | 2022-03-23 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-23 | 2022-03-28 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-29 | 2022-05-04 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-07 | 2022-05-12 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-05-13 | 2022-05-14 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-23 | 2022-03-24 | 5
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-03-29 | 2022-03-30 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-09 | 2022-05-10 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-25 | 2022-03-26 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-23 | 2022-03-24 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-03-29 | 2022-03-30 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-09 | 2022-05-10 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-05-13 | 2022-05-14 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-06-06 | 2022-06-08 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-05-27 | 2022-05-29 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-05-17 | 2022-05-19 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-10 | 2022-04-12 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-25 | 2022-03-27 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-25 | 2022-03-27 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-07-11 | 2022-07-13 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-07-11 | 2022-07-13 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-26 | 2022-03-31 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-02 | 2022-04-07 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-12 | 2022-05-17 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-05-28 | 2022-06-02 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-14 | 2022-06-15 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-02 | 2022-04-03 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-19 | 2022-05-20 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-05-23 | 2022-05-24 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-02 | 2022-04-03 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-03-31 | 2022-04-01 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-07 | 2022-04-08 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-20 | 2022-05-21 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-11 | 2022-06-12 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-05-30 | 2022-06-01 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-06 | 2022-06-08 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-08 | 2022-04-10 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-16 | 2022-04-18 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-02 | 2022-04-04 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-02 | 2022-04-04 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-06-16 | 2022-06-18 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-06-28 | 2022-06-30 | 4
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-15 | 2022-04-20 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-20 | 2022-05-25 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-26 | 2022-05-31 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-19 | 2022-06-24 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-07-07 | 2022-07-08 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-22 | 2022-04-23 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-06-01 | 2022-06-02 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-07-03 | 2022-07-04 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-22 | 2022-04-23 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-20 | 2022-04-21 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-29 | 2022-05-30 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-18 | 2022-06-19 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-12 | 2022-07-13 | 5
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-29 | 2022-07-01 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-07-04 | 2022-07-06 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-06-20 | 2022-06-22 | 4
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-06-21 | 2022-06-23 | 3
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-06-09 | 2022-06-11 | 4
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-06-12 | 2022-06-14 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-07 | 2022-07-09 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-06 | 2022-07-08 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-23 | 2022-04-28 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-06-04 | 2022-06-09 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-07-09 | 2022-07-14 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-15 | 2022-07-20 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-20 | 2022-07-21 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-06-05 | 2022-06-06 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-10 | 2022-06-11 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-14 | 2022-07-15 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-02 | 2022-05-03 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-02 | 2022-05-03 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-09 | 2022-06-10 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-14 | 2022-07-15 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-20 | 2022-07-21 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-07-19 | 2022-07-21 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-18 | 2022-07-20 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-09 | 2022-06-11 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-13 | 2022-06-15 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-21 | 2022-05-23 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-21 | 2022-05-23 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-24 | 2022-07-26 | 4
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-21 | 2022-07-23 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-06-10 | 2022-06-15 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-23 | 2022-06-28 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-07-17 | 2022-07-22 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-22 | 2022-07-27 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-27 | 2022-07-28 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-06-24 | 2022-06-25 | 6
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-29 | 2022-06-30 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-22 | 2022-07-23 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-06-16 | 2022-06-17 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-06-16 | 2022-06-17 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-29 | 2022-06-30 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-22 | 2022-07-23 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-27 | 2022-07-28 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-22 | 2022-07-24 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-25 | 2022-07-27 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-07-15 | 2022-07-17 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-07-14 | 2022-07-16 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-06-24 | 2022-06-26 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-16 | 2022-06-18 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-28 | 2022-07-30 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-28 | 2022-07-30 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-25 | 2022-06-30 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-30 | 2022-07-05 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-23 | 2022-07-28 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-28 | 2022-08-02 | 1

## Plan_D_60
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-04 | 2022-04-09 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-09 | 2022-04-10 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-12 | 2022-03-13 | 6
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-19 | 2022-03-20 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-12 | 2022-03-13 | 5
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-19 | 2022-03-20 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-09 | 2022-04-10 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-05-21 | 2022-05-23 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-04-10 | 2022-04-12 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-24 | 2022-03-26 | 4
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-05-28 | 2022-05-30 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-05-29 | 2022-05-31 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-23 | 2022-03-28 | 1
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-28 | 2022-05-03 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-06-12 | 2022-06-13 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 6
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-28 | 2022-03-29 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 5
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-21 | 2022-03-22 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-03-28 | 2022-03-29 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-06-14 | 2022-06-15 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-04-07 | 2022-04-09 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-06-01 | 2022-06-03 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-27 | 2022-03-29 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-27 | 2022-03-29 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-21 | 2022-03-23 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-21 | 2022-03-23 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-09 | 2022-06-11 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-27 | 2022-06-29 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-20 | 2022-03-25 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-27 | 2022-04-01 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-01 | 2022-04-06 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-06-26 | 2022-07-01 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-07-01 | 2022-07-02 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-25 | 2022-03-26 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-05 | 2022-04-06 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-12 | 2022-04-13 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-30 | 2022-03-31 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-30 | 2022-03-31 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-07 | 2022-04-08 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-12 | 2022-04-13 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-07-01 | 2022-07-02 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-06-30 | 2022-07-02 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-06-26 | 2022-06-28 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-06-21 | 2022-06-23 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-06-24 | 2022-06-26 | 3
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-06 | 2022-04-08 | 3
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-04 | 2022-04-06 | 4
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-07-06 | 2022-07-08 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-07-04 | 2022-07-06 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-08 | 2022-04-13 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-14 | 2022-04-19 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-19 | 2022-04-24 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-07-02 | 2022-07-07 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-07-07 | 2022-07-08 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-16 | 2022-04-17 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-28 | 2022-04-29 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-29 | 2022-04-30 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-21 | 2022-04-22 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-19 | 2022-04-20 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-27 | 2022-04-28 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-12 | 2022-05-13 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-07-07 | 2022-07-08 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-03 | 2022-06-05 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-05 | 2022-06-07 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-01 | 2022-05-03 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-05-01 | 2022-05-03 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-13 | 2022-04-15 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-13 | 2022-04-15 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-07-07 | 2022-07-09 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-07-09 | 2022-07-11 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-25 | 2022-04-30 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-10 | 2022-05-15 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-05-17 | 2022-05-22 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-07-08 | 2022-07-13 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-07-13 | 2022-07-14 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-05-06 | 2022-05-07 | 6
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-16 | 2022-05-17 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-25 | 2022-06-26 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-05-05 | 2022-05-06 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-05-07 | 2022-05-08 | 5
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-16 | 2022-05-17 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-07-04 | 2022-07-05 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-13 | 2022-07-14 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-06-08 | 2022-06-10 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-06-21 | 2022-06-23 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-17 | 2022-05-19 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-17 | 2022-05-19 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-05-04 | 2022-05-06 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-05-04 | 2022-05-06 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-23 | 2022-07-25 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-14 | 2022-07-16 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-05-09 | 2022-05-14 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-27 | 2022-06-01 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-07-06 | 2022-07-11 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-14 | 2022-07-19 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-19 | 2022-07-20 | 5
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-18 | 2022-05-19 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-03 | 2022-06-04 | 6
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-11 | 2022-07-12 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-14 | 2022-05-15 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-18 | 2022-05-19 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-03 | 2022-06-04 | 5
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-11 | 2022-07-12 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-19 | 2022-07-20 | 6
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-07-11 | 2022-07-13 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-13 | 2022-07-15 | 3
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-17 | 2022-06-19 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-17 | 2022-06-19 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-14 | 2022-05-16 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-14 | 2022-05-16 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-20 | 2022-07-22 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-23 | 2022-07-25 | 3
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-19 | 2022-05-24 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-07 | 2022-06-12 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-07-12 | 2022-07-17 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-20 | 2022-07-25 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-25 | 2022-07-26 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-31 | 2022-06-01 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-15 | 2022-06-16 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-17 | 2022-07-18 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-27 | 2022-05-28 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-30 | 2022-05-31 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-19 | 2022-06-20 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-17 | 2022-07-18 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-25 | 2022-07-26 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-17 | 2022-07-19 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-18 | 2022-07-20 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-12 | 2022-06-14 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-12 | 2022-06-14 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-24 | 2022-05-26 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-24 | 2022-05-26 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-26 | 2022-07-28 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-26 | 2022-07-28 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-01 | 2022-06-06 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-06-20 | 2022-06-25 | 2
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-21 | 2022-07-26 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-26 | 2022-07-31 | 1

## Plan_D_61
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-14 | 2022-03-19 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-04-05 | 2022-04-10 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-10 | 2022-04-11 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-08 | 2022-03-09 | 6
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-14 | 2022-03-15 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-20 | 2022-03-21 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-09 | 2022-03-10 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 5
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-12 | 2022-04-13 | 5
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-04-17 | 2022-04-19 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-06-02 | 2022-06-04 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-09 | 2022-03-11 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-09 | 2022-03-11 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-07-27 | 2022-07-29 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-06-18 | 2022-06-20 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-11 | 2022-03-16 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-21 | 2022-03-26 | 2
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-27 | 2022-04-01 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-20 | 2022-04-25 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-28 | 2022-04-29 | 6
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-04-11 | 2022-04-12 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-21 | 2022-04-22 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-18 | 2022-03-19 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-16 | 2022-03-17 | 6
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-31 | 2022-04-01 | 6
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-21 | 2022-04-22 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-28 | 2022-04-29 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-06-15 | 2022-06-17 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-06-04 | 2022-06-06 | 4
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-26 | 2022-03-28 | 3
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-26 | 2022-03-28 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-23 | 2022-03-25 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-23 | 2022-03-25 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-06-17 | 2022-06-19 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-06-20 | 2022-06-22 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-04-14 | 2022-04-19 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-26 | 2022-05-01 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-05-04 | 2022-05-09 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-06-16 | 2022-06-17 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-24 | 2022-03-25 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-19 | 2022-04-20 | 5
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-05-17 | 2022-05-18 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-26 | 2022-03-27 | 6
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-05-01 | 2022-05-02 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-05-17 | 2022-05-18 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-06-16 | 2022-06-17 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-07-01 | 2022-07-03 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-06-30 | 2022-07-02 | 3
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-19 | 2022-04-21 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-20 | 2022-04-22 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-04-05 | 2022-04-07 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-04-05 | 2022-04-07 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-07-27 | 2022-07-29 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-07-06 | 2022-07-08 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-27 | 2022-04-01 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-05-03 | 2022-05-08 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-05-18 | 2022-05-23 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-06-19 | 2022-06-24 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-06-26 | 2022-06-27 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-03 | 2022-04-04 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-05-12 | 2022-05-13 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-06-11 | 2022-06-12 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-01 | 2022-04-02 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-03 | 2022-04-04 | 5
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-05-20 | 2022-05-21 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-05-31 | 2022-06-01 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-06-26 | 2022-06-27 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-06-28 | 2022-06-30 | 4
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-06-23 | 2022-06-25 | 3
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-05-08 | 2022-05-10 | 3
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-05-08 | 2022-05-10 | 4
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-08 | 2022-04-10 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-08 | 2022-04-10 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-07-04 | 2022-07-06 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-07-09 | 2022-07-11 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-07 | 2022-04-12 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-05-24 | 2022-05-29 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-06-14 | 2022-06-19 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-06-28 | 2022-07-03 | 2
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-07-05 | 2022-07-06 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-05-14 | 2022-05-15 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-29 | 2022-05-30 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-06-20 | 2022-06-21 | 6
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-05-02 | 2022-05-03 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-18 | 2022-04-19 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-29 | 2022-05-30 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-06-20 | 2022-06-21 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-07-12 | 2022-07-13 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-07-07 | 2022-07-09 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-07-03 | 2022-07-05 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-05-30 | 2022-06-01 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-05-30 | 2022-06-01 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-12 | 2022-04-14 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-12 | 2022-04-14 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-07-11 | 2022-07-13 | 4
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-07-14 | 2022-07-16 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-05-19 | 2022-05-24 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-30 | 2022-06-04 | 2
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-06-21 | 2022-06-26 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-07-13 | 2022-07-18 | 2
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-07-18 | 2022-07-19 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-27 | 2022-05-28 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-06-05 | 2022-06-06 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-07-02 | 2022-07-03 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-25 | 2022-05-26 | 6
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-24 | 2022-05-25 | 5
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-06-05 | 2022-06-06 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-07-01 | 2022-07-02 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-07-18 | 2022-07-19 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-06-27 | 2022-06-29 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-07-15 | 2022-07-17 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-06-12 | 2022-06-14 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-06-23 | 2022-06-25 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-06-05 | 2022-06-07 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-24 | 2022-05-26 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-07-18 | 2022-07-20 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-07-18 | 2022-07-20 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-31 | 2022-06-05 | 1
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-06-06 | 2022-06-11 | 1
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-07-03 | 2022-07-08 | 1
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-07-19 | 2022-07-24 | 1
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-07-26 | 2022-07-27 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-06-07 | 2022-06-08 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-06-22 | 2022-06-23 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-07-21 | 2022-07-22 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-06-07 | 2022-06-08 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-06-14 | 2022-06-15 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-06-22 | 2022-06-23 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-07-21 | 2022-07-22 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-07-26 | 2022-07-27 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-07-21 | 2022-07-23 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-07-21 | 2022-07-23 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-14 | 2022-06-16 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-06-11 | 2022-06-13 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-06-08 | 2022-06-10 | 4
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-06-09 | 2022-06-11 | 3
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-07-24 | 2022-07-26 | 4
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-07-24 | 2022-07-26 | 3
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-06-27 | 2022-07-02 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-07-13 | 2022-07-18 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-07-22 | 2022-07-27 | 2
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-07-27 | 2022-08-01 | 1

## Plan_D_7
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-22 | 2022-03-27 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-01 | 2022-04-02 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-24 | 2022-03-25 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-01 | 2022-04-02 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-19 | 2022-03-21 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-19 | 2022-03-21 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-08 | 2022-03-10 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-08 | 2022-03-10 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-28 | 2022-03-30 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-03-28 | 2022-03-30 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-25 | 2022-03-30 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-03 | 2022-04-08 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-11 | 2022-04-12 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-30 | 2022-03-31 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-29 | 2022-03-30 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-04 | 2022-04-05 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-11 | 2022-04-12 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-31 | 2022-04-02 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-03-31 | 2022-04-02 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-22 | 2022-03-24 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-22 | 2022-03-24 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-16 | 2022-03-18 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-16 | 2022-03-18 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-09 | 2022-04-11 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-04-09 | 2022-04-11 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-31 | 2022-04-05 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-06 | 2022-04-11 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-12 | 2022-04-17 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-04-19 | 2022-04-20 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-26 | 2022-03-27 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-07 | 2022-04-08 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-13 | 2022-04-14 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-26 | 2022-03-27 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-07 | 2022-04-08 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-13 | 2022-04-14 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-04-19 | 2022-04-20 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-12 | 2022-04-14 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-12 | 2022-04-14 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-06 | 2022-04-08 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-06 | 2022-04-08 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-25 | 2022-03-27 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-25 | 2022-03-27 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-04-18 | 2022-04-20 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-04-18 | 2022-04-20 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-09 | 2022-04-14 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-15 | 2022-04-20 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-04-21 | 2022-04-26 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-05 | 2022-05-06 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-04 | 2022-04-05 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-21 | 2022-04-22 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-28 | 2022-04-29 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-15 | 2022-04-16 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-15 | 2022-04-16 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-21 | 2022-04-22 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-28 | 2022-04-29 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-07 | 2022-05-08 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-21 | 2022-04-23 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-21 | 2022-04-23 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-15 | 2022-04-17 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-15 | 2022-04-17 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-03 | 2022-04-05 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-03 | 2022-04-05 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-04-27 | 2022-04-29 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-04-27 | 2022-04-29 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-18 | 2022-04-23 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-24 | 2022-04-29 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-30 | 2022-05-05 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-09 | 2022-05-14 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-18 | 2022-05-19 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-23 | 2022-04-24 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-01 | 2022-05-02 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-07 | 2022-05-08 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-23 | 2022-04-24 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-25 | 2022-04-26 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-01 | 2022-05-02 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-13 | 2022-05-14 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-15 | 2022-05-16 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-06 | 2022-05-08 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-06 | 2022-05-08 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-30 | 2022-05-02 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-30 | 2022-05-02 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-24 | 2022-04-26 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-24 | 2022-04-26 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-14 | 2022-05-16 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-05-14 | 2022-05-16 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-27 | 2022-05-02 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-03 | 2022-05-08 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-15 | 2022-05-20 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-21 | 2022-05-26 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-05-29 | 2022-05-30 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-05 | 2022-05-06 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-10 | 2022-05-11 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-20 | 2022-05-21 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-03 | 2022-05-04 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-03 | 2022-05-04 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-10 | 2022-05-11 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-27 | 2022-05-28 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-05-29 | 2022-05-30 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-25 | 2022-05-27 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-24 | 2022-05-26 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-09 | 2022-05-11 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-09 | 2022-05-11 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-03 | 2022-05-05 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-03 | 2022-05-05 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-05-31 | 2022-06-02 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-05-31 | 2022-06-02 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-06 | 2022-05-11 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-14 | 2022-05-19 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-28 | 2022-06-02 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-03 | 2022-06-08 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-08 | 2022-06-09 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-15 | 2022-05-16 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-20 | 2022-05-21 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-02 | 2022-06-03 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-18 | 2022-05-19 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-13 | 2022-05-14 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-25 | 2022-05-26 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-02 | 2022-06-03 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-08 | 2022-06-09 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-06 | 2022-06-08 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-06 | 2022-06-08 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-28 | 2022-05-30 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-28 | 2022-05-30 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-19 | 2022-05-21 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-19 | 2022-05-21 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-09 | 2022-06-11 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-09 | 2022-06-11 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-22 | 2022-05-27 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-29 | 2022-06-03 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-04 | 2022-06-09 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-09 | 2022-06-14 | 2

## Plan_D_8
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-22 | 2022-03-27 | 1
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-04-01 | 2022-04-02 | 5
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-13 | 2022-03-14 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-24 | 2022-03-25 | 5
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 5
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-07 | 2022-03-08 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-13 | 2022-03-14 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 5
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-04-01 | 2022-04-02 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-19 | 2022-03-21 | 4
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-19 | 2022-03-21 | 3
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-12 | 2022-03-14 | 3
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-12 | 2022-03-14 | 4
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-08 | 2022-03-10 | 3
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-08 | 2022-03-10 | 4
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-28 | 2022-03-30 | 4
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-03-28 | 2022-03-30 | 3
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-25 | 2022-03-30 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-04-03 | 2022-04-08 | 1
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-11 | 2022-04-12 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-17 | 2022-03-18 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-21 | 2022-03-22 | 6
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-03-30 | 2022-03-31 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-15 | 2022-03-16 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-15 | 2022-03-16 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-29 | 2022-03-30 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-04 | 2022-04-05 | 6
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-11 | 2022-04-12 | 6
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-31 | 2022-04-02 | 4
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-03-31 | 2022-04-02 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-22 | 2022-03-24 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-22 | 2022-03-24 | 3
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-16 | 2022-03-18 | 3
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-16 | 2022-03-18 | 4
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-09 | 2022-04-11 | 4
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-04-09 | 2022-04-11 | 3
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-19 | 2022-03-24 | 2
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-31 | 2022-04-05 | 2
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-06 | 2022-04-11 | 2
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-12 | 2022-04-17 | 2
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-04-19 | 2022-04-20 | 6
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-03-26 | 2022-03-27 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-07 | 2022-04-08 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-13 | 2022-04-14 | 6
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-26 | 2022-03-27 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-03-24 | 2022-03-25 | 6
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-07 | 2022-04-08 | 5
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-13 | 2022-04-14 | 5
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-04-19 | 2022-04-20 | 5
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-12 | 2022-04-14 | 3
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-12 | 2022-04-14 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-06 | 2022-04-08 | 3
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-06 | 2022-04-08 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-25 | 2022-03-27 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-25 | 2022-03-27 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-04-18 | 2022-04-20 | 4
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-04-18 | 2022-04-20 | 3
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-03-28 | 2022-04-02 | 1
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-09 | 2022-04-14 | 1
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-15 | 2022-04-20 | 1
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-04-21 | 2022-04-26 | 1
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-05 | 2022-05-06 | 6
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-04 | 2022-04-05 | 5
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-21 | 2022-04-22 | 5
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-28 | 2022-04-29 | 6
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-15 | 2022-04-16 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-15 | 2022-04-16 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-21 | 2022-04-22 | 6
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-28 | 2022-04-29 | 5
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-05-07 | 2022-05-08 | 6
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-21 | 2022-04-23 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-04-21 | 2022-04-23 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-15 | 2022-04-17 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-15 | 2022-04-17 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-03 | 2022-04-05 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-03 | 2022-04-05 | 4
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-04-27 | 2022-04-29 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-04-27 | 2022-04-29 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-18 | 2022-04-23 | 2
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-24 | 2022-04-29 | 2
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-30 | 2022-05-05 | 2
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-09 | 2022-05-14 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-18 | 2022-05-19 | 6
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-23 | 2022-04-24 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-05-01 | 2022-05-02 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-07 | 2022-05-08 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-23 | 2022-04-24 | 6
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-25 | 2022-04-26 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-05-01 | 2022-05-02 | 5
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-13 | 2022-05-14 | 5
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-15 | 2022-05-16 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-06 | 2022-05-08 | 3
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-06 | 2022-05-08 | 4
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-30 | 2022-05-02 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-30 | 2022-05-02 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-24 | 2022-04-26 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-24 | 2022-04-26 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-05-14 | 2022-05-16 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-05-14 | 2022-05-16 | 4
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-27 | 2022-05-02 | 1
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-03 | 2022-05-08 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-15 | 2022-05-20 | 1
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-21 | 2022-05-26 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-05-29 | 2022-05-30 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-05 | 2022-05-06 | 5
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-10 | 2022-05-11 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-20 | 2022-05-21 | 5
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-03 | 2022-05-04 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-03 | 2022-05-04 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-10 | 2022-05-11 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-27 | 2022-05-28 | 6
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-05-29 | 2022-05-30 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-25 | 2022-05-27 | 3
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-24 | 2022-05-26 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-09 | 2022-05-11 | 3
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-09 | 2022-05-11 | 4
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-03 | 2022-05-05 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-03 | 2022-05-05 | 4
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-05-31 | 2022-06-02 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-05-31 | 2022-06-02 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-06 | 2022-05-11 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-14 | 2022-05-19 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-28 | 2022-06-02 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-03 | 2022-06-08 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-08 | 2022-06-09 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-15 | 2022-05-16 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-20 | 2022-05-21 | 6
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-02 | 2022-06-03 | 6
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-18 | 2022-05-19 | 5
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-13 | 2022-05-14 | 6
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-25 | 2022-05-26 | 5
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-02 | 2022-06-03 | 5
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-08 | 2022-06-09 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-06 | 2022-06-08 | 3
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-06 | 2022-06-08 | 4
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-05-28 | 2022-05-30 | 3
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-28 | 2022-05-30 | 4
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-19 | 2022-05-21 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-19 | 2022-05-21 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-09 | 2022-06-11 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-09 | 2022-06-11 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-22 | 2022-05-27 | 2
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-29 | 2022-06-03 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-04 | 2022-06-09 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-09 | 2022-06-14 | 2

## Plan_D_9
ID | Task_name | Contractor | Level | Zone | GUID | Planned_start | Planned_end | Assigned_crew
4274bd6f-ed45-11ec-bbe0-f40228892bcc | IfcSlab | 0 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtf | 2022-03-02 | 2022-03-07 | 1
4277557d-ed45-11ec-bd22-f40228892bcc | IfcSlab | 0 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtk | 2022-03-07 | 2022-03-12 | 2
4279c681-ed45-11ec-9e9d-f40228892bcc | IfcSlab | 0 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtd | 2022-03-13 | 2022-03-18 | 2
427be976-ed45-11ec-ad6c-f40228892bcc | IfcSlab | 0 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtS | 2022-03-19 | 2022-03-24 | 2
427e335e-ed45-11ec-bf86-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtJ | 2022-03-26 | 2022-03-27 | 6
42802f14-ed45-11ec-883d-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmtI | 2022-03-09 | 2022-03-10 | 5
428254e7-ed45-11ec-aa13-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtL | 2022-03-14 | 2022-03-15 | 5
428450c7-ed45-11ec-9cdd-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtK | 2022-03-23 | 2022-03-24 | 6
42864c82-ed45-11ec-ac26-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt9 | 2022-03-07 | 2022-03-08 | 6
428847de-ed45-11ec-961e-f40228892bcc | IfcColumn | 1 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt8 | 2022-03-09 | 2022-03-10 | 6
428a443c-ed45-11ec-b698-f40228892bcc | IfcColumn | 1 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtB | 2022-03-14 | 2022-03-15 | 6
428c416a-ed45-11ec-ad55-f40228892bcc | IfcColumn | 1 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtA | 2022-03-20 | 2022-03-21 | 6
428e6447-ed45-11ec-9011-f40228892bcc | IfcColumn | 1 | 0 | D | 2QUZHvxvTDdvGHPJrzsmtD | 2022-03-29 | 2022-03-30 | 6
42906038-ed45-11ec-b64e-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtC | 2022-03-19 | 2022-03-21 | 3
42919a38-ed45-11ec-bd95-f40228892bcc | IfcWall | 2 | 0 | C | 2QUZHvxvTDdvGHPJrzsmtF | 2022-03-19 | 2022-03-21 | 4
4292fa3b-ed45-11ec-8256-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmtE | 2022-03-13 | 2022-03-15 | 4
4294329f-ed45-11ec-845d-f40228892bcc | IfcWall | 2 | 0 | B | 2QUZHvxvTDdvGHPJrzsmt1 | 2022-03-13 | 2022-03-15 | 3
42958303-ed45-11ec-9a3b-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt0 | 2022-03-08 | 2022-03-10 | 4
4296bb7f-ed45-11ec-a971-f40228892bcc | IfcWall | 2 | 0 | A | 2QUZHvxvTDdvGHPJrzsmt3 | 2022-03-08 | 2022-03-10 | 3
42981b1f-ed45-11ec-b487-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt2 | 2022-03-25 | 2022-03-27 | 3
42997aa0-ed45-11ec-965f-f40228892bcc | IfcWall | 2 | 0 | D | 2QUZHvxvTDdvGHPJrzsmt5 | 2022-04-09 | 2022-04-11 | 4
429ae964-ed45-11ec-af39-f40228892bcc | IfcSlab | 0 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9s | 2022-03-10 | 2022-03-15 | 1
429cf549-ed45-11ec-8b22-f40228892bcc | IfcSlab | 0 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9l | 2022-03-16 | 2022-03-21 | 1
429f1887-ed45-11ec-8eb4-f40228892bcc | IfcSlab | 0 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9a | 2022-03-25 | 2022-03-30 | 2
42a1153c-ed45-11ec-a2e3-f40228892bcc | IfcSlab | 0 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9T | 2022-03-31 | 2022-04-05 | 2
42a339d6-ed45-11ec-a2d5-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm9G | 2022-04-07 | 2022-04-08 | 5
42a535a2-ed45-11ec-ac49-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9J | 2022-03-20 | 2022-03-21 | 5
42a73193-ed45-11ec-b9aa-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9I | 2022-03-26 | 2022-03-27 | 5
42a92d46-ed45-11ec-a1a5-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9L | 2022-04-01 | 2022-04-02 | 6
42ab2947-ed45-11ec-8888-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9K | 2022-03-17 | 2022-03-18 | 6
42ad24ed-ed45-11ec-aac8-f40228892bcc | IfcColumn | 1 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9N | 2022-03-17 | 2022-03-18 | 5
42af226c-ed45-11ec-bad4-f40228892bcc | IfcColumn | 1 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9M | 2022-03-23 | 2022-03-24 | 5
42b14593-ed45-11ec-904a-f40228892bcc | IfcColumn | 1 | 1 | C | 2QUZHvxvTDdvGHPJrzsm99 | 2022-04-01 | 2022-04-02 | 5
42b31c19-ed45-11ec-a523-f40228892bcc | IfcColumn | 1 | 1 | D | 2QUZHvxvTDdvGHPJrzsm98 | 2022-04-05 | 2022-04-06 | 5
42b53eee-ed45-11ec-9f70-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9B | 2022-03-31 | 2022-04-02 | 3
42b6778f-ed45-11ec-a482-f40228892bcc | IfcWall | 2 | 1 | C | 2QUZHvxvTDdvGHPJrzsm9A | 2022-04-03 | 2022-04-05 | 3
42b7aff7-ed45-11ec-abbe-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9D | 2022-03-25 | 2022-03-27 | 4
42b90fc8-ed45-11ec-b802-f40228892bcc | IfcWall | 2 | 1 | B | 2QUZHvxvTDdvGHPJrzsm9C | 2022-03-22 | 2022-03-24 | 4
42ba4834-ed45-11ec-9dfe-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9F | 2022-03-16 | 2022-03-18 | 4
42bba777-ed45-11ec-8b8c-f40228892bcc | IfcWall | 2 | 1 | A | 2QUZHvxvTDdvGHPJrzsm9E | 2022-03-16 | 2022-03-18 | 3
42bce015-ed45-11ec-a6d6-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm91 | 2022-04-06 | 2022-04-08 | 3
42be1874-ed45-11ec-b758-f40228892bcc | IfcWall | 2 | 1 | D | 2QUZHvxvTDdvGHPJrzsm90 | 2022-04-06 | 2022-04-08 | 4
42bf529f-ed45-11ec-a413-f40228892bcc | IfcSlab | 0 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0q | 2022-03-22 | 2022-03-27 | 1
42c1770b-ed45-11ec-9ed9-f40228892bcc | IfcSlab | 0 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0j | 2022-03-28 | 2022-04-02 | 1
42c398a4-ed45-11ec-ad4b-f40228892bcc | IfcSlab | 0 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0Y | 2022-04-03 | 2022-04-08 | 1
42c5bcd5-ed45-11ec-bd6c-f40228892bcc | IfcSlab | 0 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0R | 2022-04-09 | 2022-04-14 | 1
42c7b8a4-ed45-11ec-94b7-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0U | 2022-04-16 | 2022-04-17 | 5
42c9b62f-ed45-11ec-b4e0-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0H | 2022-04-03 | 2022-04-04 | 6
42cbb20b-ed45-11ec-a3a5-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0G | 2022-04-07 | 2022-04-08 | 6
42cdd3d0-ed45-11ec-a8e5-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0J | 2022-04-10 | 2022-04-11 | 5
42cfd0ef-ed45-11ec-8ded-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0I | 2022-03-29 | 2022-03-30 | 5
42d1ce86-ed45-11ec-9c15-f40228892bcc | IfcColumn | 1 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0L | 2022-04-03 | 2022-04-04 | 5
42d3f0ec-ed45-11ec-9019-f40228892bcc | IfcColumn | 1 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0K | 2022-04-05 | 2022-04-06 | 6
42d5ebfc-ed45-11ec-bee3-f40228892bcc | IfcColumn | 1 | 2 | C | 2QUZHvxvTDdvGHPJrzsm0N | 2022-04-10 | 2022-04-11 | 6
42d8103f-ed45-11ec-a5a9-f40228892bcc | IfcColumn | 1 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0M | 2022-04-16 | 2022-04-17 | 6
42da0be9-ed45-11ec-bcdf-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm09 | 2022-04-18 | 2022-04-20 | 4
42db4436-ed45-11ec-8428-f40228892bcc | IfcWall | 2 | 2 | C | 2QUZHvxvTDdvGHPJrzsm08 | 2022-04-15 | 2022-04-17 | 4
42dca3fc-ed45-11ec-baff-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0B | 2022-04-12 | 2022-04-14 | 4
42ddde2b-ed45-11ec-900b-f40228892bcc | IfcWall | 2 | 2 | B | 2QUZHvxvTDdvGHPJrzsm0A | 2022-04-02 | 2022-04-04 | 4
42df16ad-ed45-11ec-b947-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0D | 2022-03-28 | 2022-03-30 | 4
42e050e1-ed45-11ec-b819-f40228892bcc | IfcWall | 2 | 2 | A | 2QUZHvxvTDdvGHPJrzsm0C | 2022-03-28 | 2022-03-30 | 3
42e1b080-ed45-11ec-9532-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0F | 2022-04-21 | 2022-04-23 | 3
42e2e8ed-ed45-11ec-9efb-f40228892bcc | IfcWall | 2 | 2 | D | 2QUZHvxvTDdvGHPJrzsm0E | 2022-04-27 | 2022-04-29 | 4
42e44883-ed45-11ec-9f83-f40228892bcc | IfcSlab | 0 | 3 | A | 2QUZHvxvTDdvGHPJrzsm1K | 2022-04-06 | 2022-04-11 | 2
42e645fb-ed45-11ec-9c49-f40228892bcc | IfcSlab | 0 | 3 | B | 2QUZHvxvTDdvGHPJrzsm1D | 2022-04-12 | 2022-04-17 | 2
42e88f18-ed45-11ec-bf3b-f40228892bcc | IfcSlab | 0 | 3 | C | 2QUZHvxvTDdvGHPJrzsm12 | 2022-04-18 | 2022-04-23 | 2
42eab342-ed45-11ec-8f7e-f40228892bcc | IfcSlab | 0 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2x | 2022-04-24 | 2022-04-29 | 2
42ecb0b6-ed45-11ec-8e40-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2_ | 2022-05-02 | 2022-05-03 | 5
42eeae28-ed45-11ec-b730-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2n | 2022-04-14 | 2022-04-15 | 6
42f0a913-ed45-11ec-b27e-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2m | 2022-04-19 | 2022-04-20 | 6
42f2a5de-ed45-11ec-87d9-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2p | 2022-04-25 | 2022-04-26 | 5
42f4ca38-ed45-11ec-bcfd-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2o | 2022-04-13 | 2022-04-14 | 5
42f6c915-ed45-11ec-8cc5-f40228892bcc | IfcColumn | 1 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2r | 2022-04-12 | 2022-04-13 | 6
42f8c6b5-ed45-11ec-962f-f40228892bcc | IfcColumn | 1 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2q | 2022-04-19 | 2022-04-20 | 5
42fac136-ed45-11ec-8e69-f40228892bcc | IfcColumn | 1 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2t | 2022-04-25 | 2022-04-26 | 6
42fce6e9-ed45-11ec-95f7-f40228892bcc | IfcColumn | 1 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2s | 2022-04-30 | 2022-05-01 | 5
42fee4a8-ed45-11ec-837b-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2f | 2022-04-24 | 2022-04-26 | 3
43004422-ed45-11ec-9e0c-f40228892bcc | IfcWall | 2 | 3 | C | 2QUZHvxvTDdvGHPJrzsm2e | 2022-05-03 | 2022-05-05 | 4
43017c9c-ed45-11ec-af37-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2h | 2022-04-21 | 2022-04-23 | 4
4302b51e-ed45-11ec-a304-f40228892bcc | IfcWall | 2 | 3 | B | 2QUZHvxvTDdvGHPJrzsm2g | 2022-04-18 | 2022-04-20 | 3
4304168b-ed45-11ec-a6d3-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2j | 2022-04-11 | 2022-04-13 | 3
43054ed2-ed45-11ec-9cbb-f40228892bcc | IfcWall | 2 | 3 | A | 2QUZHvxvTDdvGHPJrzsm2i | 2022-04-15 | 2022-04-17 | 3
4306b19b-ed45-11ec-9455-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2l | 2022-05-06 | 2022-05-08 | 4
4307ea19-ed45-11ec-ac4b-f40228892bcc | IfcWall | 2 | 3 | D | 2QUZHvxvTDdvGHPJrzsm2k | 2022-05-14 | 2022-05-16 | 3
4309229c-ed45-11ec-94c1-f40228892bcc | IfcSlab | 0 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3q | 2022-04-15 | 2022-04-20 | 1
430b4720-ed45-11ec-a977-f40228892bcc | IfcSlab | 0 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3j | 2022-04-21 | 2022-04-26 | 1
430d6bde-ed45-11ec-a262-f40228892bcc | IfcSlab | 0 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3Y | 2022-04-27 | 2022-05-02 | 1
430f8e7e-ed45-11ec-881a-f40228892bcc | IfcSlab | 0 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3R | 2022-05-03 | 2022-05-08 | 1
4311b013-ed45-11ec-a8e7-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3U | 2022-05-21 | 2022-05-22 | 5
4313d5d8-ed45-11ec-93a3-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3H | 2022-04-27 | 2022-04-28 | 5
43160dda-ed45-11ec-a4ad-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3G | 2022-04-28 | 2022-04-29 | 6
43183212-ed45-11ec-8838-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3J | 2022-05-07 | 2022-05-08 | 5
431a3d1f-ed45-11ec-9e37-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3I | 2022-04-22 | 2022-04-23 | 5
431c392e-ed45-11ec-a55a-f40228892bcc | IfcColumn | 1 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3L | 2022-04-22 | 2022-04-23 | 6
431e83ac-ed45-11ec-a19e-f40228892bcc | IfcColumn | 1 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3K | 2022-04-30 | 2022-05-01 | 6
43208088-ed45-11ec-9a0e-f40228892bcc | IfcColumn | 1 | 4 | C | 2QUZHvxvTDdvGHPJrzsm3N | 2022-05-02 | 2022-05-03 | 6
4322f18a-ed45-11ec-a798-f40228892bcc | IfcColumn | 1 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3M | 2022-05-21 | 2022-05-22 | 6
43253e68-ed45-11ec-a625-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm39 | 2022-05-12 | 2022-05-14 | 4
43269df9-ed45-11ec-94a7-f40228892bcc | IfcWall | 2 | 4 | C | 2QUZHvxvTDdvGHPJrzsm38 | 2022-05-03 | 2022-05-05 | 3
4327fd89-ed45-11ec-94f9-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3B | 2022-04-30 | 2022-05-02 | 3
43295d80-ed45-11ec-b2a4-f40228892bcc | IfcWall | 2 | 4 | B | 2QUZHvxvTDdvGHPJrzsm3A | 2022-04-30 | 2022-05-02 | 4
432a961e-ed45-11ec-aa4a-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3D | 2022-04-27 | 2022-04-29 | 3
432bf5a1-ed45-11ec-85d4-f40228892bcc | IfcWall | 2 | 4 | A | 2QUZHvxvTDdvGHPJrzsm3C | 2022-04-24 | 2022-04-26 | 4
432d5806-ed45-11ec-bf72-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3F | 2022-06-01 | 2022-06-03 | 3
432e925a-ed45-11ec-814d-f40228892bcc | IfcWall | 2 | 4 | D | 2QUZHvxvTDdvGHPJrzsm3E | 2022-05-17 | 2022-05-19 | 3
432fcaf1-ed45-11ec-b707-f40228892bcc | IfcSlab | 0 | 5 | A | 2QUZHvxvTDdvGHPJrzsm4K | 2022-04-30 | 2022-05-05 | 2
4331efc5-ed45-11ec-8c32-f40228892bcc | IfcSlab | 0 | 5 | B | 2QUZHvxvTDdvGHPJrzsm4D | 2022-05-09 | 2022-05-14 | 1
43341272-ed45-11ec-9bd8-f40228892bcc | IfcSlab | 0 | 5 | C | 2QUZHvxvTDdvGHPJrzsm42 | 2022-05-14 | 2022-05-19 | 2
4336352e-ed45-11ec-aca7-f40228892bcc | IfcSlab | 0 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5x | 2022-05-23 | 2022-05-28 | 1
43388104-ed45-11ec-8999-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5_ | 2022-05-30 | 2022-05-31 | 6
433a8eb6-ed45-11ec-88d0-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5n | 2022-05-07 | 2022-05-08 | 6
433c8052-ed45-11ec-8e44-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5m | 2022-05-18 | 2022-05-19 | 5
433e7c0b-ed45-11ec-9952-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5p | 2022-05-24 | 2022-05-25 | 6
4340796c-ed45-11ec-a81a-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5o | 2022-05-05 | 2022-05-06 | 5
43427562-ed45-11ec-bced-f40228892bcc | IfcColumn | 1 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5r | 2022-05-05 | 2022-05-06 | 6
43444a16-ed45-11ec-a6d2-f40228892bcc | IfcColumn | 1 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5q | 2022-05-18 | 2022-05-19 | 6
434693e3-ed45-11ec-beb1-f40228892bcc | IfcColumn | 1 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5t | 2022-05-24 | 2022-05-25 | 5
43488e87-ed45-11ec-9ec7-f40228892bcc | IfcColumn | 1 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5s | 2022-05-30 | 2022-05-31 | 5
434ab435-ed45-11ec-8f59-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5f | 2022-05-26 | 2022-05-28 | 4
434bec9f-ed45-11ec-9519-f40228892bcc | IfcWall | 2 | 5 | C | 2QUZHvxvTDdvGHPJrzsm5e | 2022-05-23 | 2022-05-25 | 4
434d4c5e-ed45-11ec-a8c4-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5h | 2022-05-17 | 2022-05-19 | 4
434e84c8-ed45-11ec-9290-f40228892bcc | IfcWall | 2 | 5 | B | 2QUZHvxvTDdvGHPJrzsm5g | 2022-05-20 | 2022-05-22 | 3
434fbf06-ed45-11ec-9dc3-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5j | 2022-05-06 | 2022-05-08 | 3
4350f7aa-ed45-11ec-99f5-f40228892bcc | IfcWall | 2 | 5 | A | 2QUZHvxvTDdvGHPJrzsm5i | 2022-05-11 | 2022-05-13 | 3
43525930-ed45-11ec-860f-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5l | 2022-05-29 | 2022-05-31 | 3
43539148-ed45-11ec-8e71-f40228892bcc | IfcWall | 2 | 5 | D | 2QUZHvxvTDdvGHPJrzsm5k | 2022-05-29 | 2022-05-31 | 4
4354f109-ed45-11ec-8952-f40228892bcc | IfcSlab | 0 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6q | 2022-05-08 | 2022-05-13 | 2
4357154d-ed45-11ec-9155-f40228892bcc | IfcSlab | 0 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6j | 2022-05-20 | 2022-05-25 | 2
435939e4-ed45-11ec-aac5-f40228892bcc | IfcSlab | 0 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6Y | 2022-05-26 | 2022-05-31 | 2
435b374f-ed45-11ec-9a9d-f40228892bcc | IfcSlab | 0 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6R | 2022-06-01 | 2022-06-06 | 2
435d5a41-ed45-11ec-ac3c-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6U | 2022-06-08 | 2022-06-09 | 6
435f57b4-ed45-11ec-a5fb-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6H | 2022-05-15 | 2022-05-16 | 5
4361552f-ed45-11ec-8d97-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6G | 2022-05-27 | 2022-05-28 | 5
436350f4-ed45-11ec-8317-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6J | 2022-06-02 | 2022-06-03 | 5
43654cb4-ed45-11ec-9bba-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6I | 2022-05-13 | 2022-05-14 | 6
43674a16-ed45-11ec-bdf3-f40228892bcc | IfcColumn | 1 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6L | 2022-05-13 | 2022-05-14 | 5
4369479f-ed45-11ec-9e24-f40228892bcc | IfcColumn | 1 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6K | 2022-05-27 | 2022-05-28 | 6
436b6a4a-ed45-11ec-9ad2-f40228892bcc | IfcColumn | 1 | 6 | C | 2QUZHvxvTDdvGHPJrzsm6N | 2022-06-02 | 2022-06-03 | 6
436d7df7-ed45-11ec-a8bd-f40228892bcc | IfcColumn | 1 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6M | 2022-06-08 | 2022-06-09 | 5
436f896e-ed45-11ec-8576-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm69 | 2022-06-04 | 2022-06-06 | 4
4370c4dc-ed45-11ec-942a-f40228892bcc | IfcWall | 2 | 6 | C | 2QUZHvxvTDdvGHPJrzsm68 | 2022-06-04 | 2022-06-06 | 3
4371fd59-ed45-11ec-bf2a-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6B | 2022-06-01 | 2022-06-03 | 4
43735d13-ed45-11ec-af97-f40228892bcc | IfcWall | 2 | 6 | B | 2QUZHvxvTDdvGHPJrzsm6A | 2022-05-26 | 2022-05-28 | 3
437495bb-ed45-11ec-8acd-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6D | 2022-05-23 | 2022-05-25 | 3
4375f50d-ed45-11ec-89cf-f40228892bcc | IfcWall | 2 | 6 | A | 2QUZHvxvTDdvGHPJrzsm6C | 2022-05-20 | 2022-05-22 | 4
43772d98-ed45-11ec-851a-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6F | 2022-06-07 | 2022-06-09 | 3
43788ecb-ed45-11ec-b72f-f40228892bcc | IfcWall | 2 | 6 | D | 2QUZHvxvTDdvGHPJrzsm6E | 2022-06-07 | 2022-06-09 | 4
4379ee57-ed45-11ec-b90c-f40228892bcc | IfcSlab | 0 | 7 | A | 2QUZHvxvTDdvGHPJrzsmOL | 2022-05-17 | 2022-05-22 | 1
437c0ffe-ed45-11ec-a045-f40228892bcc | IfcSlab | 0 | 7 | B | 2QUZHvxvTDdvGHPJrzsmOA | 2022-05-29 | 2022-06-03 | 1
437e0d3f-ed45-11ec-80d9-f40228892bcc | IfcSlab | 0 | 7 | C | 2QUZHvxvTDdvGHPJrzsmO3 | 2022-06-04 | 2022-06-09 | 1
43803086-ed45-11ec-a505-f40228892bcc | IfcSlab | 0 | 7 | D | 2QUZHvxvTDdvGHPJrzsmPu | 2022-06-09 | 2022-06-14 | 2